## Slide 1
ISO 45001 Certification Plan
Free Gantt chart template · gantts.app

## Slide 2
ISO 45001 Certification Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Scope, context & gap analysis
Define OH&S management system scope
Context, workers & interested parties analysis
Gap analysis against ISO 45001
OH&S policy drafted & approved
Certification body selection & audit booking
◆ Scope and OH&S policy approved
Hazard identification & risk assessment
Activity, task & process mapping across sites
Identify hazards — routine operations
Identify hazards — non-routine, maintenance & emergency
Risk assessment & hierarchy of controls applied
Legal & other OH&S requirements register build
◆ Hazard and risk registers approved
Worker consultation & participation
Elect worker OH&S representatives
Health & safety committee terms of reference
Health & safety committee meeting cycle
Worker consultation on hazard identification
Remove barriers to worker participation
Worker consultation on draft OH&S objectives
◆ Consultation arrangements operating
Objectives, operational control & emergency preparedness
Derive OH&S objectives, targets & owners
Operational control procedures for high-risk tasks
Permit to work & contractor control system
Competence, training & induction rollout
Emergency preparedness plan & evacuation drill
◆ Operational controls and drill complete
Operate, record incidents & near-misses
Operate OH&S system & collect performance data
Incident, injury & near-miss reporting drive
Incident investigation & root cause records
Corrective actions closed out & verified
Periodic evaluation of legal compliance
◆ Incident and near-miss records available
Internal audit, review & two-stage audit
Internal audit fieldwork
Corrective actions from internal audit
Management review meeting
Stage 1 documentation audit
Corrective action window before Stage 2
Stage 2 certification audit
Stage 2 nonconformity closure
◆ ISO 45001 certificate issued
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Scope, context & gap analysis |  | 2026-08-02 | 2026-09-25 | 55 | 100%
1.1 | Define OH&S management system scope | OH&S manager | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | Context, workers & interested parties analysis | OH&S manager | 2026-08-12 | 2026-08-29 | 18 | 100%
1.3 | Gap analysis against ISO 45001 | Consultant | 2026-08-22 | 2026-09-12 | 22 | 100%
1.4 | OH&S policy drafted & approved | Exec | 2026-09-03 | 2026-09-20 | 18 | 100%
1.5 | Certification body selection & audit booking | OH&S manager | 2026-09-06 | 2026-09-25 | 20 | 100%
2 | Scope and OH&S policy approved |  | 2026-09-26 | 2026-09-26 | — | —
3 | Hazard identification & risk assessment |  | 2026-09-26 | 2026-12-19 | 85 | 60%
3.1 | Activity, task & process mapping across sites | Site leads | 2026-09-26 | 2026-10-20 | 25 | 100%
3.2 | Identify hazards — routine operations | Supervisors | 2026-10-16 | 2026-11-09 | 25 | 80%
3.3 | Identify hazards — non-routine, maintenance & emergency | HSE | 2026-11-05 | 2026-11-29 | 25 | 50%
3.4 | Risk assessment & hierarchy of controls applied | HSE | 2026-11-20 | 2026-12-09 | 20 | 30%
3.5 | Legal & other OH&S requirements register build | Compliance | 2026-10-06 | 2026-11-19 | 45 | 70%
4 | Hazard and risk registers approved |  | 2026-12-20 | 2026-12-20 | — | —
5 | Worker consultation & participation |  | 2026-09-11 | 2027-05-28 | 260 | 30%
5.1 | Elect worker OH&S representatives | Workforce | 2026-09-11 | 2026-09-30 | 20 | 100%
5.2 | Health & safety committee terms of | OH&S manager | 2026-10-01 | 2026-10-15 | 15 | 100%

## Slide 4
 | reference |  |  |  |  | 
5.3 | Health & safety committee meeting cycle | Committee | 2026-10-16 | 2027-05-28 | 225 | 40%
5.4 | Worker consultation on hazard identification | Worker reps | 2026-10-21 | 2026-12-04 | 45 | 60%
5.5 | Remove barriers to worker participation | Exec | 2026-12-10 | 2027-01-18 | 40 | 10%
5.6 | Worker consultation on draft OH&S objectives | Worker reps | 2026-12-30 | 2027-01-23 | 25 | 0%
6 | Consultation arrangements operating |  | 2027-05-29 | 2027-05-29 | — | —
7 | Objectives, operational control & emergency preparedness |  | 2026-12-20 | 2027-05-13 | 145 | 0%
7.1 | Derive OH&S objectives, targets & owners | OH&S manager | 2026-12-20 | 2027-01-18 | 30 | 0%
7.2 | Operational control procedures for high-risk tasks | Operations | 2027-01-24 | 2027-03-04 | 40 | 0%
7.3 | Permit to work & contractor control system | Operations | 2027-02-03 | 2027-03-19 | 45 | 0%
7.4 | Competence, training & induction rollout | HR | 2027-02-23 | 2027-04-08 | 45 | 0%
7.5 | Emergency preparedness plan & evacuation drill | HSE | 2027-04-04 | 2027-05-03 | 30 | 0%
8 | Operational controls and drill complete |  | 2027-05-14 | 2027-05-14 | — | —
9 | Operate, record incidents & near-misses |  | 2027-05-14 | 2027-08-26 | 105 | 0%
9.1 | Operate OH&S system & collect performance data | All owners | 2027-05-14 | 2027-08-21 | 100 | 0%
9.2 | Incident, injury & near-miss reporting drive | Supervisors | 2027-05-14 | 2027-08-16 | 95 | 0%
9.3 | Incident investigation & root cause records | HSE | 2027-05-29 | 2027-08-16 | 80 | 0%
9.4 | Corrective actions closed out & verified | Process owners | 2027-06-18 | 2027-08-16 | 60 | 0%
9.5 | Periodic evaluation of legal compliance | Compliance | 2027-06-18 | 2027-07-17 | 30 | 0%
10 | Incident and near-miss records available |  | 2027-08-27 | 2027-08-27 | — | —
11 | Internal audit, review & two-stage audit |  | 2027-07-23 | 2027-12-24 | 155 | 0%
11.1 | Internal audit fieldwork | Internal auditor | 2027-08-22 | 2027-09-10 | 20 | 0%

## Slide 5
11.2 | Corrective actions from internal audit | Process owners | 2027-09-11 | 2027-10-05 | 25 | 0%
11.3 | Management review meeting | Exec | 2027-10-06 | 2027-10-10 | 5 | 0%
11.4 | Stage 1 documentation audit | Certification body | 2027-10-13 | 2027-10-15 | 3 | 0%
11.5 | Corrective action window before Stage 2 | Process owners | 2027-10-18 | 2027-11-21 | 35 | 0%
11.6 | Stage 2 certification audit | Certification body | 2027-11-25 | 2027-11-28 | 4 | 0%
11.7 | Stage 2 nonconformity closure | Process owners | 2027-11-30 | 2027-12-21 | 22 | 0%
12 | ISO 45001 certificate issued |  | 2027-12-25 | 2027-12-25 | — | —