## Gantt
ISO 45001 Certification Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27
1 | Scope, context & gap analysis |  | 2026-08-02 | 2026-09-25 | 55
1.1 | Define OH&S management system scope | OH&S manager | 2026-08-02 | 2026-08-16 | 15
1.2 | Context, workers & interested parties analysis | OH&S manager | 2026-08-12 | 2026-08-29 | 18
1.3 | Gap analysis against ISO 45001 | Consultant | 2026-08-22 | 2026-09-12 | 22
1.4 | OH&S policy drafted & approved | Exec | 2026-09-03 | 2026-09-20 | 18
1.5 | Certification body selection & audit booking | OH&S manager | 2026-09-06 | 2026-09-25 | 20
2 | ◆ Scope and OH&S policy approved |  | 2026-09-26 | 2026-09-26 | [8 empty] | ◆
3 | Hazard identification & risk assessment |  | 2026-09-26 | 2026-12-19 | 85
3.1 | Activity, task & process mapping across sites | Site leads | 2026-09-26 | 2026-10-20 | 25
3.2 | Identify hazards — routine operations | Supervisors | 2026-10-16 | 2026-11-09 | 25
3.3 | Identify hazards — non-routine, maintenance & emergency | HSE | 2026-11-05 | 2026-11-29 | 25
3.4 | Risk assessment & hierarchy of controls applied | HSE | 2026-11-20 | 2026-12-09 | 20
3.5 | Legal & other OH&S requirements register build | Compliance | 2026-10-06 | 2026-11-19 | 45
4 | ◆ Hazard and risk registers approved |  | 2026-12-20 | 2026-12-20 | [21 empty] | ◆
5 | Worker consultation & participation |  | 2026-09-11 | 2027-05-28 | 260
5.1 | Elect worker OH&S representatives | Workforce | 2026-09-11 | 2026-09-30 | 20
5.2 | Health & safety committee terms of reference | OH&S manager | 2026-10-01 | 2026-10-15 | 15
5.3 | Health & safety committee meeting cycle | Committee | 2026-10-16 | 2027-05-28 | 225
5.4 | Worker consultation on hazard identification | Worker reps | 2026-10-21 | 2026-12-04 | 45
5.5 | Remove barriers to worker participation | Exec | 2026-12-10 | 2027-01-18 | 40
5.6 | Worker consultation on draft OH&S objectives | Worker reps | 2026-12-30 | 2027-01-23 | 25
6 | ◆ Consultation arrangements operating |  | 2027-05-29 | 2027-05-29 | [43 empty] | ◆
7 | Objectives, operational control & emergency preparedness |  | 2026-12-20 | 2027-05-13 | 145
7.1 | Derive OH&S objectives, targets & owners | OH&S manager | 2026-12-20 | 2027-01-18 | 30
7.2 | Operational control procedures for high-risk tasks | Operations | 2027-01-24 | 2027-03-04 | 40
7.3 | Permit to work & contractor control system | Operations | 2027-02-03 | 2027-03-19 | 45
7.4 | Competence, training & induction rollout | HR | 2027-02-23 | 2027-04-08 | 45
7.5 | Emergency preparedness plan & evacuation drill | HSE | 2027-04-04 | 2027-05-03 | 30
8 | ◆ Operational controls and drill complete |  | 2027-05-14 | 2027-05-14 | [41 empty] | ◆
9 | Operate, record incidents & near-misses |  | 2027-05-14 | 2027-08-26 | 105
9.1 | Operate OH&S system & collect performance data | All owners | 2027-05-14 | 2027-08-21 | 100
9.2 | Incident, injury & near-miss reporting drive | Supervisors | 2027-05-14 | 2027-08-16 | 95
9.3 | Incident investigation & root cause records | HSE | 2027-05-29 | 2027-08-16 | 80
9.4 | Corrective actions closed out & verified | Process owners | 2027-06-18 | 2027-08-16 | 60
9.5 | Periodic evaluation of legal compliance | Compliance | 2027-06-18 | 2027-07-17 | 30
10 | ◆ Incident and near-miss records available |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
11 | Internal audit, review & two-stage audit |  | 2027-07-23 | 2027-12-24 | 155
11.1 | Internal audit fieldwork | Internal auditor | 2027-08-22 | 2027-09-10 | 20
11.2 | Corrective actions from internal audit | Process owners | 2027-09-11 | 2027-10-05 | 25
11.3 | Management review meeting | Exec | 2027-10-06 | 2027-10-10 | 5
11.4 | Stage 1 documentation audit | Certification body | 2027-10-13 | 2027-10-15 | 3
11.5 | Corrective action window before Stage 2 | Process owners | 2027-10-18 | 2027-11-21 | 35
11.6 | Stage 2 certification audit | Certification body | 2027-11-25 | 2027-11-28 | 4
11.7 | Stage 2 nonconformity closure | Process owners | 2027-11-30 | 2027-12-21 | 22
12 | ◆ ISO 45001 certificate issued |  | 2027-12-25 | 2027-12-25 | [73 empty] | ◆