## Slide 1
ISO 9001 Certification Plan
Free Gantt chart template · gantts.app

## Slide 2
ISO 9001 Certification Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Gap analysis & planning
Scope & context of the organization
Select certification body
Gap analysis against ISO 9001
Gap report & project plan
◆ Gap analysis complete
Process mapping & risk
Map core processes
Interested parties & requirements
Risk & opportunity register
Quality objectives & KPIs
QMS documentation
Quality policy & manual
Document control system
Documented procedures
Work instructions & forms
Records & retention schedule
◆ Documentation released
Implementation & training
Staff awareness training
Process owner training
Run processes & collect records
Internal audit & corrective action
Train internal auditors
Internal audit programme
Nonconformity reports
Corrective actions
Management review
Compile management review inputs
Management review meeting
Actions from review
◆ Certification readiness confirmed
Certification audit
Stage 1 audit (documentation)
Stage 1 findings closure
Stage 2 audit (implementation)
Stage 2 nonconformity closure
◆ Certification decision
◆ Certificate issued
Surveillance
Continual improvement cycle
Internal audit cycle 2
Surveillance audit preparation
Surveillance audit year 1
◆ Surveillance passed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Gap analysis & planning |  | 2026-08-02 | 2026-09-15 | 45 | 100%
1.1 | Scope & context of the organization | Quality manager | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | Select certification body | Management | 2026-08-07 | 2026-08-31 | 25 | 100%
1.3 | Gap analysis against ISO 9001 | Quality manager | 2026-08-17 | 2026-09-05 | 20 | 100%
1.4 | Gap report & project plan | Quality manager | 2026-09-06 | 2026-09-15 | 10 | 100%
2 | Gap analysis complete |  | 2026-09-16 | 2026-09-16 | — | —
3 | Process mapping & risk |  | 2026-09-16 | 2026-11-09 | 55 | 90%
3.1 | Map core processes | Process owners | 2026-09-16 | 2026-10-20 | 35 | 100%
3.2 | Interested parties & requirements | Quality manager | 2026-10-01 | 2026-10-20 | 20 | 100%
3.3 | Risk & opportunity register | Quality manager | 2026-10-11 | 2026-11-04 | 25 | 90%
3.4 | Quality objectives & KPIs | Management | 2026-10-21 | 2026-11-09 | 20 | 70%
4 | QMS documentation |  | 2026-10-01 | 2026-12-29 | 90 | 60%
4.1 | Quality policy & manual | Quality manager | 2026-10-01 | 2026-10-25 | 25 | 100%
4.2 | Document control system | Quality manager | 2026-10-31 | 2026-11-29 | 30 | 80%
4.3 | Documented procedures | Process owners | 2026-10-16 | 2026-12-09 | 55 | 70%
4.4 | Work instructions & forms | Process owners | 2026-11-10 | 2026-12-19 | 40 | 40%
4.5 | Records & retention schedule | Quality manager | 2026-11-30 | 2026-12-24 | 25 | 20%
5 | Documentation released |  | 2026-12-30 | 2026-12-30 | — | —
6 | Implementation & training |  | 2026-12-10 | 2027-02-17 | 70 | 10%
6.1 | Staff awareness training | Quality manager | 2026-12-10 | 2027-01-03 | 25 | 20%
6.2 | Process owner training | Quality manager | 2026-12-20 | 2027-01-08 | 20 | 0%

## Slide 4
6.3 | Run processes & collect records | All | 2026-12-30 | 2027-02-17 | 50 | 0%
7 | Internal audit & corrective action |  | 2027-02-08 | 2027-04-18 | 70 | 0%
7.1 | Train internal auditors | External trainer | 2027-02-08 | 2027-02-22 | 15 | 0%
7.2 | Internal audit programme | Internal auditors | 2027-02-18 | 2027-03-14 | 25 | 0%
7.3 | Nonconformity reports | Internal auditors | 2027-03-05 | 2027-03-24 | 20 | 0%
7.4 | Corrective actions | Process owners | 2027-03-15 | 2027-04-18 | 35 | 0%
8 | Management review |  | 2027-04-14 | 2027-05-08 | 25 | 0%
8.1 | Compile management review inputs | Quality manager | 2027-04-14 | 2027-04-23 | 10 | 0%
8.2 | Management review meeting | Management | 2027-04-24 | 2027-04-25 | 2 | 0%
8.3 | Actions from review | Management | 2027-04-26 | 2027-05-08 | 13 | 0%
9 | Certification readiness confirmed |  | 2027-05-09 | 2027-05-09 | — | —
10 | Certification audit |  | 2027-05-14 | 2027-08-11 | 90 | 0%
10.1 | Stage 1 audit (documentation) | Certification body | 2027-05-14 | 2027-05-16 | 3 | 0%
10.2 | Stage 1 findings closure | Quality manager | 2027-05-19 | 2027-06-17 | 30 | 0%
10.3 | Stage 2 audit (implementation) | Certification body | 2027-06-28 | 2027-07-02 | 5 | 0%
10.4 | Stage 2 nonconformity closure | Quality manager | 2027-07-08 | 2027-08-01 | 25 | 0%
11 | Certification decision |  | 2027-08-07 | 2027-08-07 | — | —
12 | Certificate issued |  | 2027-08-12 | 2027-08-12 | — | —
13 | Surveillance |  | 2027-08-12 | 2028-02-02 | 175 | 0%
13.1 | Continual improvement cycle | Process owners | 2027-08-12 | 2028-01-28 | 170 | 0%
13.2 | Internal audit cycle 2 | Internal auditors | 2027-11-25 | 2027-12-24 | 30 | 0%
13.3 | Surveillance audit preparation | Quality manager | 2028-01-04 | 2028-01-23 | 20 | 0%
13.4 | Surveillance audit year 1 | Certification body | 2028-01-29 | 2028-01-31 | 3 | 0%
14 | Surveillance passed |  | 2028-02-03 | 2028-02-03 | — | —