## Gantt
ISO 9001 Certification Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7
1 | Gap analysis & planning |  | 2026-08-02 | 2026-09-15 | 45
1.1 | Scope & context of the organization | Quality manager | 2026-08-02 | 2026-08-16 | 15
1.2 | Select certification body | Management | 2026-08-07 | 2026-08-31 | 25
1.3 | Gap analysis against ISO 9001 | Quality manager | 2026-08-17 | 2026-09-05 | 20
1.4 | Gap report & project plan | Quality manager | 2026-09-06 | 2026-09-15 | 10
2 | ◆ Gap analysis complete |  | 2026-09-16 | 2026-09-16 | [7 empty] | ◆
3 | Process mapping & risk |  | 2026-09-16 | 2026-11-09 | 55
3.1 | Map core processes | Process owners | 2026-09-16 | 2026-10-20 | 35
3.2 | Interested parties & requirements | Quality manager | 2026-10-01 | 2026-10-20 | 20
3.3 | Risk & opportunity register | Quality manager | 2026-10-11 | 2026-11-04 | 25
3.4 | Quality objectives & KPIs | Management | 2026-10-21 | 2026-11-09 | 20
4 | QMS documentation |  | 2026-10-01 | 2026-12-29 | 90
4.1 | Quality policy & manual | Quality manager | 2026-10-01 | 2026-10-25 | 25
4.2 | Document control system | Quality manager | 2026-10-31 | 2026-11-29 | 30
4.3 | Documented procedures | Process owners | 2026-10-16 | 2026-12-09 | 55
4.4 | Work instructions & forms | Process owners | 2026-11-10 | 2026-12-19 | 40
4.5 | Records & retention schedule | Quality manager | 2026-11-30 | 2026-12-24 | 25
5 | ◆ Documentation released |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
6 | Implementation & training |  | 2026-12-10 | 2027-02-17 | 70
6.1 | Staff awareness training | Quality manager | 2026-12-10 | 2027-01-03 | 25
6.2 | Process owner training | Quality manager | 2026-12-20 | 2027-01-08 | 20
6.3 | Run processes & collect records | All | 2026-12-30 | 2027-02-17 | 50
7 | Internal audit & corrective action |  | 2027-02-08 | 2027-04-18 | 70
7.1 | Train internal auditors | External trainer | 2027-02-08 | 2027-02-22 | 15
7.2 | Internal audit programme | Internal auditors | 2027-02-18 | 2027-03-14 | 25
7.3 | Nonconformity reports | Internal auditors | 2027-03-05 | 2027-03-24 | 20
7.4 | Corrective actions | Process owners | 2027-03-15 | 2027-04-18 | 35
8 | Management review |  | 2027-04-14 | 2027-05-08 | 25
8.1 | Compile management review inputs | Quality manager | 2027-04-14 | 2027-04-23 | 10
8.2 | Management review meeting | Management | 2027-04-24 | 2027-04-25 | 2
8.3 | Actions from review | Management | 2027-04-26 | 2027-05-08 | 13
9 | ◆ Certification readiness confirmed |  | 2027-05-09 | 2027-05-09 | [41 empty] | ◆
10 | Certification audit |  | 2027-05-14 | 2027-08-11 | 90
10.1 | Stage 1 audit (documentation) | Certification body | 2027-05-14 | 2027-05-16 | 3
10.2 | Stage 1 findings closure | Quality manager | 2027-05-19 | 2027-06-17 | 30
10.3 | Stage 2 audit (implementation) | Certification body | 2027-06-28 | 2027-07-02 | 5
10.4 | Stage 2 nonconformity closure | Quality manager | 2027-07-08 | 2027-08-01 | 25
11 | ◆ Certification decision |  | 2027-08-07 | 2027-08-07 | [53 empty] | ◆
12 | ◆ Certificate issued |  | 2027-08-12 | 2027-08-12 | [54 empty] | ◆
13 | Surveillance |  | 2027-08-12 | 2028-02-02 | 175
13.1 | Continual improvement cycle | Process owners | 2027-08-12 | 2028-01-28 | 170
13.2 | Internal audit cycle 2 | Internal auditors | 2027-11-25 | 2027-12-24 | 30
13.3 | Surveillance audit preparation | Quality manager | 2028-01-04 | 2028-01-23 | 20
13.4 | Surveillance audit year 1 | Certification body | 2028-01-29 | 2028-01-31 | 3
14 | ◆ Surveillance passed |  | 2028-02-03 | 2028-02-03 | [79 empty] | ◆