## Slide 1
Kitchen Remodel
Free Gantt chart template · gantts.app

## Slide 2
Kitchen Remodel
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Design & planning
Set budget & scope
Measure & finalize layout
Select materials & finishes
Hire contractor
Apply for permits
◆ Design approved
Order long-lead items
Order cabinets (6-8 week lead)
Order countertops & appliances
Order flooring & tile
Set up a temporary kitchen
◆ Cabinets delivered
Demolition
Disconnect utilities
Demo cabinets, counters & flooring
Haul away debris
◆ Demolition complete
Rough-in & inspection
Framing & layout changes
Plumbing rough-in
Electrical rough-in
Rough-in inspection
◆ Rough-in signed off
Walls, floor & paint
Drywall & patch
Prime & paint
Install flooring
◆ Surfaces ready
Install & finish
Install cabinets
Template countertops
Countertop fabrication
Install countertops
Tile the backsplash
Install appliances
Plumbing & electrical hookups
Final inspection
Punch list & touch-ups
◆ Kitchen complete
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Design & planning |  | 2026-08-02 | 2026-08-22 | 21 | 100%
1.1 | Set budget & scope | You | 2026-08-02 | 2026-08-05 | 4 | 100%
1.2 | Measure & finalize layout | Designer | 2026-08-05 | 2026-08-10 | 6 | 100%
1.3 | Select materials & finishes | You | 2026-08-10 | 2026-08-18 | 9 | 90%
1.4 | Hire contractor | You | 2026-08-08 | 2026-08-17 | 10 | 80%
1.5 | Apply for permits | Contractor | 2026-08-16 | 2026-08-23 | 8 | 50%
2 | Design approved |  | 2026-08-23 | 2026-08-23 | , | ,
3 | Order long-lead items |  | 2026-08-19 | 2026-10-02 | 45 | 0%
3.1 | Order cabinets (6-8 week lead) | You | 2026-08-19 | 2026-10-02 | 45 | 20%
3.2 | Order countertops & appliances | You | 2026-08-21 | 2026-08-25 | 5 | 0%
3.3 | Order flooring & tile | You | 2026-08-23 | 2026-08-27 | 5 | 0%
3.4 | Set up a temporary kitchen | You | 2026-09-09 | 2026-09-12 | 4 | 0%
4 | Cabinets delivered |  | 2026-10-03 | 2026-10-03 | , | ,
5 | Demolition |  | 2026-09-13 | 2026-09-19 | 7 | 0%
5.1 | Disconnect utilities | Contractor | 2026-09-13 | 2026-09-13 | 1 | 0%
5.2 | Demo cabinets, counters & flooring | Contractor | 2026-09-14 | 2026-09-17 | 4 | 0%
5.3 | Haul away debris | Contractor | 2026-09-17 | 2026-09-18 | 2 | 0%
6 | Demolition complete |  | 2026-09-20 | 2026-09-20 | , | ,
7 | Rough-in & inspection |  | 2026-09-20 | 2026-10-03 | 14 | 0%
7.1 | Framing & layout changes | Contractor | 2026-09-20 | 2026-09-23 | 4 | 0%
7.2 | Plumbing rough-in | Plumber | 2026-09-22 | 2026-09-26 | 5 | 0%

## Slide 4
7.3 | Electrical rough-in | Electrician | 2026-09-22 | 2026-09-26 | 5 | 0%
7.4 | Rough-in inspection | Inspector | 2026-09-28 | 2026-09-29 | 2 | 0%
8 | Rough-in signed off |  | 2026-09-30 | 2026-09-30 | , | ,
9 | Walls, floor & paint |  | 2026-09-30 | 2026-10-11 | 12 | 0%
9.1 | Drywall & patch | Contractor | 2026-09-30 | 2026-10-03 | 4 | 0%
9.2 | Prime & paint | Contractor | 2026-10-03 | 2026-10-05 | 3 | 0%
9.3 | Install flooring | Contractor | 2026-10-05 | 2026-10-08 | 4 | 0%
10 | Surfaces ready |  | 2026-10-11 | 2026-10-11 | , | ,
11 | Install & finish |  | 2026-10-03 | 2026-10-30 | 28 | 0%
11.1 | Install cabinets | Contractor | 2026-10-11 | 2026-10-15 | 5 | 0%
11.2 | Template countertops | Fabricator | 2026-10-16 | 2026-10-16 | 1 | 0%
11.3 | Countertop fabrication | Fabricator | 2026-10-17 | 2026-10-26 | 10 | 0%
11.4 | Install countertops | Fabricator | 2026-10-27 | 2026-10-28 | 2 | 0%
11.5 | Tile the backsplash | Contractor | 2026-10-29 | 2026-10-31 | 3 | 0%
11.6 | Install appliances | Plumber | 2026-10-29 | 2026-10-30 | 2 | 0%
11.7 | Plumbing & electrical hookups | Plumber | 2026-10-30 | 2026-11-01 | 3 | 0%
11.8 | Final inspection | Inspector | 2026-11-02 | 2026-11-02 | 1 | 0%
11.9 | Punch list & touch-ups | Contractor | 2026-11-03 | 2026-11-05 | 3 | 0%
12 | Kitchen complete |  | 2026-11-06 | 2026-11-06 | , | ,