## Gantt
Kitchen Remodel
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9
1 | Design & planning |  | 2026-08-02 | 2026-08-22 | 21
1.1 | Set budget & scope | You | 2026-08-02 | 2026-08-05 | 4
1.2 | Measure & finalize layout | Designer | 2026-08-05 | 2026-08-10 | 6
1.3 | Select materials & finishes | You | 2026-08-10 | 2026-08-18 | 9
1.4 | Hire contractor | You | 2026-08-08 | 2026-08-17 | 10
1.5 | Apply for permits | Contractor | 2026-08-16 | 2026-08-23 | 8
2 | ◆ Design approved |  | 2026-08-23 | 2026-08-23 |  |  |  |  | ◆
3 | Order long-lead items |  | 2026-08-19 | 2026-10-02 | 45
3.1 | Order cabinets (6-8 week lead) | You | 2026-08-19 | 2026-10-02 | 45
3.2 | Order countertops & appliances | You | 2026-08-21 | 2026-08-25 | 5
3.3 | Order flooring & tile | You | 2026-08-23 | 2026-08-27 | 5
3.4 | Set up a temporary kitchen | You | 2026-09-09 | 2026-09-12 | 4
4 | ◆ Cabinets delivered |  | 2026-10-03 | 2026-10-03 | [9 empty] | ◆
5 | Demolition |  | 2026-09-13 | 2026-09-19 | 7
5.1 | Disconnect utilities | Contractor | 2026-09-13 | 2026-09-13 | 1
5.2 | Demo cabinets, counters & flooring | Contractor | 2026-09-14 | 2026-09-17 | 4
5.3 | Haul away debris | Contractor | 2026-09-17 | 2026-09-18 | 2
6 | ◆ Demolition complete |  | 2026-09-20 | 2026-09-20 | [8 empty] | ◆
7 | Rough-in & inspection |  | 2026-09-20 | 2026-10-03 | 14
7.1 | Framing & layout changes | Contractor | 2026-09-20 | 2026-09-23 | 4
7.2 | Plumbing rough-in | Plumber | 2026-09-22 | 2026-09-26 | 5
7.3 | Electrical rough-in | Electrician | 2026-09-22 | 2026-09-26 | 5
7.4 | Rough-in inspection | Inspector | 2026-09-28 | 2026-09-29 | 2
8 | ◆ Rough-in signed off |  | 2026-09-30 | 2026-09-30 | [9 empty] | ◆
9 | Walls, floor & paint |  | 2026-09-30 | 2026-10-11 | 12
9.1 | Drywall & patch | Contractor | 2026-09-30 | 2026-10-03 | 4
9.2 | Prime & paint | Contractor | 2026-10-03 | 2026-10-05 | 3
9.3 | Install flooring | Contractor | 2026-10-05 | 2026-10-08 | 4
10 | ◆ Surfaces ready |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
11 | Install & finish |  | 2026-10-03 | 2026-10-30 | 28
11.1 | Install cabinets | Contractor | 2026-10-11 | 2026-10-15 | 5
11.2 | Template countertops | Fabricator | 2026-10-16 | 2026-10-16 | 1
11.3 | Countertop fabrication | Fabricator | 2026-10-17 | 2026-10-26 | 10
11.4 | Install countertops | Fabricator | 2026-10-27 | 2026-10-28 | 2
11.5 | Tile the backsplash | Contractor | 2026-10-29 | 2026-10-31 | 3
11.6 | Install appliances | Plumber | 2026-10-29 | 2026-10-30 | 2
11.7 | Plumbing & electrical hookups | Plumber | 2026-10-30 | 2026-11-01 | 3
11.8 | Final inspection | Inspector | 2026-11-02 | 2026-11-02 | 1
11.9 | Punch list & touch-ups | Contractor | 2026-11-03 | 2026-11-05 | 3
12 | ◆ Kitchen complete |  | 2026-11-06 | 2026-11-06 | [14 empty] | ◆