## Slide 1
M&A Due Diligence Timeline
Free Gantt chart template · gantts.app

## Slide 2
M&A Due Diligence Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Approach & NDA
Target identification & approach
NDA negotiation
◆ NDA signed
Teaser & information memorandum
Indicative offer & access
First round review
Indicative offer / LOI
◆ Exclusivity agreed
Data room opened & indexed
Diligence workstreams
Financial diligence
Legal diligence
Tax diligence
Commercial diligence
IT & cyber diligence
HR & pensions diligence
Management & Q&A
Q&A log & follow-up requests
Management presentations
Site visits
Expert & customer calls
Findings & deal terms
Red flag report
Valuation adjustment & structure
W&I insurance placement
◆ Investment committee approval
SPA, signing & closing
SPA drafting & negotiation
Disclosure letter & schedules
◆ Exclusivity expires
◆ Signing
Regulatory & antitrust clearance
Third-party consents & financing
Completion mechanics & funds flow
◆ Closing
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Approach & NDA |  | 2026-08-02 | 2026-09-05 | 35 | 100%
1.1 | Target identification & approach | Corp dev | 2026-08-02 | 2026-08-16 | 15 | 100%
1.2 | NDA negotiation | Legal | 2026-08-14 | 2026-08-25 | 12 | 100%
2 | NDA signed |  | 2026-08-26 | 2026-08-26 | — | —
2.1 | Teaser & information memorandum | Adviser | 2026-08-26 | 2026-09-05 | 11 | 100%
3 | Indicative offer & access |  | 2026-09-06 | 2026-10-05 | 30 | 100%
3.1 | First round review | Corp dev | 2026-09-06 | 2026-09-19 | 14 | 100%
3.2 | Indicative offer / LOI | Corp dev | 2026-09-20 | 2026-09-29 | 10 | 100%
4 | Exclusivity agreed |  | 2026-10-01 | 2026-10-01 | — | —
4.1 | Data room opened & indexed | Seller | 2026-10-01 | 2026-10-05 | 5 | 100%
5 | Diligence workstreams |  | 2026-10-06 | 2026-12-04 | 60 | 40%
5.1 | Financial diligence | Accountants | 2026-10-06 | 2026-11-24 | 50 | 50%
5.2 | Legal diligence | Legal | 2026-10-06 | 2026-11-29 | 55 | 40%
5.3 | Tax diligence | Tax adviser | 2026-10-09 | 2026-11-22 | 45 | 35%
5.4 | Commercial diligence | Strategy | 2026-10-06 | 2026-11-24 | 50 | 45%
5.5 | IT & cyber diligence | IT adviser | 2026-10-13 | 2026-11-21 | 40 | 30%
5.6 | HR & pensions diligence | HR adviser | 2026-10-16 | 2026-11-24 | 40 | 25%
6 | Management & Q&A |  | 2026-10-11 | 2026-12-04 | 55 | 30%
6.1 | Q&A log & follow-up requests | Deal team | 2026-10-11 | 2026-12-04 | 55 | 40%
6.2 | Management presentations | Target management | 2026-10-23 | 2026-10-30 | 8 | 0%
6.3 | Site visits | Deal team | 2026-11-02 | 2026-11-07 | 6 | 0%

## Slide 4
6.4 | Expert & customer calls | Strategy | 2026-11-05 | 2026-11-24 | 20 | 0%
7 | Findings & deal terms |  | 2026-11-25 | 2026-12-29 | 35 | 0%
7.1 | Red flag report | Deal team | 2026-11-25 | 2026-12-06 | 12 | 0%
7.2 | Valuation adjustment & structure | Corp dev | 2026-12-02 | 2026-12-16 | 15 | 0%
7.3 | W&I insurance placement | Broker | 2026-12-05 | 2026-12-26 | 22 | 0%
8 | Investment committee approval |  | 2026-12-30 | 2026-12-30 | — | —
9 | SPA, signing & closing |  | 2026-11-20 | 2027-03-19 | 120 | 0%
9.1 | SPA drafting & negotiation | Legal | 2026-11-20 | 2027-01-03 | 45 | 0%
9.2 | Disclosure letter & schedules | Legal | 2026-12-15 | 2027-01-08 | 25 | 0%
10 | Exclusivity expires |  | 2027-01-04 | 2027-01-04 | — | —
11 | Signing |  | 2027-01-11 | 2027-01-11 | — | —
11.1 | Regulatory & antitrust clearance | Legal | 2027-01-11 | 2027-03-06 | 55 | 0%
11.2 | Third-party consents & financing | Deal team | 2027-01-11 | 2027-02-24 | 45 | 0%
11.3 | Completion mechanics & funds flow | Finance | 2027-02-28 | 2027-03-19 | 20 | 0%
12 | Closing |  | 2027-03-20 | 2027-03-20 | — | —