## Gantt
Manufacturing Production Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18
1 | Demand & capacity planning |  | 2026-08-02 | 2026-08-26 | 25
1.1 | Demand forecast review | Planning | 2026-08-02 | 2026-08-11 | 10
1.2 | Firm order intake | Sales | 2026-08-07 | 2026-08-16 | 10
1.3 | Master production schedule | Planning | 2026-08-12 | 2026-08-21 | 10
1.4 | Capacity & labour check | Operations | 2026-08-17 | 2026-08-24 | 8
2 | ◆ Capacity confirmed |  | 2026-08-27 | 2026-08-27 |  |  |  |  | ◆
3 | Material procurement |  | 2026-08-22 | 2026-10-13 | 53
3.1 | BOM explosion & MRP run | Planning | 2026-08-22 | 2026-08-26 | 5
3.2 | Purchase orders released | Procurement | 2026-08-27 | 2026-08-31 | 5
3.3 | Long-lead component delivery | Supplier | 2026-09-01 | 2026-10-10 | 40
3.4 | Standard material delivery | Supplier | 2026-09-01 | 2026-09-20 | 20
3.5 | Goods receipt & incoming inspection | Quality | 2026-09-21 | 2026-10-10 | 20
3.6 | Material staged at line | Warehouse | 2026-10-09 | 2026-10-13 | 5
4 | ◆ Materials available |  | 2026-10-14 | 2026-10-14 | [11 empty] | ◆
5 | Line scheduling & setup |  | 2026-10-01 | 2026-10-20 | 20
5.1 | Detailed line sequencing | Planning | 2026-10-01 | 2026-10-10 | 10
5.2 | Changeover plan & SMED review | Operations | 2026-10-06 | 2026-10-15 | 10
5.3 | Tooling & fixture preparation | Maintenance | 2026-10-09 | 2026-10-20 | 12
5.4 | Line changeover | Operations | 2026-10-14 | 2026-10-16 | 3
5.5 | First article inspection | Quality | 2026-10-17 | 2026-10-18 | 2
6 | ◆ First article approved |  | 2026-10-19 | 2026-10-19 | [12 empty] | ◆
7 | Production runs |  | 2026-10-19 | 2026-12-24 | 67
7.1 | Product A run | Line 1 | 2026-10-19 | 2026-11-07 | 20
7.2 | Changeover to Product B | Operations | 2026-11-08 | 2026-11-09 | 2
7.3 | Product B run | Line 1 | 2026-11-10 | 2026-12-04 | 25
7.4 | Changeover to Product C | Operations | 2026-12-05 | 2026-12-06 | 2
7.5 | Product C run | Line 1 | 2026-12-07 | 2026-12-24 | 18
8 | Quality control |  | 2026-10-21 | 2027-01-03 | 75
8.1 | In-process inspection & SPC | Quality | 2026-10-21 | 2026-12-24 | 65
8.2 | Nonconformance hold & disposition | Quality | 2026-11-15 | 2026-12-09 | 25
8.3 | Final inspection & test | Quality | 2026-12-25 | 2026-12-31 | 7
8.4 | Batch release documentation | Quality | 2026-12-30 | 2027-01-03 | 5
9 | ◆ Batch released |  | 2027-01-04 | 2027-01-04 | [23 empty] | ◆
10 | Packing & dispatch |  | 2026-12-25 | 2027-01-16 | 23
10.1 | Packing & labelling | Warehouse | 2026-12-28 | 2027-01-08 | 12
10.2 | Carrier booking | Logistics | 2026-12-30 | 2027-01-03 | 5
10.3 | Palletizing & load planning | Warehouse | 2027-01-04 | 2027-01-11 | 8
10.4 | Dispatch & shipping documents | Logistics | 2027-01-12 | 2027-01-16 | 5
11 | ◆ Order shipped |  | 2027-01-17 | 2027-01-17 | [25 empty] | ◆