## Gantt
Medical Clinic Opening
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30
1 | Business case, site & licensing pathway |  | 2026-08-02 | 2026-11-29 | 120
1.1 | Service line definition & demand analysis | Exec | 2026-08-02 | 2026-09-05 | 35
1.2 | Site selection & lease negotiation | Real estate | 2026-08-27 | 2026-10-20 | 55
1.3 | Licensing pathway & certificate of need review | Regulatory | 2026-09-01 | 2026-10-30 | 60
1.4 | Legal entity, NPI & tax registrations | Admin | 2026-10-31 | 2026-12-09 | 40
2 | ◆ Lease signed |  | 2026-10-21 | 2026-10-21 | [12 empty] | ◆
3 | ◆ Licensing pathway confirmed |  | 2026-10-31 | 2026-10-31 | [13 empty] | ◆
4 | Clinician credentialing & payer enrolment |  | 2026-10-01 | 2027-05-08 | 220
4.1 | Physician recruitment & offers | HR | 2026-10-01 | 2026-12-09 | 70
4.2 | Primary source verification & credentialing file build | Credentialing | 2026-12-10 | 2027-01-23 | 45
4.3 | State licence & DEA registration per clinician | Credentialing | 2026-12-10 | 2027-03-09 | 90
4.4 | Medical staff committee review | Credentialing | 2027-01-24 | 2027-03-04 | 40
4.5 | Payer enrolment & CAQH submissions | Revenue cycle | 2027-01-24 | 2027-05-08 | 105
5 | ◆ Clinicians credentialed and privileged |  | 2027-03-05 | 2027-03-05 | [31 empty] | ◆
6 | ◆ Payer contracts effective |  | 2027-05-09 | 2027-05-09 | [41 empty] | ◆
7 | Design & regulated fit-out |  | 2026-10-31 | 2027-05-18 | 200
7.1 | Medical planning & room-by-room programme | Architect | 2026-10-31 | 2026-12-09 | 40
7.2 | Construction documents & health authority plan review | Architect | 2026-12-10 | 2027-02-07 | 60
8 | ◆ Building permit issued |  | 2027-02-08 | 2027-02-08 | [28 empty] | ◆
8.1 | Demolition & rough-in | Contractor | 2027-02-08 | 2027-03-24 | 45
8.2 | Medical gas piping installation & brazing | Mechanical | 2027-03-05 | 2027-04-13 | 40
8.3 | HVAC, pressure relationships & infection-control barriers | Mechanical | 2027-03-10 | 2027-04-28 | 50
8.4 | Casework, flooring & cleanable finishes | Contractor | 2027-04-14 | 2027-05-23 | 40
9 | ◆ Fit-out substantially complete |  | 2027-05-24 | 2027-05-24 | [43 empty] | ◆
10 | Equipment, IT & commissioning |  | 2026-12-30 | 2027-07-07 | 190
10.1 | Capital equipment selection & purchase orders | Procurement | 2026-12-30 | 2027-02-12 | 45
10.2 | Imaging equipment delivery & installation | Vendor | 2027-04-24 | 2027-05-28 | 35
10.3 | Medical gas system verification & certification | Verifier | 2027-04-14 | 2027-05-03 | 20
10.4 | EHR build, interfaces & practice management setup | IT | 2027-02-18 | 2027-05-18 | 90
10.5 | Network, nurse call & security systems | IT | 2027-05-24 | 2027-06-27 | 35
10.6 | Equipment commissioning & calibration | Biomed | 2027-05-29 | 2027-07-02 | 35
10.7 | Radiation physicist survey & registration | Physicist | 2027-05-29 | 2027-06-17 | 20
11 | ◆ Equipment commissioned and calibrated |  | 2027-07-03 | 2027-07-03 | [48 empty] | ◆
12 | Inspections, licensing & accreditation |  | 2027-05-09 | 2027-08-26 | 110
12.1 | Accreditation survey readiness & policy manual | Quality | 2027-05-09 | 2027-06-27 | 50
12.2 | Fire marshal & building occupancy inspection | Regulator | 2027-05-24 | 2027-06-07 | 15
12.3 | Infection control risk assessment close-out | Infection control | 2027-05-24 | 2027-06-07 | 15
12.4 | CLIA certificate for in-house laboratory | Regulatory | 2027-05-29 | 2027-07-12 | 45
12.5 | Health department clinic licensing inspection | Regulator | 2027-06-18 | 2027-07-07 | 20
13 | ◆ Clinic licence issued |  | 2027-07-13 | 2027-07-13 | [50 empty] | ◆
14 | Staffing, dry run & go-live |  | 2027-05-14 | 2027-08-26 | 105
14.1 | Clinical & front-desk staff hiring | HR | 2027-05-14 | 2027-06-27 | 45
14.2 | Orientation, competency sign-off & EHR training | HR | 2027-07-03 | 2027-07-27 | 25
14.3 | Supply chain, formulary & sterile stock | Supply | 2027-07-03 | 2027-08-01 | 30
14.4 | Revenue cycle test claims & clearinghouse check | Revenue cycle | 2027-07-18 | 2027-08-01 | 15
14.5 | Marketing launch & referring physician outreach | Marketing | 2027-07-13 | 2027-08-21 | 40
14.6 | Mock patient day & workflow dry run | Operations | 2027-07-28 | 2027-08-03 | 7
15 | ◆ First patient seen |  | 2027-08-12 | 2027-08-12 | [54 empty] | ◆
16 | ◆ Full schedule open |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆