## Slide 1
Mining Project Schedule
Free Gantt chart template · gantts.app

## Slide 2
Mining Project Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
May 7
May 21
Jun 4
Jun 18
Jul 2
Jul 16
Jul 30
Aug 13
Aug 27
Sep 10
Sep 24
Oct 8
Oct 22
Nov 5
Nov 19
Dec 3
Dec 17
Dec 31
Jan 14
Jan 28
Feb 11
Feb 25
Mar 11
Mar 25
Apr 8
Apr 22
May 6
May 20
Jun 3
Jun 17
Jul 1
Jul 15
Jul 29
Aug 12
Aug 26
Sep 9
Exploration
Target generation & geophysics
First-pass drilling
◆ Discovery confirmed
Resource definition
Infill drilling
Assay turnaround & modelling
◆ Resource declared
Studies & feasibility
Scoping & pre-feasibility
Bankable feasibility study
◆ Investment decision
Permitting & approvals
Environmental & social impact
Mining licence & water permits
Development & construction
Site access, power & water
Process plant construction
Pre-strip / decline development
Ramp-up & operations
Commissioning & first production
Ramp to nameplate capacity
◆ Commercial production
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Exploration |  | 2026-08-02 | 2027-03-29 | 240 | 100%
1.1 | Target generation & geophysics | Geology | 2026-08-02 | 2026-10-30 | 90 | 100%
1.2 | First-pass drilling | Geology | 2026-10-31 | 2027-03-29 | 150 | 100%
2 | Discovery confirmed |  | 2027-03-30 | 2027-03-30 | — | —
3 | Resource definition |  | 2027-03-30 | 2027-12-14 | 260 | 70%
3.1 | Infill drilling | Geology | 2027-03-30 | 2027-09-25 | 180 | 90%
3.2 | Assay turnaround & modelling | Geology | 2027-06-28 | 2027-12-14 | 170 | 60%
4 | Resource declared |  | 2027-12-15 | 2027-12-15 | — | —
5 | Studies & feasibility |  | 2027-09-26 | 2028-10-29 | 400 | 30%
5.1 | Scoping & pre-feasibility | Engineering | 2027-09-26 | 2028-03-23 | 180 | 60%
5.2 | Bankable feasibility study | Engineering | 2028-03-24 | 2028-10-29 | 220 | 10%
6 | Investment decision |  | 2028-11-09 | 2028-11-09 | — | —
7 | Permitting & approvals |  | 2028-03-24 | 2029-01-17 | 300 | 20%
7.1 | Environmental & social impact | Environment | 2028-03-24 | 2028-10-09 | 200 | 30%
7.2 | Mining licence & water permits | Legal | 2028-08-21 | 2029-01-17 | 150 | 0%
8 | Development & construction |  | 2028-11-19 | 2030-01-12 | 420 | 0%
8.1 | Site access, power & water | Projects | 2028-11-19 | 2029-03-18 | 120 | 0%
8.2 | Process plant construction | EPC | 2029-02-17 | 2029-12-13 | 300 | 0%
8.3 | Pre-strip / decline development | Mining | 2029-04-18 | 2029-12-13 | 240 | 0%
9 | Ramp-up & operations |  | 2029-12-24 | 2030-09-09 | 260 | 0%
9.1 | Commissioning & first production | Operations | 2029-12-24 | 2030-03-23 | 90 | 0%

## Slide 4
9.2 | Ramp to nameplate capacity | Operations | 2030-03-14 | 2030-09-09 | 180 | 0%
10 | Commercial production |  | 2030-09-10 | 2030-09-10 | — | —