## Gantt
Mining Project Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 25 | Jan 1 | Jan 8 | Jan 15 | Jan 22 | Jan 29 | Feb 5 | Feb 12 | Feb 19 | Feb 26 | Mar 5 | Mar 12 | Mar 19 | Mar 26 | Apr 2 | Apr 9 | Apr 16 | Apr 23 | Apr 30 | May 7 | May 14 | May 21 | May 28 | Jun 4 | Jun 11 | Jun 18 | Jun 25 | Jul 2 | Jul 9 | Jul 16 | Jul 23 | Jul 30 | Aug 6 | Aug 13 | Aug 20 | Aug 27 | Sep 3 | Sep 10 | Sep 17 | Sep 24 | Oct 1 | Oct 8 | Oct 15 | Oct 22 | Oct 29 | Nov 5 | Nov 12 | Nov 19 | Nov 26 | Dec 3 | Dec 10 | Dec 17 | Dec 24 | Dec 31 | Jan 7 | Jan 14 | Jan 21 | Jan 28 | Feb 4 | Feb 11 | Feb 18 | Feb 25 | Mar 4 | Mar 11 | Mar 18 | Mar 25 | Apr 1 | Apr 8 | Apr 15 | Apr 22 | Apr 29 | May 6 | May 13 | May 20 | May 27 | Jun 3 | Jun 10 | Jun 17 | Jun 24 | Jul 1 | Jul 8 | Jul 15 | Jul 22 | Jul 29 | Aug 5 | Aug 12 | Aug 19 | Aug 26 | Sep 2 | Sep 9 | Sep 16
1 | Exploration |  | 2026-08-02 | 2027-03-29 | 240
1.1 | Target generation & geophysics | Geology | 2026-08-02 | 2026-10-30 | 90
1.2 | First-pass drilling | Geology | 2026-10-31 | 2027-03-29 | 150
2 | ◆ Discovery confirmed |  | 2027-03-30 | 2027-03-30 | [35 empty] | ◆
3 | Resource definition |  | 2027-03-30 | 2027-12-14 | 260
3.1 | Infill drilling | Geology | 2027-03-30 | 2027-09-25 | 180
3.2 | Assay turnaround & modelling | Geology | 2027-06-28 | 2027-12-14 | 170
4 | ◆ Resource declared |  | 2027-12-15 | 2027-12-15 | [72 empty] | ◆
5 | Studies & feasibility |  | 2027-09-26 | 2028-10-29 | 400
5.1 | Scoping & pre-feasibility | Engineering | 2027-09-26 | 2028-03-23 | 180
5.2 | Bankable feasibility study | Engineering | 2028-03-24 | 2028-10-29 | 220
6 | ◆ Investment decision |  | 2028-11-09 | 2028-11-09 | [119 empty] | ◆
7 | Permitting & approvals |  | 2028-03-24 | 2029-01-17 | 300
7.1 | Environmental & social impact | Environment | 2028-03-24 | 2028-10-09 | 200
7.2 | Mining licence & water permits | Legal | 2028-08-21 | 2029-01-17 | 150
8 | Development & construction |  | 2028-11-19 | 2030-01-12 | 420
8.1 | Site access, power & water | Projects | 2028-11-19 | 2029-03-18 | 120
8.2 | Process plant construction | EPC | 2029-02-17 | 2029-12-13 | 300
8.3 | Pre-strip / decline development | Mining | 2029-04-18 | 2029-12-13 | 240
9 | Ramp-up & operations |  | 2029-12-24 | 2030-09-09 | 260
9.1 | Commissioning & first production | Operations | 2029-12-24 | 2030-03-23 | 90
9.2 | Ramp to nameplate capacity | Operations | 2030-03-14 | 2030-09-09 | 180
10 | ◆ Commercial production |  | 2030-09-10 | 2030-09-10 | [215 empty] | ◆