## Slide 1
Mobile App Launch Plan
Free Gantt chart template · gantts.app

## Slide 2
Mobile App Launch Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Build hardening
◆ Feature freeze
Crash & ANR triage
Performance & memory pass
Accessibility & device matrix testing
Release candidate build
◆ Release candidate ready
Store listing & assets
Keyword & category research
App name, subtitle & description
Screenshots & preview video
Icon & store graphics
Privacy disclosure & data types
Age rating & content questionnaire
◆ Store listing ready
Beta testing
TestFlight & Play track upload
External tester recruitment
Internal beta
External beta round
Beta feedback triage & fixes
◆ Beta exit criteria met
Store review & submission
Pre-submission compliance check
App Store submission
Google Play submission
App Store review wait
Google Play review wait
Rejection & resubmission buffer
◆ Approved & ready for release
Phased rollout
Release to 1% of users
Expand to 10%
Expand to 50%
◆ Full availability
Launch announcement & press
Day-one patch & monitoring
Crash & ANR monitoring
Day-one patch window
Store review & rating response
Week-one retention review
◆ Post-launch review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Build hardening |  | 2026-08-02 | 2026-09-15 | 45 | 100%
2 | Feature freeze |  | 2026-08-02 | 2026-08-02 | — | —
2.1 | Crash & ANR triage | Engineering | 2026-08-02 | 2026-08-26 | 25 | 100%
2.2 | Performance & memory pass | Engineering | 2026-08-17 | 2026-09-05 | 20 | 100%
2.3 | Accessibility & device matrix testing | QA | 2026-08-22 | 2026-09-15 | 25 | 100%
2.4 | Release candidate build | Engineering | 2026-09-11 | 2026-09-15 | 5 | 100%
3 | Release candidate ready |  | 2026-09-16 | 2026-09-16 | — | —
4 | Store listing & assets |  | 2026-09-01 | 2026-10-20 | 50 | 80%
4.1 | Keyword & category research | Marketing | 2026-09-01 | 2026-09-15 | 15 | 100%
4.2 | App name, subtitle & description | Marketing | 2026-09-11 | 2026-09-25 | 15 | 100%
4.3 | Screenshots & preview video | Design | 2026-09-16 | 2026-10-10 | 25 | 80%
4.4 | Icon & store graphics | Design | 2026-09-16 | 2026-09-30 | 15 | 100%
4.5 | Privacy disclosure & data types | Legal | 2026-10-01 | 2026-10-15 | 15 | 60%
4.6 | Age rating & content questionnaire | Product | 2026-10-11 | 2026-10-20 | 10 | 40%
5 | Store listing ready |  | 2026-10-26 | 2026-10-26 | — | —
6 | Beta testing |  | 2026-09-16 | 2026-10-30 | 45 | 40%
6.1 | TestFlight & Play track upload | Engineering | 2026-09-16 | 2026-09-18 | 3 | 100%
6.2 | External tester recruitment | Marketing | 2026-09-16 | 2026-09-30 | 15 | 100%
6.3 | Internal beta | Staff | 2026-09-19 | 2026-10-02 | 14 | 60%
6.4 | External beta round | Testers | 2026-10-03 | 2026-10-27 | 25 | 0%
6.5 | Beta feedback triage & fixes | Engineering | 2026-10-11 | 2026-10-30 | 20 | 0%

## Slide 4
7 | Beta exit criteria met |  | 2026-10-31 | 2026-10-31 | — | —
8 | Store review & submission |  | 2026-10-31 | 2026-11-27 | 28 | 0%
8.1 | Pre-submission compliance check | Product | 2026-10-31 | 2026-11-04 | 5 | 0%
8.2 | App Store submission | Release manager | 2026-11-05 | 2026-11-05 | 1 | 0%
8.3 | Google Play submission | Release manager | 2026-11-05 | 2026-11-05 | 1 | 0%
8.4 | App Store review wait | Apple | 2026-11-06 | 2026-11-15 | 10 | 0%
8.5 | Google Play review wait | Google | 2026-11-06 | 2026-11-12 | 7 | 0%
8.6 | Rejection & resubmission buffer | Engineering | 2026-11-16 | 2026-11-25 | 10 | 0%
9 | Approved & ready for release |  | 2026-11-28 | 2026-11-28 | — | —
10 | Phased rollout |  | 2026-11-28 | 2026-12-16 | 19 | 0%
10.1 | Release to 1% of users | Release manager | 2026-11-28 | 2026-11-30 | 3 | 0%
10.2 | Expand to 10% | Release manager | 2026-12-02 | 2026-12-04 | 3 | 0%
10.3 | Expand to 50% | Release manager | 2026-12-07 | 2026-12-09 | 3 | 0%
11 | Full availability |  | 2026-12-12 | 2026-12-12 | — | —
11.1 | Launch announcement & press | Marketing | 2026-12-12 | 2026-12-16 | 5 | 0%
12 | Day-one patch & monitoring |  | 2026-11-28 | 2027-01-08 | 42 | 0%
12.1 | Crash & ANR monitoring | Engineering | 2026-11-28 | 2027-01-08 | 42 | 0%
12.2 | Day-one patch window | Engineering | 2026-12-12 | 2026-12-21 | 10 | 0%
12.3 | Store review & rating response | Support | 2026-12-15 | 2027-01-08 | 25 | 0%
12.4 | Week-one retention review | Product | 2026-12-26 | 2026-12-30 | 5 | 0%
13 | Post-launch review |  | 2027-01-09 | 2027-01-09 | — | —