## Slide 1
Moving House
Free Gantt chart template · gantts.app

## Slide 2
Moving House
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Plan & budget
Set moving date & budget
Create a moving inventory
Declutter: sell, donate, recycle
Research & get mover quotes
◆ Plan & budget set
Book & notify
Book movers or hire a van
Book time off & arrange help
Give notice / list the property
Arrange parking & lift access
◆ Movers booked
Change of address & admin
Set up mail redirection
Switch utilities (gas, electric, water)
Transfer broadband & TV
Update address: bank, insurance, licence
Register with local services (school, GP)
◆ Address changes done
Pack
Gather packing supplies
Pack non-essential rooms
Label boxes by room
Pack an essentials / first-night box
◆ Packing complete
Moving week
Confirm details with movers
Defrost fridge & disconnect appliances
Take meter readings & photos
Clean the old home
Moving day
◆ Moved in
Settle in
Unpack the essentials box
Check utilities & set up broadband
Unpack room by room
Register on the electoral roll
◆ Settled in
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Plan & budget |  | 2026-08-02 | 2026-08-15 | 14 | 100%
1.1 | Set moving date & budget | You | 2026-08-02 | 2026-08-04 | 3 | 100%
1.2 | Create a moving inventory | You | 2026-08-04 | 2026-08-07 | 4 | 100%
1.3 | Declutter: sell, donate, recycle | You | 2026-08-05 | 2026-08-29 | 25 | 60%
1.4 | Research & get mover quotes | You | 2026-08-07 | 2026-08-15 | 9 | 70%
2 | Plan & budget set |  | 2026-08-16 | 2026-08-16 | , | ,
3 | Book & notify |  | 2026-08-16 | 2026-08-29 | 14 | 0%
3.1 | Book movers or hire a van | You | 2026-08-16 | 2026-08-19 | 4 | 0%
3.2 | Book time off & arrange help | You | 2026-08-18 | 2026-08-20 | 3 | 0%
3.3 | Give notice / list the property | You | 2026-08-16 | 2026-08-20 | 5 | 0%
3.4 | Arrange parking & lift access | You | 2026-08-20 | 2026-08-23 | 4 | 0%
4 | Movers booked |  | 2026-08-30 | 2026-08-30 | , | ,
5 | Change of address & admin |  | 2026-08-23 | 2026-09-12 | 21 | 0%
5.1 | Set up mail redirection | You | 2026-08-23 | 2026-08-25 | 3 | 0%
5.2 | Switch utilities (gas, electric, water) | You | 2026-08-26 | 2026-09-06 | 12 | 0%
5.3 | Transfer broadband & TV | You | 2026-08-28 | 2026-09-06 | 10 | 0%
5.4 | Update address: bank, insurance, licence | You | 2026-08-30 | 2026-09-10 | 12 | 0%
5.5 | Register with local services (school, GP) | You | 2026-09-01 | 2026-09-10 | 10 | 0%
6 | Address changes done |  | 2026-09-13 | 2026-09-13 | , | ,
7 | Pack |  | 2026-09-06 | 2026-09-23 | 18 | 0%
7.1 | Gather packing supplies | You | 2026-09-06 | 2026-09-08 | 3 | 0%

## Slide 4
7.2 | Pack non-essential rooms | You | 2026-09-08 | 2026-09-20 | 13 | 0%
7.3 | Label boxes by room | You | 2026-09-10 | 2026-09-20 | 11 | 0%
7.4 | Pack an essentials / first-night box | You | 2026-09-21 | 2026-09-22 | 2 | 0%
8 | Packing complete |  | 2026-09-24 | 2026-09-24 | , | ,
9 | Moving week |  | 2026-09-24 | 2026-09-28 | 5 | 0%
9.1 | Confirm details with movers | You | 2026-09-24 | 2026-09-24 | 1 | 0%
9.2 | Defrost fridge & disconnect appliances | You | 2026-09-25 | 2026-09-26 | 2 | 0%
9.3 | Take meter readings & photos | You | 2026-09-27 | 2026-09-27 | 1 | 0%
9.4 | Clean the old home | You | 2026-09-26 | 2026-09-27 | 2 | 0%
9.5 | Moving day | Movers | 2026-09-27 | 2026-09-27 | 1 | 0%
10 | Moved in |  | 2026-09-28 | 2026-09-28 | , | ,
11 | Settle in |  | 2026-09-28 | 2026-10-04 | 7 | 0%
11.1 | Unpack the essentials box | You | 2026-09-28 | 2026-09-29 | 2 | 0%
11.2 | Check utilities & set up broadband | You | 2026-09-28 | 2026-10-01 | 4 | 0%
11.3 | Unpack room by room | You | 2026-09-29 | 2026-10-04 | 6 | 0%
11.4 | Register on the electoral roll | You | 2026-09-30 | 2026-10-03 | 4 | 0%
12 | Settled in |  | 2026-10-05 | 2026-10-05 | , | ,