## Gantt
Moving House
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12
1 | Plan & budget |  | 2026-08-02 | 2026-08-15 | 14 | bar: Aug 3 to Aug 10
1.1 | Set moving date & budget | You | 2026-08-02 | 2026-08-04 | 3 | bar: Aug 3
1.2 | Create a moving inventory | You | 2026-08-04 | 2026-08-07 | 4 | bar: Aug 3
1.3 | Declutter: sell, donate, recycle | You | 2026-08-05 | 2026-08-29 | 25 | bar: Aug 3 to Aug 24
1.4 | Research & get mover quotes | You | 2026-08-07 | 2026-08-15 | 9 | bar: Aug 3 to Aug 10
2 | ◆ Plan & budget set |  | 2026-08-16 | 2026-08-16 | bar: Aug 17
3 | Book & notify |  | 2026-08-16 | 2026-08-29 | 14 | bar: Aug 17 to Aug 24
3.1 | Book movers or hire a van | You | 2026-08-16 | 2026-08-19 | 4 | bar: Aug 17
3.2 | Book time off & arrange help | You | 2026-08-18 | 2026-08-20 | 3 | bar: Aug 17
3.3 | Give notice / list the property | You | 2026-08-16 | 2026-08-20 | 5 | bar: Aug 17
3.4 | Arrange parking & lift access | You | 2026-08-20 | 2026-08-23 | 4 | bar: Aug 17 to Aug 24
4 | ◆ Movers booked |  | 2026-08-30 | 2026-08-30 | bar: Aug 31
5 | Change of address & admin |  | 2026-08-23 | 2026-09-12 | 21 | bar: Aug 24 to Sep 7
5.1 | Set up mail redirection | You | 2026-08-23 | 2026-08-25 | 3 | bar: Aug 24
5.2 | Switch utilities (gas, electric, water) | You | 2026-08-26 | 2026-09-06 | 12 | bar: Aug 24 to Sep 7
5.3 | Transfer broadband & TV | You | 2026-08-28 | 2026-09-06 | 10 | bar: Aug 24 to Sep 7
5.4 | Update address: bank, insurance, licence | You | 2026-08-30 | 2026-09-10 | 12 | bar: Aug 31 to Sep 7
5.5 | Register with local services (school, GP) | You | 2026-09-01 | 2026-09-10 | 10 | bar: Aug 31 to Sep 7
6 | ◆ Address changes done |  | 2026-09-13 | 2026-09-13 | bar: Sep 14
7 | Pack |  | 2026-09-06 | 2026-09-23 | 18 | bar: Sep 7 to Sep 21
7.1 | Gather packing supplies | You | 2026-09-06 | 2026-09-08 | 3 | bar: Sep 7
7.2 | Pack non-essential rooms | You | 2026-09-08 | 2026-09-20 | 13 | bar: Sep 7 to Sep 21
7.3 | Label boxes by room | You | 2026-09-10 | 2026-09-20 | 11 | bar: Sep 7 to Sep 21
7.4 | Pack an essentials / first-night box | You | 2026-09-21 | 2026-09-22 | 2 | bar: Sep 21
8 | ◆ Packing complete |  | 2026-09-24 | 2026-09-24 | bar: Sep 21
9 | Moving week |  | 2026-09-24 | 2026-09-28 | 5 | bar: Sep 21 to Sep 28
9.1 | Confirm details with movers | You | 2026-09-24 | 2026-09-24 | 1 | bar: Sep 21
9.2 | Defrost fridge & disconnect appliances | You | 2026-09-25 | 2026-09-26 | 2 | bar: Sep 21
9.3 | Take meter readings & photos | You | 2026-09-27 | 2026-09-27 | 1 | bar: Sep 28
9.4 | Clean the old home | You | 2026-09-26 | 2026-09-27 | 2 | bar: Sep 21 to Sep 28
9.5 | Moving day | Movers | 2026-09-27 | 2026-09-27 | 1 | bar: Sep 28
10 | ◆ Moved in |  | 2026-09-28 | 2026-09-28 | bar: Sep 28
11 | Settle in |  | 2026-09-28 | 2026-10-04 | 7 | bar: Sep 28 to Oct 5
11.1 | Unpack the essentials box | You | 2026-09-28 | 2026-09-29 | 2 | bar: Sep 28
11.2 | Check utilities & set up broadband | You | 2026-09-28 | 2026-10-01 | 4 | bar: Sep 28
11.3 | Unpack room by room | You | 2026-09-29 | 2026-10-04 | 6 | bar: Sep 28 to Oct 5
11.4 | Register on the electoral roll | You | 2026-09-30 | 2026-10-03 | 4 | bar: Sep 28
12 | ◆ Settled in |  | 2026-10-05 | 2026-10-05 | bar: Oct 5