## Slide 1
Museum Exhibition Planning
Free Gantt chart template · gantts.app

## Slide 2
Museum Exhibition Planning
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Concept & curatorial development
Exhibition concept & thesis
Object wish list & checklist v1
Budget & funding approval
◆ Opening date fixed in gallery calendar
Government indemnity application
Catalogue commissioning & essays
Loans & lender agreements
Formal loan requests issued
Lender responses & substitutions
Facilities reports supplied to lenders
Insurance valuations & cover placement
◆ Loan agreements signed
Courier requirements & escort schedule
◆ Final checklist frozen
Design & fabrication
Exhibition design & 3D layout
AV & lighting design
Graphic design & interpretation text
Casework & mount design
Casework fabrication & off-gassing test
Mount making & object supports
Conservation, couriers & transport
Condition survey of home collection objects
Conservation treatment & framing
Crating & packing specifications
Export licences & customs clearance
Loan collection & courier flights
◆ Objects arrive on site
Gallery preparation & installation
Previous exhibition de-install
Gallery repaint & floor preparation
Environmental stabilisation - RH & temperature
◆ Environmental conditions logged and accepted
Casework installation & lighting focus
Graphics & wall text installation
Incoming condition reporting with couriers
Object installation & mounting
Courier sign-off & case sealing
Opening, run & de-install
Marketing campaign & ticketing live
Final walkthrough & snagging
Press preview & private view
◆ Exhibition opens to public
Public programme & events run
Light and RH monitoring during run
Rotation of light-sensitive works
De-install & outgoing condition reports
◆ Objects returned to lenders
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept & curatorial development |  | 2026-08-02 | 2027-03-19 | 230 | 100%
1.1 | Exhibition concept & thesis | Curator | 2026-08-02 | 2026-09-10 | 40 | 100%
1.2 | Object wish list & checklist v1 | Curator | 2026-09-01 | 2026-10-15 | 45 | 100%
1.3 | Budget & funding approval | Director | 2026-10-01 | 2026-11-14 | 45 | 100%
2 | Opening date fixed in gallery calendar |  | 2026-11-15 | 2026-11-15 | — | —
2.1 | Government indemnity application | Registrar | 2026-11-15 | 2027-01-13 | 60 | 90%
2.2 | Catalogue commissioning & essays | Publications | 2026-11-20 | 2027-03-19 | 120 | 60%
3 | Loans & lender agreements |  | 2026-11-15 | 2027-05-28 | 195 | 50%
3.1 | Formal loan requests issued | Registrar | 2026-11-15 | 2026-12-14 | 30 | 100%
3.2 | Lender responses & substitutions | Curator | 2026-12-15 | 2027-02-27 | 75 | 70%
3.3 | Facilities reports supplied to lenders | Registrar | 2026-12-20 | 2027-02-02 | 45 | 100%
3.4 | Insurance valuations & cover placement | Registrar | 2027-02-28 | 2027-04-13 | 45 | 20%
4 | Loan agreements signed |  | 2027-04-09 | 2027-04-09 | — | —
4.1 | Courier requirements & escort schedule | Registrar | 2027-04-09 | 2027-05-28 | 50 | 0%
5 | Final checklist frozen |  | 2027-04-19 | 2027-04-19 | — | —
6 | Design & fabrication |  | 2026-12-30 | 2027-06-27 | 180 | 20%
6.1 | Exhibition design & 3D layout | Designer | 2026-12-30 | 2027-02-22 | 55 | 80%
6.2 | AV & lighting design | Designer | 2027-03-20 | 2027-05-08 | 50 | 20%
6.3 | Graphic design & interpretation text | Interpretation | 2027-02-23 | 2027-04-23 | 60 | 30%
6.4 | Casework & mount design | Designer | 2027-02-23 | 2027-04-08 | 45 | 40%
6.5 | Casework fabrication & off-gassing test | Fabricator | 2027-04-14 | 2027-06-12 | 60 | 0%

## Slide 4
6.6 | Mount making & object supports | Mount maker | 2027-04-21 | 2027-06-14 | 55 | 0%
7 | Conservation, couriers & transport |  | 2027-04-19 | 2027-07-27 | 100 | 0%
7.1 | Condition survey of home collection objects | Conservation | 2027-04-19 | 2027-05-28 | 40 | 0%
7.2 | Conservation treatment & framing | Conservation | 2027-05-29 | 2027-07-22 | 55 | 0%
7.3 | Crating & packing specifications | Registrar | 2027-05-14 | 2027-06-12 | 30 | 0%
7.4 | Export licences & customs clearance | Registrar | 2027-05-14 | 2027-06-27 | 45 | 0%
7.5 | Loan collection & courier flights | Art handlers | 2027-06-28 | 2027-07-22 | 25 | 0%
8 | Objects arrive on site |  | 2027-07-26 | 2027-07-26 | — | —
9 | Gallery preparation & installation |  | 2027-05-29 | 2027-08-26 | 90 | 0%
9.1 | Previous exhibition de-install | Technicians | 2027-05-29 | 2027-06-12 | 15 | 0%
9.2 | Gallery repaint & floor preparation | Technicians | 2027-06-13 | 2027-07-02 | 20 | 0%
9.3 | Environmental stabilisation - RH & temperature | Facilities | 2027-07-03 | 2027-07-27 | 25 | 0%
10 | Environmental conditions logged and accepted |  | 2027-07-28 | 2027-07-28 | — | —
10.1 | Casework installation & lighting focus | Technicians | 2027-07-08 | 2027-08-01 | 25 | 0%
10.2 | Graphics & wall text installation | Technicians | 2027-08-02 | 2027-08-16 | 15 | 0%
10.3 | Incoming condition reporting with couriers | Conservation | 2027-07-28 | 2027-08-06 | 10 | 0%
10.4 | Object installation & mounting | Art handlers | 2027-08-07 | 2027-08-20 | 14 | 0%
10.5 | Courier sign-off & case sealing | Registrar | 2027-08-21 | 2027-08-24 | 4 | 0%
11 | Opening, run & de-install |  | 2027-07-03 | 2027-12-24 | 175 | 0%
11.1 | Marketing campaign & ticketing live | Marketing | 2027-07-03 | 2027-08-28 | 57 | 0%
11.2 | Final walkthrough & snagging | Curator | 2027-08-25 | 2027-08-28 | 4 | 0%
11.3 | Press preview & private view | Marketing | 2027-08-29 | 2027-08-31 | 3 | 0%
12 | Exhibition opens to |  | 2027-09-02 | 2027-09-02 | — | —

## Slide 5
 | public |  |  |  |  | 
12.1 | Public programme & events run | Learning | 2027-09-02 | 2027-11-30 | 90 | 0%
12.2 | Light and RH monitoring during run | Conservation | 2027-09-02 | 2027-11-30 | 90 | 0%
12.3 | Rotation of light-sensitive works | Conservation | 2027-10-16 | 2027-10-25 | 10 | 0%
12.4 | De-install & outgoing condition reports | Conservation | 2027-12-01 | 2027-12-15 | 15 | 0%
13 | Objects returned to lenders |  | 2027-12-25 | 2027-12-25 | — | —