## Gantt
Museum Exhibition Planning
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27
1 | Concept & curatorial development |  | 2026-08-02 | 2027-03-19 | 230
1.1 | Exhibition concept & thesis | Curator | 2026-08-02 | 2026-09-10 | 40
1.2 | Object wish list & checklist v1 | Curator | 2026-09-01 | 2026-10-15 | 45
1.3 | Budget & funding approval | Director | 2026-10-01 | 2026-11-14 | 45
2 | ◆ Opening date fixed in gallery calendar |  | 2026-11-15 | 2026-11-15 | [16 empty] | ◆
2.1 | Government indemnity application | Registrar | 2026-11-15 | 2027-01-13 | 60
2.2 | Catalogue commissioning & essays | Publications | 2026-11-20 | 2027-03-19 | 120
3 | Loans & lender agreements |  | 2026-11-15 | 2027-05-28 | 195
3.1 | Formal loan requests issued | Registrar | 2026-11-15 | 2026-12-14 | 30
3.2 | Lender responses & substitutions | Curator | 2026-12-15 | 2027-02-27 | 75
3.3 | Facilities reports supplied to lenders | Registrar | 2026-12-20 | 2027-02-02 | 45
3.4 | Insurance valuations & cover placement | Registrar | 2027-02-28 | 2027-04-13 | 45
4 | ◆ Loan agreements signed |  | 2027-04-09 | 2027-04-09 | [36 empty] | ◆
4.1 | Courier requirements & escort schedule | Registrar | 2027-04-09 | 2027-05-28 | 50
5 | ◆ Final checklist frozen |  | 2027-04-19 | 2027-04-19 | [38 empty] | ◆
6 | Design & fabrication |  | 2026-12-30 | 2027-06-27 | 180
6.1 | Exhibition design & 3D layout | Designer | 2026-12-30 | 2027-02-22 | 55
6.2 | AV & lighting design | Designer | 2027-03-20 | 2027-05-08 | 50
6.3 | Graphic design & interpretation text | Interpretation | 2027-02-23 | 2027-04-23 | 60
6.4 | Casework & mount design | Designer | 2027-02-23 | 2027-04-08 | 45
6.5 | Casework fabrication & off-gassing test | Fabricator | 2027-04-14 | 2027-06-12 | 60
6.6 | Mount making & object supports | Mount maker | 2027-04-21 | 2027-06-14 | 55
7 | Conservation, couriers & transport |  | 2027-04-19 | 2027-07-27 | 100
7.1 | Condition survey of home collection objects | Conservation | 2027-04-19 | 2027-05-28 | 40
7.2 | Conservation treatment & framing | Conservation | 2027-05-29 | 2027-07-22 | 55
7.3 | Crating & packing specifications | Registrar | 2027-05-14 | 2027-06-12 | 30
7.4 | Export licences & customs clearance | Registrar | 2027-05-14 | 2027-06-27 | 45
7.5 | Loan collection & courier flights | Art handlers | 2027-06-28 | 2027-07-22 | 25
8 | ◆ Objects arrive on site |  | 2027-07-26 | 2027-07-26 | [52 empty] | ◆
9 | Gallery preparation & installation |  | 2027-05-29 | 2027-08-26 | 90
9.1 | Previous exhibition de-install | Technicians | 2027-05-29 | 2027-06-12 | 15
9.2 | Gallery repaint & floor preparation | Technicians | 2027-06-13 | 2027-07-02 | 20
9.3 | Environmental stabilisation - RH & temperature | Facilities | 2027-07-03 | 2027-07-27 | 25
10 | ◆ Environmental conditions logged and accepted |  | 2027-07-28 | 2027-07-28 | [52 empty] | ◆
10.1 | Casework installation & lighting focus | Technicians | 2027-07-08 | 2027-08-01 | 25
10.2 | Graphics & wall text installation | Technicians | 2027-08-02 | 2027-08-16 | 15
10.3 | Incoming condition reporting with couriers | Conservation | 2027-07-28 | 2027-08-06 | 10
10.4 | Object installation & mounting | Art handlers | 2027-08-07 | 2027-08-20 | 14
10.5 | Courier sign-off & case sealing | Registrar | 2027-08-21 | 2027-08-24 | 4
11 | Opening, run & de-install |  | 2027-07-03 | 2027-12-24 | 175
11.1 | Marketing campaign & ticketing live | Marketing | 2027-07-03 | 2027-08-28 | 57
11.2 | Final walkthrough & snagging | Curator | 2027-08-25 | 2027-08-28 | 4
11.3 | Press preview & private view | Marketing | 2027-08-29 | 2027-08-31 | 3
12 | ◆ Exhibition opens to public |  | 2027-09-02 | 2027-09-02 | [57 empty] | ◆
12.1 | Public programme & events run | Learning | 2027-09-02 | 2027-11-30 | 90
12.2 | Light and RH monitoring during run | Conservation | 2027-09-02 | 2027-11-30 | 90
12.3 | Rotation of light-sensitive works | Conservation | 2027-10-16 | 2027-10-25 | 10
12.4 | De-install & outgoing condition reports | Conservation | 2027-12-01 | 2027-12-15 | 15
13 | ◆ Objects returned to lenders |  | 2027-12-25 | 2027-12-25 | [73 empty] | ◆