## Slide 1
New Product Development Plan
Free Gantt chart template · gantts.app

## Slide 2
New Product Development Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Concept
Opportunity & customer needs
Concept sketches & options
Initial business case
◆ Gate 1: concept approved
Feasibility
Technical feasibility studies
Make-or-buy analysis
Regulatory & standards scan
Cost model & risk assessment
◆ Gate 2: feasibility passed
Detailed design
System architecture
Detail design & DFMA
Bill of materials
Supplier engagement
Design review
◆ Gate 3: design freeze
Prototyping
Alpha build
Engineering evaluation
Design iterations
Beta build
Validation & testing
Design verification testing
Environmental & life testing
Certification submissions
User trials
◆ Gate 4: design validated
Tooling & industrialization
Tool design
Tool manufacture
First article inspection
Process development & fixtures
Supplier qualification
Pilot production & handover
Pilot production run
Production part approval
Ramp plan & capacity booking
Documentation & training pack
Handover to launch team
◆ Gate 5: production release
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept |  | 2026-08-02 | 2026-09-30 | 60 | 100%
1.1 | Opportunity & customer needs | Product | 2026-08-02 | 2026-08-31 | 30 | 100%
1.2 | Concept sketches & options | Design | 2026-08-22 | 2026-09-20 | 30 | 100%
1.3 | Initial business case | Product | 2026-09-06 | 2026-09-30 | 25 | 100%
2 | Gate 1: concept approved |  | 2026-10-01 | 2026-10-01 | — | —
3 | Feasibility |  | 2026-10-01 | 2026-12-09 | 70 | 100%
3.1 | Technical feasibility studies | Engineering | 2026-10-01 | 2026-11-14 | 45 | 100%
3.2 | Make-or-buy analysis | Supply chain | 2026-10-16 | 2026-11-14 | 30 | 100%
3.3 | Regulatory & standards scan | Compliance | 2026-10-11 | 2026-11-19 | 40 | 100%
3.4 | Cost model & risk assessment | Product | 2026-11-10 | 2026-12-09 | 30 | 100%
4 | Gate 2: feasibility passed |  | 2026-12-10 | 2026-12-10 | — | —
5 | Detailed design |  | 2026-12-10 | 2027-04-28 | 140 | 70%
5.1 | System architecture | Engineering | 2026-12-10 | 2027-01-18 | 40 | 100%
5.2 | Detail design & DFMA | Engineering | 2027-01-14 | 2027-04-13 | 90 | 70%
5.3 | Bill of materials | Engineering | 2027-02-28 | 2027-04-08 | 40 | 50%
5.4 | Supplier engagement | Supply chain | 2027-01-29 | 2027-04-08 | 70 | 60%
5.5 | Design review | Engineering | 2027-04-09 | 2027-04-28 | 20 | 20%
6 | Gate 3: design freeze |  | 2027-04-29 | 2027-04-29 | — | —
7 | Prototyping |  | 2027-02-18 | 2027-07-27 | 160 | 30%
7.1 | Alpha build | Prototype shop | 2027-02-18 | 2027-04-03 | 45 | 60%
7.2 | Engineering evaluation | Engineering | 2027-04-04 | 2027-05-08 | 35 | 20%

## Slide 4
7.3 | Design iterations | Engineering | 2027-05-04 | 2027-06-12 | 40 | 0%
7.4 | Beta build | Prototype shop | 2027-06-13 | 2027-07-27 | 45 | 0%
8 | Validation & testing |  | 2027-07-28 | 2028-01-03 | 160 | 0%
8.1 | Design verification testing | Test | 2027-07-28 | 2027-09-15 | 50 | 0%
8.2 | Environmental & life testing | Test | 2027-08-17 | 2027-11-14 | 90 | 0%
8.3 | Certification submissions | Compliance | 2027-09-06 | 2027-12-14 | 100 | 0%
8.4 | User trials | Product | 2027-09-26 | 2027-11-09 | 45 | 0%
9 | Gate 4: design validated |  | 2028-01-04 | 2028-01-04 | — | —
10 | Tooling & industrialization |  | 2027-05-04 | 2027-12-19 | 230 | 0%
10.1 | Tool design | Tooling | 2027-05-04 | 2027-06-17 | 45 | 0%
10.2 | Tool manufacture | Toolmaker | 2027-06-18 | 2027-10-15 | 120 | 0%
10.3 | First article inspection | Quality | 2027-10-16 | 2027-11-09 | 25 | 0%
10.4 | Process development & fixtures | Manufacturing | 2027-09-06 | 2027-11-24 | 80 | 0%
10.5 | Supplier qualification | Supply chain | 2027-10-06 | 2027-12-19 | 75 | 0%
11 | Pilot production & handover |  | 2027-12-20 | 2028-03-23 | 95 | 0%
11.1 | Pilot production run | Manufacturing | 2027-12-20 | 2028-01-18 | 30 | 0%
11.2 | Production part approval | Quality | 2028-01-19 | 2028-02-12 | 25 | 0%
11.3 | Ramp plan & capacity booking | Operations | 2028-01-24 | 2028-02-27 | 35 | 0%
11.4 | Documentation & training pack | Engineering | 2028-02-03 | 2028-03-08 | 35 | 0%
11.5 | Handover to launch team | Product | 2028-03-09 | 2028-03-23 | 15 | 0%
12 | Gate 5: production release |  | 2028-03-24 | 2028-03-24 | — | —