## Gantt
New Product Development Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27
1 | Concept |  | 2026-08-02 | 2026-09-30 | 60
1.1 | Opportunity & customer needs | Product | 2026-08-02 | 2026-08-31 | 30
1.2 | Concept sketches & options | Design | 2026-08-22 | 2026-09-20 | 30
1.3 | Initial business case | Product | 2026-09-06 | 2026-09-30 | 25
2 | ◆ Gate 1: concept approved |  | 2026-10-01 | 2026-10-01 | [9 empty] | ◆
3 | Feasibility |  | 2026-10-01 | 2026-12-09 | 70
3.1 | Technical feasibility studies | Engineering | 2026-10-01 | 2026-11-14 | 45
3.2 | Make-or-buy analysis | Supply chain | 2026-10-16 | 2026-11-14 | 30
3.3 | Regulatory & standards scan | Compliance | 2026-10-11 | 2026-11-19 | 40
3.4 | Cost model & risk assessment | Product | 2026-11-10 | 2026-12-09 | 30
4 | ◆ Gate 2: feasibility passed |  | 2026-12-10 | 2026-12-10 | [19 empty] | ◆
5 | Detailed design |  | 2026-12-10 | 2027-04-28 | 140
5.1 | System architecture | Engineering | 2026-12-10 | 2027-01-18 | 40
5.2 | Detail design & DFMA | Engineering | 2027-01-14 | 2027-04-13 | 90
5.3 | Bill of materials | Engineering | 2027-02-28 | 2027-04-08 | 40
5.4 | Supplier engagement | Supply chain | 2027-01-29 | 2027-04-08 | 70
5.5 | Design review | Engineering | 2027-04-09 | 2027-04-28 | 20
6 | ◆ Gate 3: design freeze |  | 2027-04-29 | 2027-04-29 | [39 empty] | ◆
7 | Prototyping |  | 2027-02-18 | 2027-07-27 | 160
7.1 | Alpha build | Prototype shop | 2027-02-18 | 2027-04-03 | 45
7.2 | Engineering evaluation | Engineering | 2027-04-04 | 2027-05-08 | 35
7.3 | Design iterations | Engineering | 2027-05-04 | 2027-06-12 | 40
7.4 | Beta build | Prototype shop | 2027-06-13 | 2027-07-27 | 45
8 | Validation & testing |  | 2027-07-28 | 2028-01-03 | 160
8.1 | Design verification testing | Test | 2027-07-28 | 2027-09-15 | 50
8.2 | Environmental & life testing | Test | 2027-08-17 | 2027-11-14 | 90
8.3 | Certification submissions | Compliance | 2027-09-06 | 2027-12-14 | 100
8.4 | User trials | Product | 2027-09-26 | 2027-11-09 | 45
9 | ◆ Gate 4: design validated |  | 2028-01-04 | 2028-01-04 | [75 empty] | ◆
10 | Tooling & industrialization |  | 2027-05-04 | 2027-12-19 | 230
10.1 | Tool design | Tooling | 2027-05-04 | 2027-06-17 | 45
10.2 | Tool manufacture | Toolmaker | 2027-06-18 | 2027-10-15 | 120
10.3 | First article inspection | Quality | 2027-10-16 | 2027-11-09 | 25
10.4 | Process development & fixtures | Manufacturing | 2027-09-06 | 2027-11-24 | 80
10.5 | Supplier qualification | Supply chain | 2027-10-06 | 2027-12-19 | 75
11 | Pilot production & handover |  | 2027-12-20 | 2028-03-23 | 95
11.1 | Pilot production run | Manufacturing | 2027-12-20 | 2028-01-18 | 30
11.2 | Production part approval | Quality | 2028-01-19 | 2028-02-12 | 25
11.3 | Ramp plan & capacity booking | Operations | 2028-01-24 | 2028-02-27 | 35
11.4 | Documentation & training pack | Engineering | 2028-02-03 | 2028-03-08 | 35
11.5 | Handover to launch team | Product | 2028-03-09 | 2028-03-23 | 15
12 | ◆ Gate 5: production release |  | 2028-03-24 | 2028-03-24 | [86 empty] | ◆