## Slide 1
Fundraising Campaign Plan
Free Gantt chart template · gantts.app

## Slide 2
Fundraising Campaign Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Feasibility & case for support
Needs assessment & costing
Feasibility interviews
Case for support drafted
Target setting & board approval
◆ Target approved
Prospect research & pipeline
Database review & cleansing
Wealth & capacity screening
Gift range chart
Prospect rating & portfolios
Leadership & quiet phase
Campaign cabinet recruitment
Board & cabinet giving
Lead gift cultivation
Lead gift solicitation
Major gift solicitation
Pledge documentation
◆ Quiet phase target reached
Public launch
Launch materials & case summary
Media & social plan
Launch event
◆ Public launch announced
Broad appeal to donor base
Events & appeals
Direct mail & email appeals
Community & peer-to-peer
Campaign gala
Giving day push
Matched giving
Match sponsor secured
Match window promotion
Match period
Match reconciliation
Stewardship & reporting
Acknowledgement & receipting
Donor recognition & naming
Impact reporting to donors
Pledge collection schedule
Campaign close report
◆ Campaign closed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Feasibility & case for support |  | 2026-08-02 | 2026-11-29 | 120 | 100%
1.1 | Needs assessment & costing | Programme lead | 2026-08-02 | 2026-09-05 | 35 | 100%
1.2 | Feasibility interviews | Development director | 2026-09-01 | 2026-10-20 | 50 | 100%
1.3 | Case for support drafted | Communications | 2026-10-01 | 2026-11-14 | 45 | 100%
1.4 | Target setting & board approval | Board | 2026-10-31 | 2026-11-29 | 30 | 100%
2 | Target approved |  | 2026-11-30 | 2026-11-30 | — | —
3 | Prospect research & pipeline |  | 2026-10-31 | 2027-02-17 | 110 | 90%
3.1 | Database review & cleansing | Database manager | 2026-10-31 | 2026-12-09 | 40 | 100%
3.2 | Wealth & capacity screening | Prospect research | 2026-11-30 | 2027-01-13 | 45 | 100%
3.3 | Gift range chart | Development director | 2026-12-30 | 2027-01-18 | 20 | 100%
3.4 | Prospect rating & portfolios | Development director | 2027-01-14 | 2027-02-17 | 35 | 80%
4 | Leadership & quiet phase |  | 2026-12-30 | 2027-11-24 | 330 | 40%
4.1 | Campaign cabinet recruitment | Chair | 2026-12-30 | 2027-02-27 | 60 | 100%
4.2 | Board & cabinet giving | Chair | 2027-02-18 | 2027-04-18 | 60 | 80%
4.3 | Lead gift cultivation | Development director | 2027-02-18 | 2027-07-07 | 140 | 60%
4.4 | Lead gift solicitation | Development director | 2027-05-29 | 2027-09-25 | 120 | 30%
4.5 | Major gift solicitation | Major gifts team | 2027-07-28 | 2027-11-24 | 120 | 10%
4.6 | Pledge documentation | Finance | 2027-06-28 | 2027-11-24 | 150 | 20%
5 | Quiet phase target reached |  | 2027-11-25 | 2027-11-25 | — | —
6 | Public launch |  | 2027-09-26 | 2027-12-24 | 90 | 0%
6.1 | Launch materials & case summary | Communications | 2027-09-26 | 2027-11-09 | 45 | 0%

## Slide 4
6.2 | Media & social plan | Communications | 2027-10-26 | 2027-12-04 | 40 | 0%
6.3 | Launch event | Events | 2027-12-05 | 2027-12-07 | 3 | 0%
7 | Public launch announced |  | 2027-12-08 | 2027-12-08 | — | —
7.1 | Broad appeal to donor base | Development team | 2027-12-10 | 2027-12-24 | 15 | 0%
8 | Events & appeals |  | 2027-12-10 | 2028-07-16 | 220 | 0%
8.1 | Direct mail & email appeals | Development team | 2027-12-10 | 2028-06-06 | 180 | 0%
8.2 | Community & peer-to-peer | Community fundraiser | 2028-01-14 | 2028-06-01 | 140 | 0%
8.3 | Campaign gala | Events | 2028-03-24 | 2028-03-25 | 2 | 0%
8.4 | Giving day push | Development team | 2028-05-23 | 2028-05-25 | 3 | 0%
9 | Matched giving |  | 2027-10-26 | 2028-05-22 | 210 | 0%
9.1 | Match sponsor secured | Development director | 2027-10-26 | 2027-12-24 | 60 | 0%
9.2 | Match window promotion | Communications | 2028-01-24 | 2028-02-22 | 30 | 0%
9.3 | Match period | Development team | 2028-02-23 | 2028-04-22 | 60 | 0%
9.4 | Match reconciliation | Finance | 2028-04-23 | 2028-05-22 | 30 | 0%
10 | Stewardship & reporting |  | 2027-02-18 | 2028-08-30 | 560 | 20%
10.1 | Acknowledgement & receipting | Database manager | 2027-02-18 | 2028-08-10 | 540 | 30%
10.2 | Donor recognition & naming | Development director | 2027-12-15 | 2028-04-12 | 120 | 0%
10.3 | Impact reporting to donors | Programme lead | 2028-04-13 | 2028-06-11 | 60 | 0%
10.4 | Pledge collection schedule | Finance | 2027-11-25 | 2028-08-30 | 280 | 0%
10.5 | Campaign close report | Development director | 2028-08-01 | 2028-08-30 | 30 | 0%
11 | Campaign closed |  | 2028-08-31 | 2028-08-31 | — | —