## Gantt
Fundraising Campaign Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4
1 | Feasibility & case for support |  | 2026-08-02 | 2026-11-29 | 120
1.1 | Needs assessment & costing | Programme lead | 2026-08-02 | 2026-09-05 | 35
1.2 | Feasibility interviews | Development director | 2026-09-01 | 2026-10-20 | 50
1.3 | Case for support drafted | Communications | 2026-10-01 | 2026-11-14 | 45
1.4 | Target setting & board approval | Board | 2026-10-31 | 2026-11-29 | 30
2 | ◆ Target approved |  | 2026-11-30 | 2026-11-30 | [18 empty] | ◆
3 | Prospect research & pipeline |  | 2026-10-31 | 2027-02-17 | 110
3.1 | Database review & cleansing | Database manager | 2026-10-31 | 2026-12-09 | 40
3.2 | Wealth & capacity screening | Prospect research | 2026-11-30 | 2027-01-13 | 45
3.3 | Gift range chart | Development director | 2026-12-30 | 2027-01-18 | 20
3.4 | Prospect rating & portfolios | Development director | 2027-01-14 | 2027-02-17 | 35
4 | Leadership & quiet phase |  | 2026-12-30 | 2027-11-24 | 330
4.1 | Campaign cabinet recruitment | Chair | 2026-12-30 | 2027-02-27 | 60
4.2 | Board & cabinet giving | Chair | 2027-02-18 | 2027-04-18 | 60
4.3 | Lead gift cultivation | Development director | 2027-02-18 | 2027-07-07 | 140
4.4 | Lead gift solicitation | Development director | 2027-05-29 | 2027-09-25 | 120
4.5 | Major gift solicitation | Major gifts team | 2027-07-28 | 2027-11-24 | 120
4.6 | Pledge documentation | Finance | 2027-06-28 | 2027-11-24 | 150
5 | ◆ Quiet phase target reached |  | 2027-11-25 | 2027-11-25 | [69 empty] | ◆
6 | Public launch |  | 2027-09-26 | 2027-12-24 | 90
6.1 | Launch materials & case summary | Communications | 2027-09-26 | 2027-11-09 | 45
6.2 | Media & social plan | Communications | 2027-10-26 | 2027-12-04 | 40
6.3 | Launch event | Events | 2027-12-05 | 2027-12-07 | 3
7 | ◆ Public launch announced |  | 2027-12-08 | 2027-12-08 | [71 empty] | ◆
7.1 | Broad appeal to donor base | Development team | 2027-12-10 | 2027-12-24 | 15
8 | Events & appeals |  | 2027-12-10 | 2028-07-16 | 220
8.1 | Direct mail & email appeals | Development team | 2027-12-10 | 2028-06-06 | 180
8.2 | Community & peer-to-peer | Community fundraiser | 2028-01-14 | 2028-06-01 | 140
8.3 | Campaign gala | Events | 2028-03-24 | 2028-03-25 | 2
8.4 | Giving day push | Development team | 2028-05-23 | 2028-05-25 | 3
9 | Matched giving |  | 2027-10-26 | 2028-05-22 | 210
9.1 | Match sponsor secured | Development director | 2027-10-26 | 2027-12-24 | 60
9.2 | Match window promotion | Communications | 2028-01-24 | 2028-02-22 | 30
9.3 | Match period | Development team | 2028-02-23 | 2028-04-22 | 60
9.4 | Match reconciliation | Finance | 2028-04-23 | 2028-05-22 | 30
10 | Stewardship & reporting |  | 2027-02-18 | 2028-08-30 | 560
10.1 | Acknowledgement & receipting | Database manager | 2027-02-18 | 2028-08-10 | 540
10.2 | Donor recognition & naming | Development director | 2027-12-15 | 2028-04-12 | 120
10.3 | Impact reporting to donors | Programme lead | 2028-04-13 | 2028-06-11 | 60
10.4 | Pledge collection schedule | Finance | 2027-11-25 | 2028-08-30 | 280
10.5 | Campaign close report | Development director | 2028-08-01 | 2028-08-30 | 30
11 | ◆ Campaign closed |  | 2028-08-31 | 2028-08-31 | [109 empty] | ◆