## Slide 1
Nuclear Decommissioning
Free Gantt chart template · gantts.app

## Slide 2
Nuclear Decommissioning
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
May 7
May 21
Jun 4
Jun 18
Jul 2
Jul 16
Jul 30
Aug 13
Aug 27
Sep 10
Sep 24
Oct 8
Oct 22
Nov 5
Nov 19
Dec 3
Post-operational clean-out & characterisation
Defuelling & fuel transfer off site
Radiological characterisation survey
Legacy waste inventory & material accountancy
Asbestos & hazardous material survey
Decommissioning strategy & end-state definition
◆ Fuel-free status declared
◆ Characterisation baseline issued
Regulatory permissioning & waste route agreement
Safety case & hazard analysis for dismantling
Environmental permit variation application
Waste acceptance criteria agreed with disposal site
Disposal route capacity & consignment booking
ALARP dose budget & radiological protection plan
◆ Regulator permission to start dismantling
◆ Waste route confirmed available
Ancillary plant removal & containment
Asbestos removal & conventional hazard clearance
Ventilation & containment tent installation
Redundant plant & pipework de-planting
Active drains & pond clean-out
Decontamination of accessible surfaces
◆ Ancillary buildings radiologically cleared
Reactor & primary circuit dismantling
Remote handling & cutting equipment trials
Dose budget allocation per work area
Primary circuit segmentation & size reduction
Dose uptake review & shift rotation adjustment
Reactor internals removal under shielding
Bioshield & activated concrete removal
◆ Reactor building emptied
Waste packaging, consignment & disposal
Waste segregation, assay & characterisation records
Intermediate-level waste packaging into containers
Low-level waste consignment to disposal facility
Interim store loading & container monitoring
Free-release material clearance & recycling
◆ All active waste consigned or stored
Demolition, remediation & delicensing
Final radiological survey of structures
Conventional demolition of cleared buildings
Land quality assessment & soil remediation
Site end-state survey & records package
Regulator delicensing decision
◆ Site delicensed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Post-operational clean-out & characterisation |  | 2026-08-02 | 2027-03-19 | 230 | 90%
1.1 | Defuelling & fuel transfer off site | Operations | 2026-08-02 | 2026-11-29 | 120 | 100%
1.2 | Radiological characterisation survey | Characterisation | 2026-10-01 | 2027-01-18 | 110 | 80%
1.3 | Legacy waste inventory & material accountancy | Waste | 2026-11-10 | 2027-02-07 | 90 | 70%
1.4 | Asbestos & hazardous material survey | Characterisation | 2026-11-20 | 2027-01-18 | 60 | 60%
1.5 | Decommissioning strategy & end-state definition | Client | 2026-12-30 | 2027-03-19 | 80 | 40%
2 | Fuel-free status declared |  | 2026-11-30 | 2026-11-30 | — | —
3 | Characterisation baseline issued |  | 2027-03-20 | 2027-03-20 | — | —
4 | Regulatory permissioning & waste route agreement |  | 2027-01-19 | 2027-08-26 | 220 | 20%
4.1 | Safety case & hazard analysis for dismantling | Safety case | 2027-01-19 | 2027-05-08 | 110 | 40%
4.2 | Environmental permit variation application | Regulatory | 2027-03-20 | 2027-06-27 | 100 | 10%
4.3 | Waste acceptance criteria agreed with disposal site | Waste | 2027-03-30 | 2027-06-27 | 90 | 0%
4.4 | Disposal route capacity & consignment booking | Waste | 2027-05-29 | 2027-08-26 | 90 | 0%
4.5 | ALARP dose budget & radiological protection plan | Rad protection | 2027-04-19 | 2027-06-27 | 70 | 0%
5 | Regulator permission to start dismantling |  | 2027-08-27 | 2027-08-27 | — | —
6 | Waste route confirmed available |  | 2027-08-27 | 2027-08-27 | — | —
7 | Ancillary plant removal & containment |  | 2027-08-27 | 2028-03-23 | 210 | 0%
7.1 | Asbestos removal & conventional hazard | Contractor | 2027-08-27 | 2027-11-04 | 70 | 0%

## Slide 4
 | clearance |  |  |  |  | 
7.2 | Ventilation & containment tent installation | Contractor | 2027-09-26 | 2027-11-24 | 60 | 0%
7.3 | Redundant plant & pipework de-planting | Dismantling | 2027-11-15 | 2028-02-12 | 90 | 0%
7.4 | Active drains & pond clean-out | Dismantling | 2027-12-05 | 2028-02-22 | 80 | 0%
7.5 | Decontamination of accessible surfaces | Decontamination | 2028-01-04 | 2028-03-23 | 80 | 0%
8 | Ancillary buildings radiologically cleared |  | 2028-03-24 | 2028-03-24 | — | —
9 | Reactor & primary circuit dismantling |  | 2028-02-23 | 2029-03-28 | 400 | 0%
9.1 | Remote handling & cutting equipment trials | Dismantling | 2028-02-23 | 2028-05-02 | 70 | 0%
9.2 | Dose budget allocation per work area | Rad protection | 2028-03-24 | 2028-05-02 | 40 | 0%
9.3 | Primary circuit segmentation & size reduction | Dismantling | 2028-05-03 | 2028-08-20 | 110 | 0%
9.4 | Dose uptake review & shift rotation adjustment | Rad protection | 2028-07-02 | 2028-10-29 | 120 | 0%
9.5 | Reactor internals removal under shielding | Dismantling | 2028-08-21 | 2028-12-18 | 120 | 0%
9.6 | Bioshield & activated concrete removal | Dismantling | 2028-12-19 | 2029-03-18 | 90 | 0%
10 | Reactor building emptied |  | 2029-03-19 | 2029-03-19 | — | —
11 | Waste packaging, consignment & disposal |  | 2028-05-03 | 2029-05-17 | 380 | 0%
11.1 | Waste segregation, assay & characterisation records | Waste | 2028-05-03 | 2028-08-30 | 120 | 0%
11.2 | Intermediate-level waste packaging into containers | Waste | 2028-08-31 | 2029-01-07 | 130 | 0%
11.3 | Low-level waste consignment to disposal facility | Waste | 2028-09-20 | 2029-02-16 | 150 | 0%
11.4 | Interim store loading & container monitoring | Waste | 2029-01-08 | 2029-04-07 | 90 | 0%
11.5 | Free-release material clearance & recycling | Waste | 2029-01-18 | 2029-04-07 | 80 | 0%
12 | All active waste |  | 2029-05-18 | 2029-05-18 | — | —

## Slide 5
 | consigned or stored |  |  |  |  | 
13 | Demolition, remediation & delicensing |  | 2029-03-19 | 2029-12-03 | 260 | 0%
13.1 | Final radiological survey of structures | Characterisation | 2029-03-19 | 2029-05-27 | 70 | 0%
13.2 | Conventional demolition of cleared buildings | Contractor | 2029-05-28 | 2029-08-25 | 90 | 0%
13.3 | Land quality assessment & soil remediation | Environment | 2029-07-17 | 2029-10-14 | 90 | 0%
13.4 | Site end-state survey & records package | Client | 2029-09-25 | 2029-11-13 | 50 | 0%
13.5 | Regulator delicensing decision | Regulator | 2029-11-14 | 2029-12-03 | 20 | 0%
14 | Site delicensed |  | 2029-12-04 | 2029-12-04 | — | —