## Gantt
Nuclear Decommissioning
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 25 | Jan 1 | Jan 8 | Jan 15 | Jan 22 | Jan 29 | Feb 5 | Feb 12 | Feb 19 | Feb 26 | Mar 5 | Mar 12 | Mar 19 | Mar 26 | Apr 2 | Apr 9 | Apr 16 | Apr 23 | Apr 30 | May 7 | May 14 | May 21 | May 28 | Jun 4 | Jun 11 | Jun 18 | Jun 25 | Jul 2 | Jul 9 | Jul 16 | Jul 23 | Jul 30 | Aug 6 | Aug 13 | Aug 20 | Aug 27 | Sep 3 | Sep 10 | Sep 17 | Sep 24 | Oct 1 | Oct 8 | Oct 15 | Oct 22 | Oct 29 | Nov 5 | Nov 12 | Nov 19 | Nov 26 | Dec 3 | Dec 10
1 | Post-operational clean-out & characterisation |  | 2026-08-02 | 2027-03-19 | 230
1.1 | Defuelling & fuel transfer off site | Operations | 2026-08-02 | 2026-11-29 | 120
1.2 | Radiological characterisation survey | Characterisation | 2026-10-01 | 2027-01-18 | 110
1.3 | Legacy waste inventory & material accountancy | Waste | 2026-11-10 | 2027-02-07 | 90
1.4 | Asbestos & hazardous material survey | Characterisation | 2026-11-20 | 2027-01-18 | 60
1.5 | Decommissioning strategy & end-state definition | Client | 2026-12-30 | 2027-03-19 | 80
2 | ◆ Fuel-free status declared |  | 2026-11-30 | 2026-11-30 | [18 empty] | ◆
3 | ◆ Characterisation baseline issued |  | 2027-03-20 | 2027-03-20 | [33 empty] | ◆
4 | Regulatory permissioning & waste route agreement |  | 2027-01-19 | 2027-08-26 | 220
4.1 | Safety case & hazard analysis for dismantling | Safety case | 2027-01-19 | 2027-05-08 | 110
4.2 | Environmental permit variation application | Regulatory | 2027-03-20 | 2027-06-27 | 100
4.3 | Waste acceptance criteria agreed with disposal site | Waste | 2027-03-30 | 2027-06-27 | 90
4.4 | Disposal route capacity & consignment booking | Waste | 2027-05-29 | 2027-08-26 | 90
4.5 | ALARP dose budget & radiological protection plan | Rad protection | 2027-04-19 | 2027-06-27 | 70
5 | ◆ Regulator permission to start dismantling |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
6 | ◆ Waste route confirmed available |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
7 | Ancillary plant removal & containment |  | 2027-08-27 | 2028-03-23 | 210
7.1 | Asbestos removal & conventional hazard clearance | Contractor | 2027-08-27 | 2027-11-04 | 70
7.2 | Ventilation & containment tent installation | Contractor | 2027-09-26 | 2027-11-24 | 60
7.3 | Redundant plant & pipework de-planting | Dismantling | 2027-11-15 | 2028-02-12 | 90
7.4 | Active drains & pond clean-out | Dismantling | 2027-12-05 | 2028-02-22 | 80
7.5 | Decontamination of accessible surfaces | Decontamination | 2028-01-04 | 2028-03-23 | 80
8 | ◆ Ancillary buildings radiologically cleared |  | 2028-03-24 | 2028-03-24 | [86 empty] | ◆
9 | Reactor & primary circuit dismantling |  | 2028-02-23 | 2029-03-28 | 400
9.1 | Remote handling & cutting equipment trials | Dismantling | 2028-02-23 | 2028-05-02 | 70
9.2 | Dose budget allocation per work area | Rad protection | 2028-03-24 | 2028-05-02 | 40
9.3 | Primary circuit segmentation & size reduction | Dismantling | 2028-05-03 | 2028-08-20 | 110
9.4 | Dose uptake review & shift rotation adjustment | Rad protection | 2028-07-02 | 2028-10-29 | 120
9.5 | Reactor internals removal under shielding | Dismantling | 2028-08-21 | 2028-12-18 | 120
9.6 | Bioshield & activated concrete removal | Dismantling | 2028-12-19 | 2029-03-18 | 90
10 | ◆ Reactor building emptied |  | 2029-03-19 | 2029-03-19 | [138 empty] | ◆
11 | Waste packaging, consignment & disposal |  | 2028-05-03 | 2029-05-17 | 380
11.1 | Waste segregation, assay & characterisation records | Waste | 2028-05-03 | 2028-08-30 | 120
11.2 | Intermediate-level waste packaging into containers | Waste | 2028-08-31 | 2029-01-07 | 130
11.3 | Low-level waste consignment to disposal facility | Waste | 2028-09-20 | 2029-02-16 | 150
11.4 | Interim store loading & container monitoring | Waste | 2029-01-08 | 2029-04-07 | 90
11.5 | Free-release material clearance & recycling | Waste | 2029-01-18 | 2029-04-07 | 80
12 | ◆ All active waste consigned or stored |  | 2029-05-18 | 2029-05-18 | [146 empty] | ◆
13 | Demolition, remediation & delicensing |  | 2029-03-19 | 2029-12-03 | 260
13.1 | Final radiological survey of structures | Characterisation | 2029-03-19 | 2029-05-27 | 70
13.2 | Conventional demolition of cleared buildings | Contractor | 2029-05-28 | 2029-08-25 | 90
13.3 | Land quality assessment & soil remediation | Environment | 2029-07-17 | 2029-10-14 | 90
13.4 | Site end-state survey & records package | Client | 2029-09-25 | 2029-11-13 | 50
13.5 | Regulator delicensing decision | Regulator | 2029-11-14 | 2029-12-03 | 20
14 | ◆ Site delicensed |  | 2029-12-04 | 2029-12-04 | [175 empty] | ◆