## Slide 1
Office Relocation Project Plan
Free Gantt chart template · gantts.app

## Slide 2
Office Relocation Project Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Requirements & search
Headcount & space requirements
Budget & business case
Site search & shortlist
Lease & legal
Heads of terms
Due diligence & survey
Lease negotiation & signature
◆ Lease signed
◆ Notice served on old lease
Design & fit-out
Test fit & space plan
Detailed design & landlord approval
Fit-out construction
Furniture delivery & install
Snagging
IT & connectivity
◆ Circuit orders placed
Circuit provisioning
Comms room & cabling
AV & meeting rooms
Network pilot day
Move planning & communications
Move vendor selection
Staff communications plan
Seat allocation & floor plans
Crate distribution & packing
Move & decommission
Move weekend
First-day floor support
Old site clearance
Dilapidations settlement
◆ Old site handed back
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Requirements & search |  | 2026-08-02 | 2026-10-15 | 75 | 100%
1.1 | Headcount & space requirements | Facilities | 2026-08-02 | 2026-08-26 | 25 | 100%
1.2 | Budget & business case | Finance | 2026-08-22 | 2026-09-15 | 25 | 100%
1.3 | Site search & shortlist | Agent | 2026-09-01 | 2026-10-15 | 45 | 100%
2 | Lease & legal |  | 2026-10-16 | 2026-12-14 | 60 | 100%
2.1 | Heads of terms | Agent | 2026-10-16 | 2026-11-04 | 20 | 100%
2.2 | Due diligence & survey | Surveyor | 2026-10-31 | 2026-11-29 | 30 | 100%
2.3 | Lease negotiation & signature | Legal | 2026-11-15 | 2026-12-14 | 30 | 100%
3 | Lease signed |  | 2026-12-15 | 2026-12-15 | — | —
4 | Notice served on old lease |  | 2026-12-20 | 2026-12-20 | — | —
5 | Design & fit-out |  | 2026-11-30 | 2027-04-28 | 150 | 40%
5.1 | Test fit & space plan | Designer | 2026-11-30 | 2026-12-29 | 30 | 100%
5.2 | Detailed design & landlord approval | Designer | 2026-12-30 | 2027-02-07 | 40 | 70%
5.3 | Fit-out construction | Contractor | 2027-02-08 | 2027-04-13 | 65 | 10%
5.4 | Furniture delivery & install | Facilities | 2027-03-30 | 2027-04-23 | 25 | 0%
5.5 | Snagging | Contractor | 2027-04-21 | 2027-04-28 | 8 | 0%
6 | IT & connectivity |  | 2026-12-15 | 2027-04-23 | 130 | 30%
7 | Circuit orders placed |  | 2026-12-15 | 2026-12-15 | — | —
7.1 | Circuit provisioning | Provider | 2026-12-15 | 2027-04-03 | 110 | 30%
7.2 | Comms room & cabling | IT | 2027-02-18 | 2027-03-29 | 40 | 0%
7.3 | AV & meeting rooms | IT | 2027-03-25 | 2027-04-23 | 30 | 0%

## Slide 4
7.4 | Network pilot day | IT | 2027-04-24 | 2027-04-26 | 3 | 0%
8 | Move planning & communications |  | 2027-01-29 | 2027-05-03 | 95 | 20%
8.1 | Move vendor selection | Facilities | 2027-01-29 | 2027-02-27 | 30 | 60%
8.2 | Staff communications plan | Comms | 2027-02-18 | 2027-04-18 | 60 | 20%
8.3 | Seat allocation & floor plans | Facilities | 2027-03-20 | 2027-04-18 | 30 | 0%
8.4 | Crate distribution & packing | All staff | 2027-04-24 | 2027-05-03 | 10 | 0%
9 | Move & decommission |  | 2027-05-04 | 2027-07-07 | 65 | 0%
9.1 | Move weekend | Movers | 2027-05-04 | 2027-05-06 | 3 | 0%
9.2 | First-day floor support | IT & facilities | 2027-05-07 | 2027-05-11 | 5 | 0%
9.3 | Old site clearance | Facilities | 2027-05-09 | 2027-05-28 | 20 | 0%
9.4 | Dilapidations settlement | Surveyor | 2027-05-19 | 2027-07-07 | 50 | 0%
10 | Old site handed back |  | 2027-07-08 | 2027-07-08 | — | —