## Gantt
Office Relocation Project Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12
1 | Requirements & search |  | 2026-08-02 | 2026-10-15 | 75
1.1 | Headcount & space requirements | Facilities | 2026-08-02 | 2026-08-26 | 25
1.2 | Budget & business case | Finance | 2026-08-22 | 2026-09-15 | 25
1.3 | Site search & shortlist | Agent | 2026-09-01 | 2026-10-15 | 45
2 | Lease & legal |  | 2026-10-16 | 2026-12-14 | 60
2.1 | Heads of terms | Agent | 2026-10-16 | 2026-11-04 | 20
2.2 | Due diligence & survey | Surveyor | 2026-10-31 | 2026-11-29 | 30
2.3 | Lease negotiation & signature | Legal | 2026-11-15 | 2026-12-14 | 30
3 | ◆ Lease signed |  | 2026-12-15 | 2026-12-15 | [20 empty] | ◆
4 | ◆ Notice served on old lease |  | 2026-12-20 | 2026-12-20 | [21 empty] | ◆
5 | Design & fit-out |  | 2026-11-30 | 2027-04-28 | 150
5.1 | Test fit & space plan | Designer | 2026-11-30 | 2026-12-29 | 30
5.2 | Detailed design & landlord approval | Designer | 2026-12-30 | 2027-02-07 | 40
5.3 | Fit-out construction | Contractor | 2027-02-08 | 2027-04-13 | 65
5.4 | Furniture delivery & install | Facilities | 2027-03-30 | 2027-04-23 | 25
5.5 | Snagging | Contractor | 2027-04-21 | 2027-04-28 | 8
6 | IT & connectivity |  | 2026-12-15 | 2027-04-23 | 130
7 | ◆ Circuit orders placed |  | 2026-12-15 | 2026-12-15 | [20 empty] | ◆
7.1 | Circuit provisioning | Provider | 2026-12-15 | 2027-04-03 | 110
7.2 | Comms room & cabling | IT | 2027-02-18 | 2027-03-29 | 40
7.3 | AV & meeting rooms | IT | 2027-03-25 | 2027-04-23 | 30
7.4 | Network pilot day | IT | 2027-04-24 | 2027-04-26 | 3
8 | Move planning & communications |  | 2027-01-29 | 2027-05-03 | 95
8.1 | Move vendor selection | Facilities | 2027-01-29 | 2027-02-27 | 30
8.2 | Staff communications plan | Comms | 2027-02-18 | 2027-04-18 | 60
8.3 | Seat allocation & floor plans | Facilities | 2027-03-20 | 2027-04-18 | 30
8.4 | Crate distribution & packing | All staff | 2027-04-24 | 2027-05-03 | 10
9 | Move & decommission |  | 2027-05-04 | 2027-07-07 | 65
9.1 | Move weekend | Movers | 2027-05-04 | 2027-05-06 | 3
9.2 | First-day floor support | IT & facilities | 2027-05-07 | 2027-05-11 | 5
9.3 | Old site clearance | Facilities | 2027-05-09 | 2027-05-28 | 20
9.4 | Dilapidations settlement | Surveyor | 2027-05-19 | 2027-07-07 | 50
10 | ◆ Old site handed back |  | 2027-07-08 | 2027-07-08 | [49 empty] | ◆