## Slide 1
Oil & Gas Pipeline Construction
Free Gantt chart template · gantts.app

## Slide 2
Oil & Gas Pipeline Construction
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Route selection, permits & right-of-way
Route survey & alternatives study
Environmental & social impact assessment
Regulatory permit application & hearings
Landowner negotiation & easement acquisition
Archaeological & heritage clearance survey
◆ Right-of-way secured
◆ Construction permit issued
Pipe procurement & logistics
Line pipe mill order & production
Mill coating & weld-end preparation
Rail & truck haul to stockpile yards
◆ Pipe on the right-of-way
Pre-construction & environmental windows
Environmental window & nesting season mapping
Access road & bridge upgrades
Right-of-way clearing & grading
Topsoil stripping & erosion control
Contractor mobilisation & spread setup
◆ Spread ready to string pipe
Mainline construction spread
Stringing pipe along the trench line
Trench excavation
Field bending & line-up
Mainline welding
Radiographic & ultrasonic weld inspection
Field joint coating & holiday detection
Lower-in & padding
Backfill & rough grade restoration
◆ Mainline welding complete
Cathodic protection & test station installation
Crossings & special works
Horizontal directional drill — major river crossing
Watercourse crossings within in-stream window
Road, rail & foreign line crossings
Pump & compressor station construction
Block valve site construction
◆ In-stream work window closed
Hydrotest, tie-in & commissioning
Section isolation & test manifold installation
Hydrostatic test fill & pressurisation
Test hold, leak assessment & repairs
◆ Hydrotest passed
Dewatering, cleaning & drying pigs
Golden weld tie-ins
SCADA, leak detection & control room integration
Nitrogen purge & introduction of product
Final reclamation & landowner sign-off
◆ Pipeline in service
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Route selection, permits & right-of-way |  | 2026-08-02 | 2027-03-09 | 220 | 100%
1.1 | Route survey & alternatives study | Engineering | 2026-08-02 | 2026-09-20 | 50 | 100%
1.2 | Environmental & social impact assessment | Environment | 2026-09-11 | 2026-12-29 | 110 | 100%
1.3 | Regulatory permit application & hearings | Regulatory | 2026-10-31 | 2027-02-27 | 120 | 90%
1.4 | Landowner negotiation & easement acquisition | Land | 2026-10-01 | 2027-02-27 | 150 | 85%
1.5 | Archaeological & heritage clearance survey | Environment | 2026-11-30 | 2027-01-28 | 60 | 80%
2 | Right-of-way secured |  | 2027-02-28 | 2027-02-28 | — | —
3 | Construction permit issued |  | 2027-03-05 | 2027-03-05 | — | —
4 | Pipe procurement & logistics |  | 2026-10-01 | 2027-05-18 | 230 | 60%
4.1 | Line pipe mill order & production | Procurement | 2026-10-01 | 2027-02-27 | 150 | 90%
4.2 | Mill coating & weld-end preparation | Procurement | 2027-01-29 | 2027-04-08 | 70 | 60%
4.3 | Rail & truck haul to stockpile yards | Logistics | 2027-03-25 | 2027-05-18 | 55 | 20%
5 | Pipe on the right-of-way |  | 2027-05-19 | 2027-05-19 | — | —
6 | Pre-construction & environmental windows |  | 2027-02-18 | 2027-06-27 | 130 | 20%
6.1 | Environmental window & nesting season mapping | Environment | 2027-02-18 | 2027-03-19 | 30 | 100%
6.2 | Access road & bridge upgrades | Civils | 2027-03-20 | 2027-05-08 | 50 | 40%
6.3 | Right-of-way clearing & grading | Civils | 2027-04-09 | 2027-06-17 | 70 | 20%
6.4 | Topsoil stripping & erosion control | Civils | 2027-05-09 | 2027-06-27 | 50 | 0%
6.5 | Contractor mobilisation & spread setup | Contractor | 2027-05-29 | 2027-06-22 | 25 | 0%
7 | Spread ready to string pipe |  | 2027-06-28 | 2027-06-28 | — | —
8 | Mainline construction |  | 2027-06-28 | 2028-01-03 | 190 | 0%

## Slide 4
 | spread |  |  |  |  | 
8.1 | Stringing pipe along the trench line | Spread | 2027-06-28 | 2027-08-26 | 60 | 0%
8.2 | Trench excavation | Spread | 2027-07-08 | 2027-09-15 | 70 | 0%
8.3 | Field bending & line-up | Spread | 2027-07-18 | 2027-09-20 | 65 | 0%
8.4 | Mainline welding | Welding | 2027-07-28 | 2027-10-25 | 90 | 0%
8.5 | Radiographic & ultrasonic weld inspection | NDT | 2027-08-07 | 2027-11-04 | 90 | 0%
8.6 | Field joint coating & holiday detection | Coating | 2027-08-22 | 2027-11-14 | 85 | 0%
8.7 | Lower-in & padding | Spread | 2027-09-06 | 2027-11-24 | 80 | 0%
8.8 | Backfill & rough grade restoration | Spread | 2027-09-26 | 2027-12-14 | 80 | 0%
9 | Mainline welding complete |  | 2027-10-26 | 2027-10-26 | — | —
9.1 | Cathodic protection & test station installation | Corrosion | 2027-12-15 | 2028-01-28 | 45 | 0%
10 | Crossings & special works |  | 2027-08-17 | 2028-02-12 | 180 | 0%
10.1 | Horizontal directional drill — major river crossing | HDD | 2027-08-17 | 2027-10-15 | 60 | 0%
10.2 | Watercourse crossings within in-stream window | Crossings | 2027-10-16 | 2027-11-29 | 45 | 0%
10.3 | Road, rail & foreign line crossings | Crossings | 2027-09-06 | 2027-12-04 | 90 | 0%
10.4 | Pump & compressor station construction | Stations | 2027-08-17 | 2028-01-23 | 160 | 0%
10.5 | Block valve site construction | Civils | 2027-12-15 | 2028-02-12 | 60 | 0%
11 | In-stream work window closed |  | 2027-11-30 | 2027-11-30 | — | —
12 | Hydrotest, tie-in & commissioning |  | 2028-01-04 | 2028-07-11 | 190 | 0%
12.1 | Section isolation & test manifold installation | Commissioning | 2028-01-29 | 2028-02-27 | 30 | 0%
12.2 | Hydrostatic test fill & pressurisation | Commissioning | 2028-02-28 | 2028-04-02 | 35 | 0%
12.3 | Test hold, leak assessment & repairs | Commissioning | 2028-04-03 | 2028-04-27 | 25 | 0%

## Slide 5
13 | Hydrotest passed |  | 2028-04-28 | 2028-04-28 | — | —
13.1 | Dewatering, cleaning & drying pigs | Commissioning | 2028-04-28 | 2028-05-27 | 30 | 0%
13.2 | Golden weld tie-ins | Welding | 2028-05-28 | 2028-06-21 | 25 | 0%
13.3 | SCADA, leak detection & control room integration | Controls | 2028-03-24 | 2028-06-01 | 70 | 0%
13.4 | Nitrogen purge & introduction of product | Commissioning | 2028-06-22 | 2028-07-11 | 20 | 0%
13.5 | Final reclamation & landowner sign-off | Environment | 2028-06-22 | 2028-08-20 | 60 | 0%
14 | Pipeline in service |  | 2028-07-12 | 2028-07-12 | — | —