## Gantt
Oil & Gas Pipeline Construction
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21
1 | Route selection, permits & right-of-way |  | 2026-08-02 | 2027-03-09 | 220
1.1 | Route survey & alternatives study | Engineering | 2026-08-02 | 2026-09-20 | 50
1.2 | Environmental & social impact assessment | Environment | 2026-09-11 | 2026-12-29 | 110
1.3 | Regulatory permit application & hearings | Regulatory | 2026-10-31 | 2027-02-27 | 120
1.4 | Landowner negotiation & easement acquisition | Land | 2026-10-01 | 2027-02-27 | 150
1.5 | Archaeological & heritage clearance survey | Environment | 2026-11-30 | 2027-01-28 | 60
2 | ◆ Right-of-way secured |  | 2027-02-28 | 2027-02-28 | [31 empty] | ◆
3 | ◆ Construction permit issued |  | 2027-03-05 | 2027-03-05 | [31 empty] | ◆
4 | Pipe procurement & logistics |  | 2026-10-01 | 2027-05-18 | 230
4.1 | Line pipe mill order & production | Procurement | 2026-10-01 | 2027-02-27 | 150
4.2 | Mill coating & weld-end preparation | Procurement | 2027-01-29 | 2027-04-08 | 70
4.3 | Rail & truck haul to stockpile yards | Logistics | 2027-03-25 | 2027-05-18 | 55
5 | ◆ Pipe on the right-of-way |  | 2027-05-19 | 2027-05-19 | [42 empty] | ◆
6 | Pre-construction & environmental windows |  | 2027-02-18 | 2027-06-27 | 130
6.1 | Environmental window & nesting season mapping | Environment | 2027-02-18 | 2027-03-19 | 30
6.2 | Access road & bridge upgrades | Civils | 2027-03-20 | 2027-05-08 | 50
6.3 | Right-of-way clearing & grading | Civils | 2027-04-09 | 2027-06-17 | 70
6.4 | Topsoil stripping & erosion control | Civils | 2027-05-09 | 2027-06-27 | 50
6.5 | Contractor mobilisation & spread setup | Contractor | 2027-05-29 | 2027-06-22 | 25
7 | ◆ Spread ready to string pipe |  | 2027-06-28 | 2027-06-28 | [48 empty] | ◆
8 | Mainline construction spread |  | 2027-06-28 | 2028-01-03 | 190
8.1 | Stringing pipe along the trench line | Spread | 2027-06-28 | 2027-08-26 | 60
8.2 | Trench excavation | Spread | 2027-07-08 | 2027-09-15 | 70
8.3 | Field bending & line-up | Spread | 2027-07-18 | 2027-09-20 | 65
8.4 | Mainline welding | Welding | 2027-07-28 | 2027-10-25 | 90
8.5 | Radiographic & ultrasonic weld inspection | NDT | 2027-08-07 | 2027-11-04 | 90
8.6 | Field joint coating & holiday detection | Coating | 2027-08-22 | 2027-11-14 | 85
8.7 | Lower-in & padding | Spread | 2027-09-06 | 2027-11-24 | 80
8.8 | Backfill & rough grade restoration | Spread | 2027-09-26 | 2027-12-14 | 80
9 | ◆ Mainline welding complete |  | 2027-10-26 | 2027-10-26 | [65 empty] | ◆
9.1 | Cathodic protection & test station installation | Corrosion | 2027-12-15 | 2028-01-28 | 45
10 | Crossings & special works |  | 2027-08-17 | 2028-02-12 | 180
10.1 | Horizontal directional drill — major river crossing | HDD | 2027-08-17 | 2027-10-15 | 60
10.2 | Watercourse crossings within in-stream window | Crossings | 2027-10-16 | 2027-11-29 | 45
10.3 | Road, rail & foreign line crossings | Crossings | 2027-09-06 | 2027-12-04 | 90
10.4 | Pump & compressor station construction | Stations | 2027-08-17 | 2028-01-23 | 160
10.5 | Block valve site construction | Civils | 2027-12-15 | 2028-02-12 | 60
11 | ◆ In-stream work window closed |  | 2027-11-30 | 2027-11-30 | [70 empty] | ◆
12 | Hydrotest, tie-in & commissioning |  | 2028-01-04 | 2028-07-11 | 190
12.1 | Section isolation & test manifold installation | Commissioning | 2028-01-29 | 2028-02-27 | 30
12.2 | Hydrostatic test fill & pressurisation | Commissioning | 2028-02-28 | 2028-04-02 | 35
12.3 | Test hold, leak assessment & repairs | Commissioning | 2028-04-03 | 2028-04-27 | 25
13 | ◆ Hydrotest passed |  | 2028-04-28 | 2028-04-28 | [91 empty] | ◆
13.1 | Dewatering, cleaning & drying pigs | Commissioning | 2028-04-28 | 2028-05-27 | 30
13.2 | Golden weld tie-ins | Welding | 2028-05-28 | 2028-06-21 | 25
13.3 | SCADA, leak detection & control room integration | Controls | 2028-03-24 | 2028-06-01 | 70
13.4 | Nitrogen purge & introduction of product | Commissioning | 2028-06-22 | 2028-07-11 | 20
13.5 | Final reclamation & landowner sign-off | Environment | 2028-06-22 | 2028-08-20 | 60
14 | ◆ Pipeline in service |  | 2028-07-12 | 2028-07-12 | [102 empty] | ◆