## Slide 1
OKR Quarterly Planning
Free Gantt chart template · gantts.app

## Slide 2
OKR Quarterly Planning
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Company direction
Strategy & annual goal review
Draft company objectives
Publish drafting guidance
◆ Company OKRs drafted
Closing the previous quarter
Collect final key result data
Team self-scoring
Cross-team calibration
Scored results readout
◆ Previous quarter scored
Team drafting
Team drafting sessions
Write first-draft OKRs
◆ Drafts submitted
Alignment
Cross-team dependency review
Capacity & conflict negotiation
◆ Alignment complete
Commitment & kickoff
Leadership review & final edits
Publish in tracking tool
All-hands kickoff
◆ OKRs committed
In-quarter execution
Weekly confidence updates
Mid-quarter check-in
Adjust or drop objectives
Quarter-end scoring
Retrospective on process
◆ Next cycle drafting begins
◆ Quarter closed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Company direction |  | 2026-08-02 | 2026-08-15 | 14 | 100%
1.1 | Strategy & annual goal review | Leadership | 2026-08-02 | 2026-08-06 | 5 | 100%
1.2 | Draft company objectives | Leadership | 2026-08-06 | 2026-08-11 | 6 | 100%
1.3 | Publish drafting guidance | Chief of staff | 2026-08-12 | 2026-08-15 | 4 | 100%
2 | Company OKRs drafted |  | 2026-08-16 | 2026-08-16 | — | —
3 | Closing the previous quarter |  | 2026-08-02 | 2026-08-22 | 21 | 90%
3.1 | Collect final key result data | OKR owners | 2026-08-02 | 2026-08-08 | 7 | 100%
3.2 | Team self-scoring | Team leads | 2026-08-08 | 2026-08-13 | 6 | 100%
3.3 | Cross-team calibration | Leadership | 2026-08-14 | 2026-08-18 | 5 | 80%
3.4 | Scored results readout | Chief of staff | 2026-08-19 | 2026-08-22 | 4 | 40%
4 | Previous quarter scored |  | 2026-08-23 | 2026-08-23 | — | —
5 | Team drafting |  | 2026-08-16 | 2026-08-29 | 14 | 30%
5.1 | Team drafting sessions | Team leads | 2026-08-16 | 2026-08-22 | 7 | 50%
5.2 | Write first-draft OKRs | Team leads | 2026-08-21 | 2026-08-27 | 7 | 20%
6 | Drafts submitted |  | 2026-08-30 | 2026-08-30 | — | —
7 | Alignment |  | 2026-08-30 | 2026-09-08 | 10 | 0%
7.1 | Cross-team dependency review | Team leads | 2026-08-30 | 2026-09-03 | 5 | 0%
7.2 | Capacity & conflict negotiation | Team leads | 2026-09-02 | 2026-09-06 | 5 | 0%
8 | Alignment complete |  | 2026-09-09 | 2026-09-09 | — | —
9 | Commitment & kickoff |  | 2026-09-09 | 2026-09-18 | 10 | 0%
9.1 | Leadership review & final edits | Leadership | 2026-09-09 | 2026-09-13 | 5 | 0%

## Slide 4
9.2 | Publish in tracking tool | Chief of staff | 2026-09-14 | 2026-09-16 | 3 | 0%
9.3 | All-hands kickoff | Leadership | 2026-09-17 | 2026-09-17 | 1 | 0%
10 | OKRs committed |  | 2026-09-18 | 2026-09-18 | — | —
11 | In-quarter execution |  | 2026-09-18 | 2026-12-22 | 96 | 0%
11.1 | Weekly confidence updates | OKR owners | 2026-09-18 | 2026-12-16 | 90 | 0%
11.2 | Mid-quarter check-in | Leadership | 2026-11-02 | 2026-11-04 | 3 | 0%
11.3 | Adjust or drop objectives | Team leads | 2026-11-05 | 2026-11-09 | 5 | 0%
11.4 | Quarter-end scoring | OKR owners | 2026-12-10 | 2026-12-17 | 8 | 0%
11.5 | Retrospective on process | All | 2026-12-16 | 2026-12-20 | 5 | 0%
12 | Next cycle drafting begins |  | 2026-12-10 | 2026-12-10 | — | —
13 | Quarter closed |  | 2026-12-23 | 2026-12-23 | — | —