## Slide 1
Online Course Creation Plan
Free Gantt chart template · gantts.app

## Slide 2
Online Course Creation Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Plan & validate
Define audience & outcome
Validate topic (survey / pre-sell)
◆ Topic validated
Outline & script
Curriculum & module outline
Write lesson scripts & slides
◆ Scripts ready
Record & produce
Set up recording (audio, lighting)
Record video lessons
Record screencasts & demos
◆ Filming wrapped
Edit & assemble
Edit video & audio
Build workbooks & quizzes
Add captions & thumbnails
◆ Course assembled
Platform & sales page
Choose platform & upload
Set pricing & checkout
Build sales page
◆ Store live
Launch & promote
Warm up email list
Pre-launch content & webinar
Cart open, launch
Post-launch & gather reviews
◆ Launch complete
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Plan & validate |  | 2026-08-02 | 2026-08-15 | 14 | 100%
1.1 | Define audience & outcome | Instructor | 2026-08-02 | 2026-08-06 | 5 | 100%
1.2 | Validate topic (survey / pre-sell) | Instructor | 2026-08-07 | 2026-08-15 | 9 | 100%
2 | Topic validated |  | 2026-08-16 | 2026-08-16 | , | ,
3 | Outline & script |  | 2026-08-16 | 2026-09-05 | 21 | 70%
3.1 | Curriculum & module outline | Instructor | 2026-08-16 | 2026-08-22 | 7 | 100%
3.2 | Write lesson scripts & slides | Instructor | 2026-08-23 | 2026-09-05 | 14 | 55%
4 | Scripts ready |  | 2026-09-06 | 2026-09-06 | , | ,
5 | Record & produce |  | 2026-09-06 | 2026-09-26 | 21 | 15%
5.1 | Set up recording (audio, lighting) | Producer | 2026-09-06 | 2026-09-08 | 3 | 40%
5.2 | Record video lessons | Instructor | 2026-09-09 | 2026-09-23 | 15 | 10%
5.3 | Record screencasts & demos | Instructor | 2026-09-21 | 2026-09-26 | 6 | 0%
6 | Filming wrapped |  | 2026-09-27 | 2026-09-27 | , | ,
7 | Edit & assemble |  | 2026-09-27 | 2026-10-17 | 21 | 0%
7.1 | Edit video & audio | Editor | 2026-09-27 | 2026-10-08 | 12 | 0%
7.2 | Build workbooks & quizzes | Instructor | 2026-09-27 | 2026-10-06 | 10 | 0%
7.3 | Add captions & thumbnails | Editor | 2026-10-09 | 2026-10-14 | 6 | 0%
8 | Course assembled |  | 2026-10-18 | 2026-10-18 | , | ,
9 | Platform & sales page |  | 2026-10-11 | 2026-10-28 | 18 | 0%
9.1 | Choose platform & upload | Producer | 2026-10-11 | 2026-10-17 | 7 | 0%
9.2 | Set pricing & checkout | Instructor | 2026-10-18 | 2026-10-21 | 4 | 0%

## Slide 4
9.3 | Build sales page | Marketing | 2026-10-18 | 2026-10-28 | 11 | 0%
10 | Store live |  | 2026-10-29 | 2026-10-29 | , | ,
11 | Launch & promote |  | 2026-10-25 | 2026-11-19 | 26 | 0%
11.1 | Warm up email list | Marketing | 2026-10-25 | 2026-11-01 | 8 | 0%
11.2 | Pre-launch content & webinar | Marketing | 2026-11-02 | 2026-11-06 | 5 | 0%
11.3 | Cart open, launch | Instructor | 2026-11-07 | 2026-11-13 | 7 | 0%
11.4 | Post-launch & gather reviews | Marketing | 2026-11-14 | 2026-11-19 | 6 | 0%
12 | Launch complete |  | 2026-11-20 | 2026-11-20 | , | ,