## Gantt
Online Course Creation Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23
1 | Plan & validate |  | 2026-08-02 | 2026-08-15 | 14
1.1 | Define audience & outcome | Instructor | 2026-08-02 | 2026-08-06 | 5
1.2 | Validate topic (survey / pre-sell) | Instructor | 2026-08-07 | 2026-08-15 | 9
2 | ◆ Topic validated |  | 2026-08-16 | 2026-08-16 |  |  |  | ◆
3 | Outline & script |  | 2026-08-16 | 2026-09-05 | 21
3.1 | Curriculum & module outline | Instructor | 2026-08-16 | 2026-08-22 | 7
3.2 | Write lesson scripts & slides | Instructor | 2026-08-23 | 2026-09-05 | 14
4 | ◆ Scripts ready |  | 2026-09-06 | 2026-09-06 | [6 empty] | ◆
5 | Record & produce |  | 2026-09-06 | 2026-09-26 | 21
5.1 | Set up recording (audio, lighting) | Producer | 2026-09-06 | 2026-09-08 | 3
5.2 | Record video lessons | Instructor | 2026-09-09 | 2026-09-23 | 15
5.3 | Record screencasts & demos | Instructor | 2026-09-21 | 2026-09-26 | 6
6 | ◆ Filming wrapped |  | 2026-09-27 | 2026-09-27 | [9 empty] | ◆
7 | Edit & assemble |  | 2026-09-27 | 2026-10-17 | 21
7.1 | Edit video & audio | Editor | 2026-09-27 | 2026-10-08 | 12
7.2 | Build workbooks & quizzes | Instructor | 2026-09-27 | 2026-10-06 | 10
7.3 | Add captions & thumbnails | Editor | 2026-10-09 | 2026-10-14 | 6
8 | ◆ Course assembled |  | 2026-10-18 | 2026-10-18 | [12 empty] | ◆
9 | Platform & sales page |  | 2026-10-11 | 2026-10-28 | 18
9.1 | Choose platform & upload | Producer | 2026-10-11 | 2026-10-17 | 7
9.2 | Set pricing & checkout | Instructor | 2026-10-18 | 2026-10-21 | 4
9.3 | Build sales page | Marketing | 2026-10-18 | 2026-10-28 | 11
10 | ◆ Store live |  | 2026-10-29 | 2026-10-29 | [13 empty] | ◆
11 | Launch & promote |  | 2026-10-25 | 2026-11-19 | 26
11.1 | Warm up email list | Marketing | 2026-10-25 | 2026-11-01 | 8
11.2 | Pre-launch content & webinar | Marketing | 2026-11-02 | 2026-11-06 | 5
11.3 | Cart open, launch | Instructor | 2026-11-07 | 2026-11-13 | 7
11.4 | Post-launch & gather reviews | Marketing | 2026-11-14 | 2026-11-19 | 6
12 | ◆ Launch complete |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆