## Slide 1
Performance Review Cycle
Free Gantt chart template · gantts.app

## Slide 2
Performance Review Cycle
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Plan & set up
Define cycle scope & timeline
Update competencies & rating scale
Configure the review tool
Communicate the cycle to the org
Train managers
◆ Cycle framework ready
Goals & self-review
Confirm goals under review
Employee self-assessments
Gather 360 / peer feedback
Collect performance data
◆ Self-reviews in
Manager reviews
Managers write reviews
Draft ratings
Manager one-up review
◆ Draft ratings ready
Calibration
Prepare calibration data
Calibration sessions
Finalize ratings
Comp & promotion decisions
◆ Ratings finalized
Delivery
Prepare review packets
Deliver reviews in 1:1s
◆ Reviews delivered
Development & close
Set next-cycle goals
Agree development plans
Gather feedback on the process
Close the cycle & report
◆ Cycle closed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Plan & set up |  | 2026-08-02 | 2026-08-15 | 14 | 100%
1.1 | Define cycle scope & timeline | HR | 2026-08-02 | 2026-08-05 | 4 | 100%
1.2 | Update competencies & rating scale | HR | 2026-08-05 | 2026-08-09 | 5 | 80%
1.3 | Configure the review tool | HR | 2026-08-07 | 2026-08-11 | 5 | 60%
1.4 | Communicate the cycle to the org | HR | 2026-08-10 | 2026-08-13 | 4 | 40%
1.5 | Train managers | HR | 2026-08-12 | 2026-08-15 | 4 | 30%
2 | Cycle framework ready |  | 2026-08-16 | 2026-08-16 | , | ,
3 | Goals & self-review |  | 2026-08-16 | 2026-08-29 | 14 | 0%
3.1 | Confirm goals under review | Employee | 2026-08-16 | 2026-08-20 | 5 | 0%
3.2 | Employee self-assessments | Employee | 2026-08-18 | 2026-08-27 | 10 | 0%
3.3 | Gather 360 / peer feedback | Employee | 2026-08-20 | 2026-08-29 | 10 | 0%
3.4 | Collect performance data | Manager | 2026-08-20 | 2026-08-27 | 8 | 0%
4 | Self-reviews in |  | 2026-08-30 | 2026-08-30 | , | ,
5 | Manager reviews |  | 2026-08-30 | 2026-09-12 | 14 | 0%
5.1 | Managers write reviews | Manager | 2026-08-30 | 2026-09-10 | 12 | 0%
5.2 | Draft ratings | Manager | 2026-09-03 | 2026-09-10 | 8 | 0%
5.3 | Manager one-up review | Manager | 2026-09-09 | 2026-09-12 | 4 | 0%
6 | Draft ratings ready |  | 2026-09-13 | 2026-09-13 | , | ,
7 | Calibration |  | 2026-09-13 | 2026-09-24 | 12 | 0%
7.1 | Prepare calibration data | HR | 2026-09-13 | 2026-09-15 | 3 | 0%
7.2 | Calibration sessions | Leadership | 2026-09-16 | 2026-09-20 | 5 | 0%

## Slide 4
7.3 | Finalize ratings | HR | 2026-09-20 | 2026-09-22 | 3 | 0%
7.4 | Comp & promotion decisions | Leadership | 2026-09-20 | 2026-09-24 | 5 | 0%
8 | Ratings finalized |  | 2026-09-25 | 2026-09-25 | , | ,
9 | Delivery |  | 2026-09-25 | 2026-10-01 | 7 | 0%
9.1 | Prepare review packets | HR | 2026-09-25 | 2026-09-26 | 2 | 0%
9.2 | Deliver reviews in 1:1s | Manager | 2026-09-27 | 2026-10-01 | 5 | 0%
10 | Reviews delivered |  | 2026-10-02 | 2026-10-02 | , | ,
11 | Development & close |  | 2026-10-02 | 2026-10-11 | 10 | 0%
11.1 | Set next-cycle goals | Employee | 2026-10-02 | 2026-10-06 | 5 | 0%
11.2 | Agree development plans | Manager | 2026-10-02 | 2026-10-07 | 6 | 0%
11.3 | Gather feedback on the process | HR | 2026-10-04 | 2026-10-07 | 4 | 0%
11.4 | Close the cycle & report | HR | 2026-10-07 | 2026-10-09 | 3 | 0%
12 | Cycle closed |  | 2026-10-10 | 2026-10-10 | , | ,