## Gantt
Performance Review Cycle
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12
1 | Plan & set up |  | 2026-08-02 | 2026-08-15 | 14
1.1 | Define cycle scope & timeline | HR | 2026-08-02 | 2026-08-05 | 4
1.2 | Update competencies & rating scale | HR | 2026-08-05 | 2026-08-09 | 5
1.3 | Configure the review tool | HR | 2026-08-07 | 2026-08-11 | 5
1.4 | Communicate the cycle to the org | HR | 2026-08-10 | 2026-08-13 | 4
1.5 | Train managers | HR | 2026-08-12 | 2026-08-15 | 4
2 | ◆ Cycle framework ready |  | 2026-08-16 | 2026-08-16 |  |  |  | ◆
3 | Goals & self-review |  | 2026-08-16 | 2026-08-29 | 14
3.1 | Confirm goals under review | Employee | 2026-08-16 | 2026-08-20 | 5
3.2 | Employee self-assessments | Employee | 2026-08-18 | 2026-08-27 | 10
3.3 | Gather 360 / peer feedback | Employee | 2026-08-20 | 2026-08-29 | 10
3.4 | Collect performance data | Manager | 2026-08-20 | 2026-08-27 | 8
4 | ◆ Self-reviews in |  | 2026-08-30 | 2026-08-30 | [5 empty] | ◆
5 | Manager reviews |  | 2026-08-30 | 2026-09-12 | 14
5.1 | Managers write reviews | Manager | 2026-08-30 | 2026-09-10 | 12
5.2 | Draft ratings | Manager | 2026-09-03 | 2026-09-10 | 8
5.3 | Manager one-up review | Manager | 2026-09-09 | 2026-09-12 | 4
6 | ◆ Draft ratings ready |  | 2026-09-13 | 2026-09-13 | [7 empty] | ◆
7 | Calibration |  | 2026-09-13 | 2026-09-24 | 12
7.1 | Prepare calibration data | HR | 2026-09-13 | 2026-09-15 | 3
7.2 | Calibration sessions | Leadership | 2026-09-16 | 2026-09-20 | 5
7.3 | Finalize ratings | HR | 2026-09-20 | 2026-09-22 | 3
7.4 | Comp & promotion decisions | Leadership | 2026-09-20 | 2026-09-24 | 5
8 | ◆ Ratings finalized |  | 2026-09-25 | 2026-09-25 | [8 empty] | ◆
9 | Delivery |  | 2026-09-25 | 2026-10-01 | 7
9.1 | Prepare review packets | HR | 2026-09-25 | 2026-09-26 | 2
9.2 | Deliver reviews in 1:1s | Manager | 2026-09-27 | 2026-10-01 | 5
10 | ◆ Reviews delivered |  | 2026-10-02 | 2026-10-02 | [9 empty] | ◆
11 | Development & close |  | 2026-10-02 | 2026-10-11 | 10
11.1 | Set next-cycle goals | Employee | 2026-10-02 | 2026-10-06 | 5
11.2 | Agree development plans | Manager | 2026-10-02 | 2026-10-07 | 6
11.3 | Gather feedback on the process | HR | 2026-10-04 | 2026-10-07 | 4
11.4 | Close the cycle & report | HR | 2026-10-07 | 2026-10-09 | 3
12 | ◆ Cycle closed |  | 2026-10-10 | 2026-10-10 | [10 empty] | ◆