## Slide 1
Pharma Product Launch Plan
Free Gantt chart template · gantts.app

## Slide 2
Pharma Product Launch Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Regulatory submission
Dossier compilation
Pre-submission meeting
◆ Submission to first market
Regulatory review clock
Questions & responses
Labelling negotiation
◆ Marketing authorisation granted
CMC & manufacturing readiness
Process scale-up & tech transfer
Site readiness & equipment qualification
Three validation batches
Stability data package
Pre-approval inspection
Launch stock manufacture
◆ Launch stock released
Serialisation & labelling
Artwork & translations per market
Serialisation & aggregation set-up
National repository connections
Packaging line qualification
Pricing & reimbursement
Value dossier & HTA submission
Pricing strategy & reference analysis
Payer negotiations - first market
Reimbursement listing decision
◆ First reimbursement listing
Medical affairs & evidence
Publication plan & data disclosure
Advisory boards & KOL engagement
Medical education programme
Medical information & RWE set-up
Commercial launch by country
Brand positioning & launch materials
Field force hiring
Field force training & launch meeting
◆ First commercial sale
Wave two markets
Wave three markets
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Regulatory submission |  | 2026-08-02 | 2027-09-05 | 400 | 60%
1.1 | Dossier compilation | Regulatory | 2026-08-02 | 2026-10-30 | 90 | 100%
1.2 | Pre-submission meeting | Regulatory | 2026-10-01 | 2026-10-20 | 20 | 100%
2 | Submission to first market |  | 2026-11-05 | 2026-11-05 | — | —
2.1 | Regulatory review clock | Agency | 2026-11-05 | 2027-07-02 | 240 | 60%
2.2 | Questions & responses | Regulatory | 2027-02-18 | 2027-05-18 | 90 | 40%
2.3 | Labelling negotiation | Regulatory | 2027-06-18 | 2027-08-16 | 60 | 0%
3 | Marketing authorisation granted |  | 2027-09-06 | 2027-09-06 | — | —
4 | CMC & manufacturing readiness |  | 2026-09-01 | 2027-09-25 | 390 | 40%
4.1 | Process scale-up & tech transfer | MSAT | 2026-09-01 | 2026-12-29 | 120 | 100%
4.2 | Site readiness & equipment qualification | Manufacturing | 2026-11-30 | 2027-02-27 | 90 | 80%
4.3 | Three validation batches | Manufacturing | 2027-02-23 | 2027-06-12 | 110 | 40%
4.4 | Stability data package | QC | 2027-04-09 | 2027-08-16 | 130 | 20%
4.5 | Pre-approval inspection | Agency | 2027-06-28 | 2027-07-17 | 20 | 0%
4.6 | Launch stock manufacture | Manufacturing | 2027-07-18 | 2027-09-25 | 70 | 0%
5 | Launch stock released |  | 2027-09-26 | 2027-09-26 | — | —
6 | Serialisation & labelling |  | 2027-02-18 | 2027-10-25 | 250 | 20%
6.1 | Artwork & translations per market | Packaging | 2027-02-18 | 2027-06-07 | 110 | 40%
6.2 | Serialisation & aggregation set-up | IT | 2027-04-09 | 2027-08-06 | 120 | 20%
6.3 | National repository connections | IT | 2027-07-08 | 2027-09-15 | 70 | 0%
6.4 | Packaging line qualification | Manufacturing | 2027-08-27 | 2027-10-25 | 60 | 0%

## Slide 4
7 | Pricing & reimbursement |  | 2027-03-20 | 2028-03-03 | 350 | 10%
7.1 | Value dossier & HTA submission | Market access | 2027-03-20 | 2027-07-17 | 120 | 30%
7.2 | Pricing strategy & reference analysis | Market access | 2027-05-09 | 2027-08-06 | 90 | 20%
7.3 | Payer negotiations - first market | Market access | 2027-09-06 | 2027-12-24 | 110 | 0%
7.4 | Reimbursement listing decision | Payer | 2027-12-20 | 2028-02-02 | 45 | 0%
8 | First reimbursement listing |  | 2028-02-03 | 2028-02-03 | — | —
9 | Medical affairs & evidence |  | 2026-11-30 | 2028-01-03 | 400 | 30%
9.1 | Publication plan & data disclosure | Medical affairs | 2026-11-30 | 2027-04-08 | 130 | 60%
9.2 | Advisory boards & KOL engagement | Medical affairs | 2027-02-18 | 2027-07-27 | 160 | 30%
9.3 | Medical education programme | Medical affairs | 2027-06-28 | 2027-11-04 | 130 | 10%
9.4 | Medical information & RWE set-up | Medical affairs | 2027-09-06 | 2028-01-03 | 120 | 0%
10 | Commercial launch by country |  | 2027-07-08 | 2028-05-22 | 320 | 5%
10.1 | Brand positioning & launch materials | Marketing | 2027-07-08 | 2027-10-05 | 90 | 20%
10.2 | Field force hiring | Commercial | 2027-09-06 | 2027-11-14 | 70 | 0%
10.3 | Field force training & launch meeting | Commercial | 2027-11-15 | 2027-12-24 | 40 | 0%
11 | First commercial sale |  | 2028-02-13 | 2028-02-13 | — | —
11.1 | Wave two markets | Commercial | 2028-02-13 | 2028-04-12 | 60 | 0%
11.2 | Wave three markets | Commercial | 2028-04-03 | 2028-05-22 | 50 | 0%