## Gantt
Pharma Product Launch Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29
1 | Regulatory submission |  | 2026-08-02 | 2027-09-05 | 400
1.1 | Dossier compilation | Regulatory | 2026-08-02 | 2026-10-30 | 90
1.2 | Pre-submission meeting | Regulatory | 2026-10-01 | 2026-10-20 | 20
2 | ◆ Submission to first market |  | 2026-11-05 | 2026-11-05 | [14 empty] | ◆
2.1 | Regulatory review clock | Agency | 2026-11-05 | 2027-07-02 | 240
2.2 | Questions & responses | Regulatory | 2027-02-18 | 2027-05-18 | 90
2.3 | Labelling negotiation | Regulatory | 2027-06-18 | 2027-08-16 | 60
3 | ◆ Marketing authorisation granted |  | 2027-09-06 | 2027-09-06 | [58 empty] | ◆
4 | CMC & manufacturing readiness |  | 2026-09-01 | 2027-09-25 | 390
4.1 | Process scale-up & tech transfer | MSAT | 2026-09-01 | 2026-12-29 | 120
4.2 | Site readiness & equipment qualification | Manufacturing | 2026-11-30 | 2027-02-27 | 90
4.3 | Three validation batches | Manufacturing | 2027-02-23 | 2027-06-12 | 110
4.4 | Stability data package | QC | 2027-04-09 | 2027-08-16 | 130
4.5 | Pre-approval inspection | Agency | 2027-06-28 | 2027-07-17 | 20
4.6 | Launch stock manufacture | Manufacturing | 2027-07-18 | 2027-09-25 | 70
5 | ◆ Launch stock released |  | 2027-09-26 | 2027-09-26 | [61 empty] | ◆
6 | Serialisation & labelling |  | 2027-02-18 | 2027-10-25 | 250
6.1 | Artwork & translations per market | Packaging | 2027-02-18 | 2027-06-07 | 110
6.2 | Serialisation & aggregation set-up | IT | 2027-04-09 | 2027-08-06 | 120
6.3 | National repository connections | IT | 2027-07-08 | 2027-09-15 | 70
6.4 | Packaging line qualification | Manufacturing | 2027-08-27 | 2027-10-25 | 60
7 | Pricing & reimbursement |  | 2027-03-20 | 2028-03-03 | 350
7.1 | Value dossier & HTA submission | Market access | 2027-03-20 | 2027-07-17 | 120
7.2 | Pricing strategy & reference analysis | Market access | 2027-05-09 | 2027-08-06 | 90
7.3 | Payer negotiations - first market | Market access | 2027-09-06 | 2027-12-24 | 110
7.4 | Reimbursement listing decision | Payer | 2027-12-20 | 2028-02-02 | 45
8 | ◆ First reimbursement listing |  | 2028-02-03 | 2028-02-03 | [79 empty] | ◆
9 | Medical affairs & evidence |  | 2026-11-30 | 2028-01-03 | 400
9.1 | Publication plan & data disclosure | Medical affairs | 2026-11-30 | 2027-04-08 | 130
9.2 | Advisory boards & KOL engagement | Medical affairs | 2027-02-18 | 2027-07-27 | 160
9.3 | Medical education programme | Medical affairs | 2027-06-28 | 2027-11-04 | 130
9.4 | Medical information & RWE set-up | Medical affairs | 2027-09-06 | 2028-01-03 | 120
10 | Commercial launch by country |  | 2027-07-08 | 2028-05-22 | 320
10.1 | Brand positioning & launch materials | Marketing | 2027-07-08 | 2027-10-05 | 90
10.2 | Field force hiring | Commercial | 2027-09-06 | 2027-11-14 | 70
10.3 | Field force training & launch meeting | Commercial | 2027-11-15 | 2027-12-24 | 40
11 | ◆ First commercial sale |  | 2028-02-13 | 2028-02-13 | [81 empty] | ◆
11.1 | Wave two markets | Commercial | 2028-02-13 | 2028-04-12 | 60
11.2 | Wave three markets | Commercial | 2028-04-03 | 2028-05-22 | 50