## Slide 1
PhD Research Timeline
Free Gantt chart template · gantts.app

## Slide 2
PhD Research Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
May 7
May 21
Jun 4
Jun 18
Jul 2
Jul 16
Jul 30
Aug 13
Aug 27
Sep 10
Sep 24
Oct 8
Oct 22
Nov 5
Nov 19
Dec 3
Dec 17
Dec 31
Jan 14
Jan 28
Feb 11
Feb 25
Mar 11
Year 1 — foundations
Coursework & methods training
Literature scoping
◆ Qualifying / upgrade exam
Proposal & candidacy
Research design & proposal
◆ Proposal defense
Year 2 — data collection
Ethics approval
Fieldwork / experiments
First conference paper
Year 3 — analysis & output
Data analysis
Journal submissions
Writing up
Chapter drafting
Supervisor feedback cycles
Full revision & formatting
Submission & viva
◆ Thesis submitted
Examiner reading period
◆ Viva voce
Corrections
◆ Degree awarded
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Year 1 — foundations |  | 2026-08-02 | 2027-05-28 | 300 | 100%
1.1 | Coursework & methods training | Student | 2026-08-02 | 2027-01-28 | 180 | 100%
1.2 | Literature scoping | Student | 2026-09-01 | 2027-01-28 | 150 | 100%
2 | Qualifying / upgrade exam |  | 2027-05-29 | 2027-05-29 | — | —
3 | Proposal & candidacy |  | 2027-03-30 | 2027-08-26 | 150 | 80%
3.1 | Research design & proposal | Student | 2027-03-30 | 2027-07-17 | 110 | 100%
4 | Proposal defense |  | 2027-08-27 | 2027-08-27 | — | —
5 | Year 2 — data collection |  | 2027-08-27 | 2028-07-21 | 330 | 30%
5.1 | Ethics approval | Committee | 2027-08-27 | 2027-10-25 | 60 | 100%
5.2 | Fieldwork / experiments | Student | 2027-10-26 | 2028-06-21 | 240 | 25%
5.3 | First conference paper | Student | 2028-03-24 | 2028-06-21 | 90 | 10%
6 | Year 3 — analysis & output |  | 2028-07-02 | 2029-04-27 | 300 | 0%
6.1 | Data analysis | Student | 2028-07-02 | 2028-12-28 | 180 | 0%
6.2 | Journal submissions | Student | 2028-10-30 | 2029-04-27 | 180 | 0%
7 | Writing up |  | 2029-03-09 | 2029-11-03 | 240 | 0%
7.1 | Chapter drafting | Student | 2029-03-09 | 2029-08-05 | 150 | 0%
7.2 | Supervisor feedback cycles | Supervisor | 2029-07-07 | 2029-09-14 | 70 | 0%
7.3 | Full revision & formatting | Student | 2029-09-05 | 2029-11-03 | 60 | 0%
8 | Submission & viva |  | 2029-11-04 | 2030-03-13 | 130 | 0%
9 | Thesis submitted |  | 2029-11-09 | 2029-11-09 | — | —
9.1 | Examiner reading period | Examiners | 2029-11-09 | 2030-01-22 | 75 | 0%

## Slide 4
10 | Viva voce |  | 2030-01-28 | 2030-01-28 | — | —
10.1 | Corrections | Student | 2030-01-28 | 2030-03-13 | 45 | 0%
11 | Degree awarded |  | 2030-03-14 | 2030-03-14 | — | —