## Gantt
PhD Research Timeline
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 25 | Jan 1 | Jan 8 | Jan 15 | Jan 22 | Jan 29 | Feb 5 | Feb 12 | Feb 19 | Feb 26 | Mar 5 | Mar 12 | Mar 19 | Mar 26 | Apr 2 | Apr 9 | Apr 16 | Apr 23 | Apr 30 | May 7 | May 14 | May 21 | May 28 | Jun 4 | Jun 11 | Jun 18 | Jun 25 | Jul 2 | Jul 9 | Jul 16 | Jul 23 | Jul 30 | Aug 6 | Aug 13 | Aug 20 | Aug 27 | Sep 3 | Sep 10 | Sep 17 | Sep 24 | Oct 1 | Oct 8 | Oct 15 | Oct 22 | Oct 29 | Nov 5 | Nov 12 | Nov 19 | Nov 26 | Dec 3 | Dec 10 | Dec 17 | Dec 24 | Dec 31 | Jan 7 | Jan 14 | Jan 21 | Jan 28 | Feb 4 | Feb 11 | Feb 18 | Feb 25 | Mar 4 | Mar 11 | Mar 18
1 | Year 1 — foundations |  | 2026-08-02 | 2027-05-28 | 300
1.1 | Coursework & methods training | Student | 2026-08-02 | 2027-01-28 | 180
1.2 | Literature scoping | Student | 2026-09-01 | 2027-01-28 | 150
2 | ◆ Qualifying / upgrade exam |  | 2027-05-29 | 2027-05-29 | [43 empty] | ◆
3 | Proposal & candidacy |  | 2027-03-30 | 2027-08-26 | 150
3.1 | Research design & proposal | Student | 2027-03-30 | 2027-07-17 | 110
4 | ◆ Proposal defense |  | 2027-08-27 | 2027-08-27 | [56 empty] | ◆
5 | Year 2 — data collection |  | 2027-08-27 | 2028-07-21 | 330
5.1 | Ethics approval | Committee | 2027-08-27 | 2027-10-25 | 60
5.2 | Fieldwork / experiments | Student | 2027-10-26 | 2028-06-21 | 240
5.3 | First conference paper | Student | 2028-03-24 | 2028-06-21 | 90
6 | Year 3 — analysis & output |  | 2028-07-02 | 2029-04-27 | 300
6.1 | Data analysis | Student | 2028-07-02 | 2028-12-28 | 180
6.2 | Journal submissions | Student | 2028-10-30 | 2029-04-27 | 180
7 | Writing up |  | 2029-03-09 | 2029-11-03 | 240
7.1 | Chapter drafting | Student | 2029-03-09 | 2029-08-05 | 150
7.2 | Supervisor feedback cycles | Supervisor | 2029-07-07 | 2029-09-14 | 70
7.3 | Full revision & formatting | Student | 2029-09-05 | 2029-11-03 | 60
8 | Submission & viva |  | 2029-11-04 | 2030-03-13 | 130
9 | ◆ Thesis submitted |  | 2029-11-09 | 2029-11-09 | [171 empty] | ◆
9.1 | Examiner reading period | Examiners | 2029-11-09 | 2030-01-22 | 75
10 | ◆ Viva voce |  | 2030-01-28 | 2030-01-28 | [183 empty] | ◆
10.1 | Corrections | Student | 2030-01-28 | 2030-03-13 | 45
11 | ◆ Degree awarded |  | 2030-03-14 | 2030-03-14 | [189 empty] | ◆