## Slide 1
Podcast Launch Plan
Free Gantt chart template · gantts.app

## Slide 2
Podcast Launch Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Concept & plan
Define niche & target audience
Choose format & show name
Plan first season (10 episodes)
◆ Concept locked
Branding & setup
Cover art & branding
Intro & outro music
Choose hosting & equipment
Set up recording space
◆ Setup ready
Record launch episodes
Book & prep guests
Record 3-5 launch episodes
◆ Recording done
Edit & assets
Edit episodes & audio
Write show notes & transcripts
Record trailer
◆ Episodes ready
Submit & pre-launch
Set up RSS & submit to Apple/Spotify
Build website & landing page
Pre-launch promo & email list
◆ Directories approved
Launch & grow
◆ Launch day: 3-episode drop
Launch promotion & outreach
Guest & cross-promo outreach
Review analytics & iterate
◆ First month reviewed
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Concept & plan |  | 2026-08-02 | 2026-08-15 | 14 | 100%
1.1 | Define niche & target audience | Host | 2026-08-02 | 2026-08-06 | 5 | 100%
1.2 | Choose format & show name | Host | 2026-08-07 | 2026-08-11 | 5 | 100%
1.3 | Plan first season (10 episodes) | Host | 2026-08-10 | 2026-08-15 | 6 | 80%
2 | Concept locked |  | 2026-08-16 | 2026-08-16 | , | ,
3 | Branding & setup |  | 2026-08-16 | 2026-09-05 | 21 | 40%
3.1 | Cover art & branding | Designer | 2026-08-16 | 2026-08-27 | 12 | 50%
3.2 | Intro & outro music | Producer | 2026-08-20 | 2026-08-26 | 7 | 20%
3.3 | Choose hosting & equipment | Host | 2026-08-16 | 2026-08-22 | 7 | 100%
3.4 | Set up recording space | Host | 2026-08-23 | 2026-08-27 | 5 | 0%
4 | Setup ready |  | 2026-09-06 | 2026-09-06 | , | ,
5 | Record launch episodes |  | 2026-08-30 | 2026-09-26 | 28 | 0%
5.1 | Book & prep guests | Host | 2026-08-30 | 2026-09-12 | 14 | 0%
5.2 | Record 3-5 launch episodes | Host | 2026-09-06 | 2026-09-23 | 18 | 0%
6 | Recording done |  | 2026-09-27 | 2026-09-27 | , | ,
7 | Edit & assets |  | 2026-09-20 | 2026-10-10 | 21 | 0%
7.1 | Edit episodes & audio | Editor | 2026-09-20 | 2026-10-04 | 15 | 0%
7.2 | Write show notes & transcripts | Host | 2026-09-27 | 2026-10-06 | 10 | 0%
7.3 | Record trailer | Host | 2026-09-27 | 2026-09-29 | 3 | 0%
8 | Episodes ready |  | 2026-10-11 | 2026-10-11 | , | ,
9 | Submit & pre-launch |  | 2026-10-01 | 2026-10-22 | 22 | 0%

## Slide 4
9.1 | Set up RSS & submit to Apple/Spotify | Host | 2026-10-01 | 2026-10-08 | 8 | 0%
9.2 | Build website & landing page | Marketing | 2026-10-01 | 2026-10-14 | 14 | 0%
9.3 | Pre-launch promo & email list | Marketing | 2026-10-11 | 2026-10-20 | 10 | 0%
10 | Directories approved |  | 2026-10-18 | 2026-10-18 | , | ,
11 | Launch & grow |  | 2026-10-18 | 2026-11-14 | 28 | 0%
12 | Launch day: 3-episode drop |  | 2026-10-18 | 2026-10-18 | , | ,
12.1 | Launch promotion & outreach | Marketing | 2026-10-18 | 2026-10-31 | 14 | 0%
12.2 | Guest & cross-promo outreach | Host | 2026-10-25 | 2026-11-07 | 14 | 0%
12.3 | Review analytics & iterate | Host | 2026-11-01 | 2026-11-10 | 10 | 0%
13 | First month reviewed |  | 2026-11-15 | 2026-11-15 | , | ,