## Gantt
Podcast Launch Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16
1 | Concept & plan |  | 2026-08-02 | 2026-08-15 | 14
1.1 | Define niche & target audience | Host | 2026-08-02 | 2026-08-06 | 5
1.2 | Choose format & show name | Host | 2026-08-07 | 2026-08-11 | 5
1.3 | Plan first season (10 episodes) | Host | 2026-08-10 | 2026-08-15 | 6
2 | ◆ Concept locked |  | 2026-08-16 | 2026-08-16 |  |  |  | ◆
3 | Branding & setup |  | 2026-08-16 | 2026-09-05 | 21
3.1 | Cover art & branding | Designer | 2026-08-16 | 2026-08-27 | 12
3.2 | Intro & outro music | Producer | 2026-08-20 | 2026-08-26 | 7
3.3 | Choose hosting & equipment | Host | 2026-08-16 | 2026-08-22 | 7
3.4 | Set up recording space | Host | 2026-08-23 | 2026-08-27 | 5
4 | ◆ Setup ready |  | 2026-09-06 | 2026-09-06 | [6 empty] | ◆
5 | Record launch episodes |  | 2026-08-30 | 2026-09-26 | 28
5.1 | Book & prep guests | Host | 2026-08-30 | 2026-09-12 | 14
5.2 | Record 3-5 launch episodes | Host | 2026-09-06 | 2026-09-23 | 18
6 | ◆ Recording done |  | 2026-09-27 | 2026-09-27 | [9 empty] | ◆
7 | Edit & assets |  | 2026-09-20 | 2026-10-10 | 21
7.1 | Edit episodes & audio | Editor | 2026-09-20 | 2026-10-04 | 15
7.2 | Write show notes & transcripts | Host | 2026-09-27 | 2026-10-06 | 10
7.3 | Record trailer | Host | 2026-09-27 | 2026-09-29 | 3
8 | ◆ Episodes ready |  | 2026-10-11 | 2026-10-11 | [11 empty] | ◆
9 | Submit & pre-launch |  | 2026-10-01 | 2026-10-22 | 22
9.1 | Set up RSS & submit to Apple/Spotify | Host | 2026-10-01 | 2026-10-08 | 8
9.2 | Build website & landing page | Marketing | 2026-10-01 | 2026-10-14 | 14
9.3 | Pre-launch promo & email list | Marketing | 2026-10-11 | 2026-10-20 | 10
10 | ◆ Directories approved |  | 2026-10-18 | 2026-10-18 | [12 empty] | ◆
11 | Launch & grow |  | 2026-10-18 | 2026-11-14 | 28
12 | ◆ Launch day: 3-episode drop |  | 2026-10-18 | 2026-10-18 | [12 empty] | ◆
12.1 | Launch promotion & outreach | Marketing | 2026-10-18 | 2026-10-31 | 14
12.2 | Guest & cross-promo outreach | Host | 2026-10-25 | 2026-11-07 | 14
12.3 | Review analytics & iterate | Host | 2026-11-01 | 2026-11-10 | 10
13 | ◆ First month reviewed |  | 2026-11-15 | 2026-11-15 | [16 empty] | ◆