## Slide 1
Port Terminal Construction
Free Gantt chart template · gantts.app

## Slide 2
Port Terminal Construction
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Studies & consents
Bathymetric & geotechnical survey
Environmental impact assessment
Disposal ground licensing
Marine licence & dredging consent
◆ Dredging consent granted
Dredging & reclamation
Dredger mobilisation window
Capital dredging campaign
Disposal to licensed ground
Reclamation fill placement
Surcharge & settlement monitoring
Quay wall & berth
Piling & caisson placement
Capping beam & deck
Fenders & bollards
Berth pocket dredge to depth
◆ Berth available
Crane rail & yard
Ground improvement
Crane rail beams & rails
Rail survey & alignment proof
Yard paving & drainage
Lighting masts & reefer racks
Gate complex & weighbridges
STS cranes & equipment
◆ STS crane order placed
Crane fabrication
Heavy-lift vessel voyage
Crane offload & walk ashore
Crane erection & load testing
Yard equipment delivery
◆ Cranes accepted
TOS & go-live
TOS configuration & master data
Gate, OCR & customs integration
Network & radio coverage
Operator training & simulation
Trial vessel call
◆ First commercial vessel
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Studies & consents |  | 2026-08-02 | 2027-02-27 | 210 | 100%
1.1 | Bathymetric & geotechnical survey | Survey | 2026-08-02 | 2026-10-10 | 70 | 100%
1.2 | Environmental impact assessment | Consultant | 2026-09-21 | 2027-01-08 | 110 | 100%
1.3 | Disposal ground licensing | Consultant | 2026-11-30 | 2027-02-27 | 90 | 100%
1.4 | Marine licence & dredging consent | Legal | 2026-12-30 | 2027-02-27 | 60 | 100%
2 | Dredging consent granted |  | 2027-02-28 | 2027-02-28 | — | —
3 | Dredging & reclamation |  | 2027-02-28 | 2028-01-23 | 330 | 40%
3.1 | Dredger mobilisation window | Marine contractor | 2027-02-28 | 2027-03-24 | 25 | 100%
3.2 | Capital dredging campaign | Marine contractor | 2027-03-25 | 2027-08-01 | 130 | 60%
3.3 | Disposal to licensed ground | Marine contractor | 2027-03-30 | 2027-08-06 | 130 | 55%
3.4 | Reclamation fill placement | Marine contractor | 2027-05-29 | 2027-09-25 | 120 | 25%
3.5 | Surcharge & settlement monitoring | Geotechnical | 2027-09-26 | 2028-01-23 | 120 | 0%
4 | Quay wall & berth |  | 2027-05-29 | 2028-03-03 | 280 | 10%
4.1 | Piling & caisson placement | Marine contractor | 2027-05-29 | 2027-10-15 | 140 | 20%
4.2 | Capping beam & deck | Civils | 2027-10-06 | 2028-01-03 | 90 | 0%
4.3 | Fenders & bollards | Marine contractor | 2027-12-20 | 2028-02-02 | 45 | 0%
4.4 | Berth pocket dredge to depth | Marine contractor | 2028-01-04 | 2028-03-03 | 60 | 0%
5 | Berth available |  | 2028-03-04 | 2028-03-04 | — | —
6 | Crane rail & yard |  | 2028-01-04 | 2028-09-19 | 260 | 0%
6.1 | Ground improvement | Civils | 2028-01-04 | 2028-03-23 | 80 | 0%
6.2 | Crane rail beams & rails | Civils | 2028-03-14 | 2028-06-01 | 80 | 0%

## Slide 4
6.3 | Rail survey & alignment proof | Survey | 2028-05-28 | 2028-06-21 | 25 | 0%
6.4 | Yard paving & drainage | Civils | 2028-03-24 | 2028-08-10 | 140 | 0%
6.5 | Lighting masts & reefer racks | Electrical | 2028-07-02 | 2028-08-30 | 60 | 0%
6.6 | Gate complex & weighbridges | Civils | 2028-06-22 | 2028-09-19 | 90 | 0%
7 | STS cranes & equipment |  | 2027-03-30 | 2028-10-09 | 560 | 30%
8 | STS crane order placed |  | 2027-03-30 | 2027-03-30 | — | —
8.1 | Crane fabrication | Crane supplier | 2027-03-30 | 2028-06-01 | 430 | 45%
8.2 | Heavy-lift vessel voyage | Crane supplier | 2028-06-02 | 2028-07-16 | 45 | 0%
8.3 | Crane offload & walk ashore | Crane supplier | 2028-07-17 | 2028-07-31 | 15 | 0%
8.4 | Crane erection & load testing | Crane supplier | 2028-08-01 | 2028-09-24 | 55 | 0%
8.5 | Yard equipment delivery | Procurement | 2028-07-02 | 2028-09-09 | 70 | 0%
9 | Cranes accepted |  | 2028-09-25 | 2028-09-25 | — | —
10 | TOS & go-live |  | 2027-11-25 | 2028-11-08 | 350 | 5%
10.1 | TOS configuration & master data | IT | 2027-11-25 | 2028-04-22 | 150 | 15%
10.2 | Gate, OCR & customs integration | IT | 2028-03-24 | 2028-07-21 | 120 | 0%
10.3 | Network & radio coverage | IT | 2028-06-22 | 2028-08-20 | 60 | 0%
10.4 | Operator training & simulation | Operations | 2028-08-16 | 2028-09-29 | 45 | 0%
10.5 | Trial vessel call | Operations | 2028-09-30 | 2028-10-06 | 7 | 0%
11 | First commercial vessel |  | 2028-11-09 | 2028-11-09 | — | —