## Gantt
Port Terminal Construction
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13
1 | Studies & consents |  | 2026-08-02 | 2027-02-27 | 210
1.1 | Bathymetric & geotechnical survey | Survey | 2026-08-02 | 2026-10-10 | 70
1.2 | Environmental impact assessment | Consultant | 2026-09-21 | 2027-01-08 | 110
1.3 | Disposal ground licensing | Consultant | 2026-11-30 | 2027-02-27 | 90
1.4 | Marine licence & dredging consent | Legal | 2026-12-30 | 2027-02-27 | 60
2 | ◆ Dredging consent granted |  | 2027-02-28 | 2027-02-28 | [31 empty] | ◆
3 | Dredging & reclamation |  | 2027-02-28 | 2028-01-23 | 330
3.1 | Dredger mobilisation window | Marine contractor | 2027-02-28 | 2027-03-24 | 25
3.2 | Capital dredging campaign | Marine contractor | 2027-03-25 | 2027-08-01 | 130
3.3 | Disposal to licensed ground | Marine contractor | 2027-03-30 | 2027-08-06 | 130
3.4 | Reclamation fill placement | Marine contractor | 2027-05-29 | 2027-09-25 | 120
3.5 | Surcharge & settlement monitoring | Geotechnical | 2027-09-26 | 2028-01-23 | 120
4 | Quay wall & berth |  | 2027-05-29 | 2028-03-03 | 280
4.1 | Piling & caisson placement | Marine contractor | 2027-05-29 | 2027-10-15 | 140
4.2 | Capping beam & deck | Civils | 2027-10-06 | 2028-01-03 | 90
4.3 | Fenders & bollards | Marine contractor | 2027-12-20 | 2028-02-02 | 45
4.4 | Berth pocket dredge to depth | Marine contractor | 2028-01-04 | 2028-03-03 | 60
5 | ◆ Berth available |  | 2028-03-04 | 2028-03-04 | [83 empty] | ◆
6 | Crane rail & yard |  | 2028-01-04 | 2028-09-19 | 260
6.1 | Ground improvement | Civils | 2028-01-04 | 2028-03-23 | 80
6.2 | Crane rail beams & rails | Civils | 2028-03-14 | 2028-06-01 | 80
6.3 | Rail survey & alignment proof | Survey | 2028-05-28 | 2028-06-21 | 25
6.4 | Yard paving & drainage | Civils | 2028-03-24 | 2028-08-10 | 140
6.5 | Lighting masts & reefer racks | Electrical | 2028-07-02 | 2028-08-30 | 60
6.6 | Gate complex & weighbridges | Civils | 2028-06-22 | 2028-09-19 | 90
7 | STS cranes & equipment |  | 2027-03-30 | 2028-10-09 | 560
8 | ◆ STS crane order placed |  | 2027-03-30 | 2027-03-30 | [35 empty] | ◆
8.1 | Crane fabrication | Crane supplier | 2027-03-30 | 2028-06-01 | 430
8.2 | Heavy-lift vessel voyage | Crane supplier | 2028-06-02 | 2028-07-16 | 45
8.3 | Crane offload & walk ashore | Crane supplier | 2028-07-17 | 2028-07-31 | 15
8.4 | Crane erection & load testing | Crane supplier | 2028-08-01 | 2028-09-24 | 55
8.5 | Yard equipment delivery | Procurement | 2028-07-02 | 2028-09-09 | 70
9 | ◆ Cranes accepted |  | 2028-09-25 | 2028-09-25 | [113 empty] | ◆
10 | TOS & go-live |  | 2027-11-25 | 2028-11-08 | 350
10.1 | TOS configuration & master data | IT | 2027-11-25 | 2028-04-22 | 150
10.2 | Gate, OCR & customs integration | IT | 2028-03-24 | 2028-07-21 | 120
10.3 | Network & radio coverage | IT | 2028-06-22 | 2028-08-20 | 60
10.4 | Operator training & simulation | Operations | 2028-08-16 | 2028-09-29 | 45
10.5 | Trial vessel call | Operations | 2028-09-30 | 2028-10-06 | 7
11 | ◆ First commercial vessel |  | 2028-11-09 | 2028-11-09 | [119 empty] | ◆