## Slide 1
Post-Merger Integration Plan
Free Gantt chart template · gantts.app

## Slide 2
Post-Merger Integration Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Pre-close planning
Stand up integration office
Name workstream leads
Clean-team analysis
Day one checklist
◆ Close
Day one readiness
Legal entity & signing authority
Employee & customer communications
Payroll & benefits continuity
System access & email routing
Organization & people
Org design
Selection & retention decisions
Consultation where required
Harmonize terms & benefits
Finance & reporting
Chart of accounts mapping
Consolidated reporting pack
Banking & treasury consolidation
◆ First combined month-end
Systems & data
Application rationalization
Identity & email migration
CRM consolidation
ERP & finance systems
◆ Systems cutover
Customers & synergies
Customer & contract migration
Brand & go-to-market alignment
Synergy delivery tracking
◆ Synergy run-rate achieved
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Pre-close planning |  | 2026-08-02 | 2026-09-30 | 60 | 100%
1.1 | Stand up integration office | IMO lead | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Name workstream leads | IMO lead | 2026-08-17 | 2026-08-31 | 15 | 100%
1.3 | Clean-team analysis | Clean team | 2026-08-22 | 2026-09-30 | 40 | 100%
1.4 | Day one checklist | IMO lead | 2026-09-01 | 2026-09-30 | 30 | 100%
2 | Close |  | 2026-10-01 | 2026-10-01 | — | —
3 | Day one readiness |  | 2026-10-01 | 2026-10-30 | 30 | 60%
3.1 | Legal entity & signing authority | Legal | 2026-10-01 | 2026-10-10 | 10 | 100%
3.2 | Employee & customer communications | Comms | 2026-10-01 | 2026-10-07 | 7 | 100%
3.3 | Payroll & benefits continuity | HR | 2026-10-01 | 2026-10-25 | 25 | 60%
3.4 | System access & email routing | IT | 2026-10-01 | 2026-10-20 | 20 | 50%
4 | Organization & people |  | 2026-10-16 | 2027-04-13 | 180 | 20%
4.1 | Org design | HR | 2026-10-16 | 2026-12-04 | 50 | 40%
4.2 | Selection & retention decisions | HR | 2026-11-25 | 2027-01-08 | 45 | 20%
4.3 | Consultation where required | HR | 2026-12-30 | 2027-02-12 | 45 | 0%
4.4 | Harmonize terms & benefits | HR | 2027-02-13 | 2027-04-13 | 60 | 0%
5 | Finance & reporting |  | 2026-10-01 | 2027-02-27 | 150 | 30%
5.1 | Chart of accounts mapping | Finance | 2026-10-01 | 2026-11-14 | 45 | 60%
5.2 | Consolidated reporting pack | Finance | 2026-11-05 | 2026-12-14 | 40 | 30%
5.3 | Banking & treasury consolidation | Treasury | 2026-11-20 | 2027-01-18 | 60 | 10%
6 | First combined month-end |  | 2026-12-30 | 2026-12-30 | — | —

## Slide 4
7 | Systems & data |  | 2026-10-31 | 2027-06-07 | 220 | 10%
7.1 | Application rationalization | IT | 2026-10-31 | 2026-12-19 | 50 | 30%
7.2 | Identity & email migration | IT | 2026-12-10 | 2027-02-07 | 60 | 10%
7.3 | CRM consolidation | IT | 2027-02-03 | 2027-04-13 | 70 | 0%
7.4 | ERP & finance systems | IT | 2027-03-10 | 2027-06-07 | 90 | 0%
8 | Systems cutover |  | 2027-06-08 | 2027-06-08 | — | —
9 | Customers & synergies |  | 2026-10-11 | 2027-07-27 | 290 | 15%
9.1 | Customer & contract migration | Commercial | 2026-10-11 | 2027-02-07 | 120 | 25%
9.2 | Brand & go-to-market alignment | Marketing | 2026-11-30 | 2027-02-27 | 90 | 10%
9.3 | Synergy delivery tracking | IMO lead | 2026-10-31 | 2027-07-27 | 270 | 10%
10 | Synergy run-rate achieved |  | 2027-07-28 | 2027-07-28 | — | —