## Gantt
Post-Merger Integration Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2
1 | Pre-close planning |  | 2026-08-02 | 2026-09-30 | 60
1.1 | Stand up integration office | IMO lead | 2026-08-02 | 2026-08-21 | 20
1.2 | Name workstream leads | IMO lead | 2026-08-17 | 2026-08-31 | 15
1.3 | Clean-team analysis | Clean team | 2026-08-22 | 2026-09-30 | 40
1.4 | Day one checklist | IMO lead | 2026-09-01 | 2026-09-30 | 30
2 | ◆ Close |  | 2026-10-01 | 2026-10-01 | [9 empty] | ◆
3 | Day one readiness |  | 2026-10-01 | 2026-10-30 | 30
3.1 | Legal entity & signing authority | Legal | 2026-10-01 | 2026-10-10 | 10
3.2 | Employee & customer communications | Comms | 2026-10-01 | 2026-10-07 | 7
3.3 | Payroll & benefits continuity | HR | 2026-10-01 | 2026-10-25 | 25
3.4 | System access & email routing | IT | 2026-10-01 | 2026-10-20 | 20
4 | Organization & people |  | 2026-10-16 | 2027-04-13 | 180
4.1 | Org design | HR | 2026-10-16 | 2026-12-04 | 50
4.2 | Selection & retention decisions | HR | 2026-11-25 | 2027-01-08 | 45
4.3 | Consultation where required | HR | 2026-12-30 | 2027-02-12 | 45
4.4 | Harmonize terms & benefits | HR | 2027-02-13 | 2027-04-13 | 60
5 | Finance & reporting |  | 2026-10-01 | 2027-02-27 | 150
5.1 | Chart of accounts mapping | Finance | 2026-10-01 | 2026-11-14 | 45
5.2 | Consolidated reporting pack | Finance | 2026-11-05 | 2026-12-14 | 40
5.3 | Banking & treasury consolidation | Treasury | 2026-11-20 | 2027-01-18 | 60
6 | ◆ First combined month-end |  | 2026-12-30 | 2026-12-30 | [22 empty] | ◆
7 | Systems & data |  | 2026-10-31 | 2027-06-07 | 220
7.1 | Application rationalization | IT | 2026-10-31 | 2026-12-19 | 50
7.2 | Identity & email migration | IT | 2026-12-10 | 2027-02-07 | 60
7.3 | CRM consolidation | IT | 2027-02-03 | 2027-04-13 | 70
7.4 | ERP & finance systems | IT | 2027-03-10 | 2027-06-07 | 90
8 | ◆ Systems cutover |  | 2027-06-08 | 2027-06-08 | [45 empty] | ◆
9 | Customers & synergies |  | 2026-10-11 | 2027-07-27 | 290
9.1 | Customer & contract migration | Commercial | 2026-10-11 | 2027-02-07 | 120
9.2 | Brand & go-to-market alignment | Marketing | 2026-11-30 | 2027-02-27 | 90
9.3 | Synergy delivery tracking | IMO lead | 2026-10-31 | 2027-07-27 | 270
10 | ◆ Synergy run-rate achieved |  | 2027-07-28 | 2027-07-28 | [52 empty] | ◆