## Slide 1
Product Launch Plan
Free Gantt chart template · gantts.app

## Slide 2
Product Launch Plan
Aug 3
Aug 17
Aug 31
Strategy
Market & competitor research
Positioning & messaging
Product readiness
Finalize product & beta
Pricing & packaging
Go-to-market
Marketing assets & content
PR & email campaign
Sales enablement
Launch
Pre-launch checklist
◆ Launch day
Post-launch review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Strategy |  | 2026-08-02 | 2026-08-11 | 10 | 100%
1.1 | Market & competitor research | PMM | 2026-08-02 | 2026-08-06 | 5 | 100%
1.2 | Positioning & messaging | PMM | 2026-08-07 | 2026-08-11 | 5 | 70%
2 | Product readiness |  | 2026-08-12 | 2026-08-27 | 16 | 40%
2.1 | Finalize product & beta | Product | 2026-08-12 | 2026-08-23 | 12 | 45%
2.2 | Pricing & packaging | PMM | 2026-08-16 | 2026-08-21 | 6 | 20%
3 | Go-to-market |  | 2026-08-18 | 2026-08-31 | 14 | 15%
3.1 | Marketing assets & content | Marketing | 2026-08-18 | 2026-08-27 | 10 | 20%
3.2 | PR & email campaign | Comms | 2026-08-24 | 2026-08-31 | 8 | 0%
3.3 | Sales enablement | Sales | 2026-08-24 | 2026-08-29 | 6 | 0%
4 | Launch |  | 2026-09-01 | 2026-09-06 | 6 | 0%
4.1 | Pre-launch checklist | PMM | 2026-09-01 | 2026-09-03 | 3 | 0%
4.2 | Launch day |  | 2026-09-04 | 2026-09-04 | — | —
4.3 | Post-launch review | Team | 2026-09-05 | 2026-09-09 | 5 | 0%