## Slide 1
Product Recall Plan
Free Gantt chart template · gantts.app

## Slide 2
Product Recall Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Hour zero — detect, contain, convene
Signal received & logged
Convene recall team & open incident log
Place distribution & shipments on hold
Identify affected lot & batch codes
Trace distribution records & quantity shipped
◆ Recall team convened and shipments held
Risk assessment & recall decision
Hazard characterisation
Exposure & severity assessment
Retain sample testing & verification
Classify recall severity level
Determine depth of recall
◆ Recall decision recorded
Regulator notification
Confirm applicable authorities per market
Confirm reporting window & content per jurisdiction
Prepare regulator notification pack
Submit primary market notification
Submit secondary market notifications
Agree public notice wording with regulator
◆ Regulators notified
Customer & public notification
Draft notification letters & press release
Notify distributors & wholesalers
Notify retailers & instruct stock removal
Direct customer contact from sales records
Publish public notice & website banner
Stand up customer contact line & scripts
◆ Public notice issued
Retrieval, quarantine & disposition
Set up return logistics & carrier instructions
Receive returned stock & log by lot
Secure quarantine area & segregation controls
Reconcile returns against quantity distributed
Disposition decision — rework, destroy or release
Witnessed destruction & certificates
◆ Quantity reconciliation complete
Effectiveness checks, root cause & closure
Effectiveness check round 1
Effectiveness check round 2
Effectiveness check round 3
Root cause investigation
Corrective & preventive action plan
Interim status reports to regulator
Final recall report submitted
Lessons learned & mock recall scheduled
◆ Recall closed by regulator
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Hour zero — detect, contain, convene |  | 2026-08-02 | 2026-08-04 | 3 | 100%
1.1 | Signal received & logged | Quality | 2026-08-02 | 2026-08-02 | 1 | 100%
1.2 | Convene recall team & open incident log | Recall coordinator | 2026-08-02 | 2026-08-02 | 1 | 100%
1.3 | Place distribution & shipments on hold | Logistics | 2026-08-03 | 2026-08-03 | 1 | 100%
1.4 | Identify affected lot & batch codes | Quality | 2026-08-03 | 2026-08-04 | 2 | 100%
1.5 | Trace distribution records & quantity shipped | Supply chain | 2026-08-03 | 2026-08-05 | 3 | 90%
2 | Recall team convened and shipments held |  | 2026-08-05 | 2026-08-05 | — | —
3 | Risk assessment & recall decision |  | 2026-08-04 | 2026-08-08 | 5 | 80%
3.1 | Hazard characterisation | Technical lead | 2026-08-04 | 2026-08-05 | 2 | 100%
3.2 | Exposure & severity assessment | Technical lead | 2026-08-05 | 2026-08-06 | 2 | 80%
3.3 | Retain sample testing & verification | Lab | 2026-08-05 | 2026-08-08 | 4 | 60%
3.4 | Classify recall severity level | Quality director | 2026-08-07 | 2026-08-07 | 1 | 40%
3.5 | Determine depth of recall | Recall committee | 2026-08-07 | 2026-08-07 | 1 | 20%
4 | Recall decision recorded |  | 2026-08-09 | 2026-08-09 | — | —
5 | Regulator notification |  | 2026-08-08 | 2026-08-17 | 10 | 0%
5.1 | Confirm applicable authorities per market | Regulatory affairs | 2026-08-08 | 2026-08-09 | 2 | 0%
5.2 | Confirm reporting window & content per jurisdiction | Legal | 2026-08-08 | 2026-08-09 | 2 | 0%
5.3 | Prepare regulator notification pack | Regulatory affairs | 2026-08-09 | 2026-08-10 | 2 | 0%
5.4 | Submit primary market notification | Regulatory affairs | 2026-08-10 | 2026-08-10 | 1 | 0%
5.5 | Submit secondary market | Regulatory affairs | 2026-08-11 | 2026-08-13 | 3 | 0%

## Slide 4
 | notifications |  |  |  |  | 
5.6 | Agree public notice wording with regulator | Regulatory affairs | 2026-08-11 | 2026-08-14 | 4 | 0%
6 | Regulators notified |  | 2026-08-15 | 2026-08-15 | — | —
7 | Customer & public notification |  | 2026-08-12 | 2026-08-25 | 14 | 0%
7.1 | Draft notification letters & press release | Communications | 2026-08-10 | 2026-08-12 | 3 | 0%
7.2 | Notify distributors & wholesalers | Sales | 2026-08-15 | 2026-08-16 | 2 | 0%
7.3 | Notify retailers & instruct stock removal | Sales | 2026-08-16 | 2026-08-18 | 3 | 0%
7.4 | Direct customer contact from sales records | Customer service | 2026-08-16 | 2026-08-21 | 6 | 0%
7.5 | Publish public notice & website banner | Communications | 2026-08-16 | 2026-08-17 | 2 | 0%
7.6 | Stand up customer contact line & scripts | Customer service | 2026-08-15 | 2026-08-18 | 4 | 0%
8 | Public notice issued |  | 2026-08-18 | 2026-08-18 | — | —
9 | Retrieval, quarantine & disposition |  | 2026-08-18 | 2026-09-26 | 40 | 0%
9.1 | Set up return logistics & carrier instructions | Logistics | 2026-08-16 | 2026-08-20 | 5 | 0%
9.2 | Receive returned stock & log by lot | Warehouse | 2026-08-21 | 2026-09-19 | 30 | 0%
9.3 | Secure quarantine area & segregation controls | Warehouse | 2026-08-19 | 2026-08-24 | 6 | 0%
9.4 | Reconcile returns against quantity distributed | Supply chain | 2026-09-01 | 2026-09-22 | 22 | 0%
9.5 | Disposition decision — rework, destroy or release | Quality director | 2026-09-21 | 2026-09-26 | 6 | 0%
9.6 | Witnessed destruction & certificates | Quality | 2026-09-27 | 2026-10-04 | 8 | 0%
10 | Quantity reconciliation complete |  | 2026-09-27 | 2026-09-27 | — | —
11 | Effectiveness checks, root cause & closure |  | 2026-08-24 | 2026-11-01 | 70 | 0%
11.1 | Effectiveness check round 1 | Quality | 2026-08-24 | 2026-08-29 | 6 | 0%
11.2 | Effectiveness check round 2 | Quality | 2026-09-11 | 2026-09-16 | 6 | 0%
11.3 | Effectiveness check round 3 | Quality | 2026-10-03 | 2026-10-08 | 6 | 0%
11.4 | Root cause investigation | Engineering | 2026-08-22 | 2026-09-20 | 30 | 0%

## Slide 5
11.5 | Corrective & preventive action plan | Quality director | 2026-09-21 | 2026-10-15 | 25 | 0%
11.6 | Interim status reports to regulator | Regulatory affairs | 2026-08-27 | 2026-10-25 | 60 | 0%
11.7 | Final recall report submitted | Regulatory affairs | 2026-10-21 | 2026-10-28 | 8 | 0%
11.8 | Lessons learned & mock recall scheduled | Recall coordinator | 2026-10-26 | 2026-11-01 | 7 | 0%
12 | Recall closed by regulator |  | 2026-11-02 | 2026-11-02 | — | —