## Gantt
Product Recall Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9
1 | Hour zero — detect, contain, convene |  | 2026-08-02 | 2026-08-04 | 3
1.1 | Signal received & logged | Quality | 2026-08-02 | 2026-08-02 | 1
1.2 | Convene recall team & open incident log | Recall coordinator | 2026-08-02 | 2026-08-02 | 1
1.3 | Place distribution & shipments on hold | Logistics | 2026-08-03 | 2026-08-03 | 1
1.4 | Identify affected lot & batch codes | Quality | 2026-08-03 | 2026-08-04 | 2
1.5 | Trace distribution records & quantity shipped | Supply chain | 2026-08-03 | 2026-08-05 | 3
2 | ◆ Recall team convened and shipments held |  | 2026-08-05 | 2026-08-05 |  | ◆
3 | Risk assessment & recall decision |  | 2026-08-04 | 2026-08-08 | 5
3.1 | Hazard characterisation | Technical lead | 2026-08-04 | 2026-08-05 | 2
3.2 | Exposure & severity assessment | Technical lead | 2026-08-05 | 2026-08-06 | 2
3.3 | Retain sample testing & verification | Lab | 2026-08-05 | 2026-08-08 | 4
3.4 | Classify recall severity level | Quality director | 2026-08-07 | 2026-08-07 | 1
3.5 | Determine depth of recall | Recall committee | 2026-08-07 | 2026-08-07 | 1
4 | ◆ Recall decision recorded |  | 2026-08-09 | 2026-08-09 |  |  | ◆
5 | Regulator notification |  | 2026-08-08 | 2026-08-17 | 10
5.1 | Confirm applicable authorities per market | Regulatory affairs | 2026-08-08 | 2026-08-09 | 2
5.2 | Confirm reporting window & content per jurisdiction | Legal | 2026-08-08 | 2026-08-09 | 2
5.3 | Prepare regulator notification pack | Regulatory affairs | 2026-08-09 | 2026-08-10 | 2
5.4 | Submit primary market notification | Regulatory affairs | 2026-08-10 | 2026-08-10 | 1
5.5 | Submit secondary market notifications | Regulatory affairs | 2026-08-11 | 2026-08-13 | 3
5.6 | Agree public notice wording with regulator | Regulatory affairs | 2026-08-11 | 2026-08-14 | 4
6 | ◆ Regulators notified |  | 2026-08-15 | 2026-08-15 |  |  | ◆
7 | Customer & public notification |  | 2026-08-12 | 2026-08-25 | 14
7.1 | Draft notification letters & press release | Communications | 2026-08-10 | 2026-08-12 | 3
7.2 | Notify distributors & wholesalers | Sales | 2026-08-15 | 2026-08-16 | 2
7.3 | Notify retailers & instruct stock removal | Sales | 2026-08-16 | 2026-08-18 | 3
7.4 | Direct customer contact from sales records | Customer service | 2026-08-16 | 2026-08-21 | 6
7.5 | Publish public notice & website banner | Communications | 2026-08-16 | 2026-08-17 | 2
7.6 | Stand up customer contact line & scripts | Customer service | 2026-08-15 | 2026-08-18 | 4
8 | ◆ Public notice issued |  | 2026-08-18 | 2026-08-18 |  |  |  | ◆
9 | Retrieval, quarantine & disposition |  | 2026-08-18 | 2026-09-26 | 40
9.1 | Set up return logistics & carrier instructions | Logistics | 2026-08-16 | 2026-08-20 | 5
9.2 | Receive returned stock & log by lot | Warehouse | 2026-08-21 | 2026-09-19 | 30
9.3 | Secure quarantine area & segregation controls | Warehouse | 2026-08-19 | 2026-08-24 | 6
9.4 | Reconcile returns against quantity distributed | Supply chain | 2026-09-01 | 2026-09-22 | 22
9.5 | Disposition decision — rework, destroy or release | Quality director | 2026-09-21 | 2026-09-26 | 6
9.6 | Witnessed destruction & certificates | Quality | 2026-09-27 | 2026-10-04 | 8
10 | ◆ Quantity reconciliation complete |  | 2026-09-27 | 2026-09-27 | [9 empty] | ◆
11 | Effectiveness checks, root cause & closure |  | 2026-08-24 | 2026-11-01 | 70
11.1 | Effectiveness check round 1 | Quality | 2026-08-24 | 2026-08-29 | 6
11.2 | Effectiveness check round 2 | Quality | 2026-09-11 | 2026-09-16 | 6
11.3 | Effectiveness check round 3 | Quality | 2026-10-03 | 2026-10-08 | 6
11.4 | Root cause investigation | Engineering | 2026-08-22 | 2026-09-20 | 30
11.5 | Corrective & preventive action plan | Quality director | 2026-09-21 | 2026-10-15 | 25
11.6 | Interim status reports to regulator | Regulatory affairs | 2026-08-27 | 2026-10-25 | 60
11.7 | Final recall report submitted | Regulatory affairs | 2026-10-21 | 2026-10-28 | 8
11.8 | Lessons learned & mock recall scheduled | Recall coordinator | 2026-10-26 | 2026-11-01 | 7
12 | ◆ Recall closed by regulator |  | 2026-11-02 | 2026-11-02 | [14 empty] | ◆