## Slide 1
QA Test Plan Schedule
Free Gantt chart template · gantts.app

## Slide 2
QA Test Plan Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Test planning & criteria
Test strategy & scope definition
Risk-based test prioritisation
Define entry & exit criteria per phase
Test estimation & resource plan
Defect management process & triage rules
◆ Test plan and criteria approved
Environment & test data readiness
Test environment build & provisioning
Environment configuration & integration stubs
Test data requirements defined
Test data extraction & masking
Test accounts, roles & access setup
Environment smoke test & sign-off
◆ Environment entry criteria met
Test design & automation
Test condition & scenario design
Test case authoring
Requirements traceability matrix
Automation framework setup
Regression suite automation build
Performance test script development
◆ Test cases ready for execution
Execution — unit, integration, system
Unit & component test execution
Integration & interface testing
System test execution wave 1
System test execution wave 2
Security testing
◆ System test exit criteria met
Defect triage, fix & retest loop
Daily defect triage & severity assignment
Defect fix cycles
Retest & verification of fixes
Regression impact assessment per fix
Deferred defect review & disposition
Defect discovery rate trend reporting
◆ Defect thresholds met
UAT, regression & release readiness
UAT preparation & business user onboarding
UAT execution
UAT defect resolution
Code freeze for regression
Full regression run
Performance & load test execution
Release readiness review
Test closure report & lessons learned
◆ Release sign-off
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Test planning & criteria |  | 2026-08-02 | 2026-08-31 | 30 | 100%
1.1 | Test strategy & scope definition | Test manager | 2026-08-02 | 2026-08-11 | 10 | 100%
1.2 | Risk-based test prioritisation | Test manager | 2026-08-10 | 2026-08-17 | 8 | 100%
1.3 | Define entry & exit criteria per phase | Test manager | 2026-08-14 | 2026-08-21 | 8 | 100%
1.4 | Test estimation & resource plan | Test manager | 2026-08-18 | 2026-08-25 | 8 | 100%
1.5 | Defect management process & triage rules | QA lead | 2026-08-20 | 2026-08-27 | 8 | 100%
2 | Test plan and criteria approved |  | 2026-09-01 | 2026-09-01 | — | —
3 | Environment & test data readiness |  | 2026-08-22 | 2026-09-30 | 40 | 80%
3.1 | Test environment build & provisioning | DevOps | 2026-08-22 | 2026-09-15 | 25 | 100%
3.2 | Environment configuration & integration stubs | DevOps | 2026-09-06 | 2026-09-23 | 18 | 80%
3.3 | Test data requirements defined | QA lead | 2026-08-30 | 2026-09-10 | 12 | 100%
3.4 | Test data extraction & masking | Data team | 2026-09-11 | 2026-09-28 | 18 | 50%
3.5 | Test accounts, roles & access setup | DevOps | 2026-09-16 | 2026-09-25 | 10 | 30%
3.6 | Environment smoke test & sign-off | QA lead | 2026-09-26 | 2026-09-30 | 5 | 0%
4 | Environment entry criteria met |  | 2026-10-01 | 2026-10-01 | — | —
5 | Test design & automation |  | 2026-09-01 | 2026-10-25 | 55 | 40%
5.1 | Test condition & scenario design | Test analysts | 2026-09-01 | 2026-09-25 | 25 | 70%
5.2 | Test case authoring | Test analysts | 2026-09-16 | 2026-10-15 | 30 | 40%
5.3 | Requirements traceability matrix | Test manager | 2026-09-21 | 2026-10-15 | 25 | 20%
5.4 | Automation framework setup | Automation engineer | 2026-09-06 | 2026-10-05 | 30 | 50%
5.5 | Regression suite | Automation engineer | 2026-10-01 | 2026-11-14 | 45 | 10%

## Slide 4
 | automation build |  |  |  |  | 
5.6 | Performance test script development | Performance engineer | 2026-10-06 | 2026-11-04 | 30 | 0%
6 | Test cases ready for execution |  | 2026-10-26 | 2026-10-26 | — | —
7 | Execution — unit, integration, system |  | 2026-10-01 | 2027-01-03 | 95 | 0%
7.1 | Unit & component test execution | Developers | 2026-10-01 | 2026-11-04 | 35 | 0%
7.2 | Integration & interface testing | Test analysts | 2026-10-21 | 2026-12-04 | 45 | 0%
7.3 | System test execution wave 1 | Test analysts | 2026-11-10 | 2026-12-09 | 30 | 0%
7.4 | System test execution wave 2 | Test analysts | 2026-11-30 | 2026-12-29 | 30 | 0%
7.5 | Security testing | Security tester | 2026-11-20 | 2026-12-14 | 25 | 0%
8 | System test exit criteria met |  | 2027-01-04 | 2027-01-04 | — | —
9 | Defect triage, fix & retest loop |  | 2026-10-06 | 2027-02-02 | 120 | 0%
9.1 | Daily defect triage & severity assignment | Triage board | 2026-10-06 | 2027-01-28 | 115 | 0%
9.2 | Defect fix cycles | Developers | 2026-10-16 | 2027-01-28 | 105 | 0%
9.3 | Retest & verification of fixes | Test analysts | 2026-10-26 | 2027-01-28 | 95 | 0%
9.4 | Regression impact assessment per fix | QA lead | 2026-11-05 | 2027-01-28 | 85 | 0%
9.5 | Deferred defect review & disposition | Product owner | 2026-12-30 | 2027-01-18 | 20 | 0%
9.6 | Defect discovery rate trend reporting | Test manager | 2026-10-31 | 2027-01-28 | 90 | 0%
10 | Defect thresholds met |  | 2027-02-03 | 2027-02-03 | — | —
11 | UAT, regression & release readiness |  | 2026-12-30 | 2027-03-14 | 75 | 0%
11.1 | UAT preparation & business user onboarding | Business analyst | 2026-12-25 | 2027-01-08 | 15 | 0%
11.2 | UAT execution | Business users | 2027-01-09 | 2027-02-07 | 30 | 0%
11.3 | UAT defect resolution | Developers | 2027-01-24 | 2027-02-14 | 22 | 0%
11.4 | Code freeze for regression | Release manager | 2027-02-08 | 2027-02-09 | 2 | 0%
11.5 | Full regression run | Automation engineer | 2027-02-10 | 2027-02-27 | 18 | 0%
11.6 | Performance & load test | Performance engineer | 2027-02-08 | 2027-02-27 | 20 | 0%

## Slide 5
 | execution |  |  |  |  | 
11.7 | Release readiness review | Release manager | 2027-03-02 | 2027-03-06 | 5 | 0%
11.8 | Test closure report & lessons learned | Test manager | 2027-03-05 | 2027-03-12 | 8 | 0%
12 | Release sign-off |  | 2027-03-15 | 2027-03-15 | — | —