## Gantt
QA Test Plan Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22
1 | Test planning & criteria |  | 2026-08-02 | 2026-08-31 | 30
1.1 | Test strategy & scope definition | Test manager | 2026-08-02 | 2026-08-11 | 10
1.2 | Risk-based test prioritisation | Test manager | 2026-08-10 | 2026-08-17 | 8
1.3 | Define entry & exit criteria per phase | Test manager | 2026-08-14 | 2026-08-21 | 8
1.4 | Test estimation & resource plan | Test manager | 2026-08-18 | 2026-08-25 | 8
1.5 | Defect management process & triage rules | QA lead | 2026-08-20 | 2026-08-27 | 8
2 | ◆ Test plan and criteria approved |  | 2026-09-01 | 2026-09-01 | [5 empty] | ◆
3 | Environment & test data readiness |  | 2026-08-22 | 2026-09-30 | 40
3.1 | Test environment build & provisioning | DevOps | 2026-08-22 | 2026-09-15 | 25
3.2 | Environment configuration & integration stubs | DevOps | 2026-09-06 | 2026-09-23 | 18
3.3 | Test data requirements defined | QA lead | 2026-08-30 | 2026-09-10 | 12
3.4 | Test data extraction & masking | Data team | 2026-09-11 | 2026-09-28 | 18
3.5 | Test accounts, roles & access setup | DevOps | 2026-09-16 | 2026-09-25 | 10
3.6 | Environment smoke test & sign-off | QA lead | 2026-09-26 | 2026-09-30 | 5
4 | ◆ Environment entry criteria met |  | 2026-10-01 | 2026-10-01 | [9 empty] | ◆
5 | Test design & automation |  | 2026-09-01 | 2026-10-25 | 55
5.1 | Test condition & scenario design | Test analysts | 2026-09-01 | 2026-09-25 | 25
5.2 | Test case authoring | Test analysts | 2026-09-16 | 2026-10-15 | 30
5.3 | Requirements traceability matrix | Test manager | 2026-09-21 | 2026-10-15 | 25
5.4 | Automation framework setup | Automation engineer | 2026-09-06 | 2026-10-05 | 30
5.5 | Regression suite automation build | Automation engineer | 2026-10-01 | 2026-11-14 | 45
5.6 | Performance test script development | Performance engineer | 2026-10-06 | 2026-11-04 | 30
6 | ◆ Test cases ready for execution |  | 2026-10-26 | 2026-10-26 | [13 empty] | ◆
7 | Execution — unit, integration, system |  | 2026-10-01 | 2027-01-03 | 95
7.1 | Unit & component test execution | Developers | 2026-10-01 | 2026-11-04 | 35
7.2 | Integration & interface testing | Test analysts | 2026-10-21 | 2026-12-04 | 45
7.3 | System test execution wave 1 | Test analysts | 2026-11-10 | 2026-12-09 | 30
7.4 | System test execution wave 2 | Test analysts | 2026-11-30 | 2026-12-29 | 30
7.5 | Security testing | Security tester | 2026-11-20 | 2026-12-14 | 25
8 | ◆ System test exit criteria met |  | 2027-01-04 | 2027-01-04 | [23 empty] | ◆
9 | Defect triage, fix & retest loop |  | 2026-10-06 | 2027-02-02 | 120
9.1 | Daily defect triage & severity assignment | Triage board | 2026-10-06 | 2027-01-28 | 115
9.2 | Defect fix cycles | Developers | 2026-10-16 | 2027-01-28 | 105
9.3 | Retest & verification of fixes | Test analysts | 2026-10-26 | 2027-01-28 | 95
9.4 | Regression impact assessment per fix | QA lead | 2026-11-05 | 2027-01-28 | 85
9.5 | Deferred defect review & disposition | Product owner | 2026-12-30 | 2027-01-18 | 20
9.6 | Defect discovery rate trend reporting | Test manager | 2026-10-31 | 2027-01-28 | 90
10 | ◆ Defect thresholds met |  | 2027-02-03 | 2027-02-03 | [27 empty] | ◆
11 | UAT, regression & release readiness |  | 2026-12-30 | 2027-03-14 | 75
11.1 | UAT preparation & business user onboarding | Business analyst | 2026-12-25 | 2027-01-08 | 15
11.2 | UAT execution | Business users | 2027-01-09 | 2027-02-07 | 30
11.3 | UAT defect resolution | Developers | 2027-01-24 | 2027-02-14 | 22
11.4 | Code freeze for regression | Release manager | 2027-02-08 | 2027-02-09 | 2
11.5 | Full regression run | Automation engineer | 2027-02-10 | 2027-02-27 | 18
11.6 | Performance & load test execution | Performance engineer | 2027-02-08 | 2027-02-27 | 20
11.7 | Release readiness review | Release manager | 2027-03-02 | 2027-03-06 | 5
11.8 | Test closure report & lessons learned | Test manager | 2027-03-05 | 2027-03-12 | 8
12 | ◆ Release sign-off |  | 2027-03-15 | 2027-03-15 | [33 empty] | ◆