## Slide 1
Rail Signalling Upgrade Plan
Free Gantt chart template · gantts.app

## Slide 2
Rail Signalling Upgrade Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Scheme design
Feasibility & option selection
Signalling layout & scheme plan
Control tables & interface design
Design assurance & review
◆ Design accepted
Data preparation & FAT
Interlocking data preparation
Independent data checking
Simulation & offline proving
Factory acceptance testing
◆ FAT passed
Possession planning
Possession strategy
◆ Possession applications submitted
Timetable & diversionary planning
Bus replacement & customer comms
◆ Possessions confirmed
Enabling & installation
Cable routes & troughing
Location cases & lineside civils
Signal & point machine install
Pre-wiring & offline assembly
Possession 1: cutover wiring
Possession 2: apparatus changeover
Testing & commissioning
Wire count & installation checks
Principles testing
Functional & through testing
Driver route learning
◆ Go / no-go for commissioning
Commissioning possession
◆ System commissioned
Entry into service
Signal box handover & fallback
Fault-free running period
Safety case closure & as-builts
◆ In service
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Scheme design |  | 2026-08-02 | 2027-02-17 | 200 | 100%
1.1 | Feasibility & option selection | Sponsor | 2026-08-02 | 2026-09-25 | 55 | 100%
1.2 | Signalling layout & scheme plan | Design | 2026-09-16 | 2026-11-29 | 75 | 100%
1.3 | Control tables & interface design | Design | 2026-11-20 | 2027-01-28 | 70 | 100%
1.4 | Design assurance & review | Assurance | 2027-01-09 | 2027-02-17 | 40 | 100%
2 | Design accepted |  | 2027-02-18 | 2027-02-18 | , | ,
3 | Data preparation & FAT |  | 2027-02-18 | 2027-09-05 | 200 | 60%
3.1 | Interlocking data preparation | Data prep | 2027-02-18 | 2027-05-13 | 85 | 100%
3.2 | Independent data checking | Checker | 2027-04-24 | 2027-07-02 | 70 | 80%
3.3 | Simulation & offline proving | Test team | 2027-06-18 | 2027-08-01 | 45 | 40%
3.4 | Factory acceptance testing | Test team | 2027-07-23 | 2027-09-05 | 45 | 20%
4 | FAT passed |  | 2027-09-06 | 2027-09-06 | , | ,
5 | Possession planning |  | 2026-10-01 | 2027-07-27 | 300 | 70%
5.1 | Possession strategy | Planning | 2026-10-01 | 2026-11-19 | 50 | 100%
6 | Possession applications submitted |  | 2026-11-20 | 2026-11-20 | , | ,
6.1 | Timetable & diversionary planning | Planning | 2026-11-20 | 2027-03-29 | 130 | 90%
6.2 | Bus replacement & customer comms | Operations | 2027-03-30 | 2027-06-27 | 90 | 40%
7 | Possessions confirmed |  | 2027-07-28 | 2027-07-28 | , | ,
8 | Enabling & installation |  | 2027-05-29 | 2027-12-04 | 190 | 20%
8.1 | Cable routes & troughing | Civils | 2027-05-29 | 2027-08-26 | 90 | 45%
8.2 | Location cases & lineside civils | Civils | 2027-08-07 | 2027-10-15 | 70 | 10%

## Slide 4
8.3 | Signal & point machine install | Installation | 2027-09-11 | 2027-11-09 | 60 | 0%
8.4 | Pre-wiring & offline assembly | Installation | 2027-09-06 | 2027-10-30 | 55 | 0%
8.5 | Possession 1: cutover wiring | Installation | 2027-11-05 | 2027-11-07 | 3 | 0%
8.6 | Possession 2: apparatus changeover | Installation | 2027-11-25 | 2027-11-27 | 3 | 0%
9 | Testing & commissioning |  | 2027-11-07 | 2028-02-04 | 90 | 0%
9.1 | Wire count & installation checks | Tester | 2027-11-07 | 2027-12-01 | 25 | 0%
9.2 | Principles testing | Tester in charge | 2027-11-29 | 2027-12-28 | 30 | 0%
9.3 | Functional & through testing | Tester in charge | 2027-12-27 | 2028-01-20 | 25 | 0%
9.4 | Driver route learning | Operations | 2027-12-05 | 2028-01-18 | 45 | 0%
10 | Go / no-go for commissioning |  | 2028-01-22 | 2028-01-22 | , | ,
10.1 | Commissioning possession | All | 2028-01-29 | 2028-01-31 | 3 | 0%
11 | System commissioned |  | 2028-02-01 | 2028-02-01 | , | ,
12 | Entry into service |  | 2028-02-01 | 2028-03-31 | 60 | 0%
12.1 | Signal box handover & fallback | Operations | 2028-02-01 | 2028-02-14 | 14 | 0%
12.2 | Fault-free running period | Maintenance | 2028-02-03 | 2028-03-03 | 30 | 0%
12.3 | Safety case closure & as-builts | Assurance | 2028-02-23 | 2028-03-31 | 38 | 0%
13 | In service |  | 2028-04-01 | 2028-04-01 | , | ,