## Gantt
Rail Signalling Upgrade Plan
Made free at gantts.app, edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3
1 | Scheme design |  | 2026-08-02 | 2027-02-17 | 200
1.1 | Feasibility & option selection | Sponsor | 2026-08-02 | 2026-09-25 | 55
1.2 | Signalling layout & scheme plan | Design | 2026-09-16 | 2026-11-29 | 75
1.3 | Control tables & interface design | Design | 2026-11-20 | 2027-01-28 | 70
1.4 | Design assurance & review | Assurance | 2027-01-09 | 2027-02-17 | 40
2 | ◆ Design accepted |  | 2027-02-18 | 2027-02-18 | [29 empty] | ◆
3 | Data preparation & FAT |  | 2027-02-18 | 2027-09-05 | 200
3.1 | Interlocking data preparation | Data prep | 2027-02-18 | 2027-05-13 | 85
3.2 | Independent data checking | Checker | 2027-04-24 | 2027-07-02 | 70
3.3 | Simulation & offline proving | Test team | 2027-06-18 | 2027-08-01 | 45
3.4 | Factory acceptance testing | Test team | 2027-07-23 | 2027-09-05 | 45
4 | ◆ FAT passed |  | 2027-09-06 | 2027-09-06 | [58 empty] | ◆
5 | Possession planning |  | 2026-10-01 | 2027-07-27 | 300
5.1 | Possession strategy | Planning | 2026-10-01 | 2026-11-19 | 50
6 | ◆ Possession applications submitted |  | 2026-11-20 | 2026-11-20 | [16 empty] | ◆
6.1 | Timetable & diversionary planning | Planning | 2026-11-20 | 2027-03-29 | 130
6.2 | Bus replacement & customer comms | Operations | 2027-03-30 | 2027-06-27 | 90
7 | ◆ Possessions confirmed |  | 2027-07-28 | 2027-07-28 | [52 empty] | ◆
8 | Enabling & installation |  | 2027-05-29 | 2027-12-04 | 190
8.1 | Cable routes & troughing | Civils | 2027-05-29 | 2027-08-26 | 90
8.2 | Location cases & lineside civils | Civils | 2027-08-07 | 2027-10-15 | 70
8.3 | Signal & point machine install | Installation | 2027-09-11 | 2027-11-09 | 60
8.4 | Pre-wiring & offline assembly | Installation | 2027-09-06 | 2027-10-30 | 55
8.5 | Possession 1: cutover wiring | Installation | 2027-11-05 | 2027-11-07 | 3
8.6 | Possession 2: apparatus changeover | Installation | 2027-11-25 | 2027-11-27 | 3
9 | Testing & commissioning |  | 2027-11-07 | 2028-02-04 | 90
9.1 | Wire count & installation checks | Tester | 2027-11-07 | 2027-12-01 | 25
9.2 | Principles testing | Tester in charge | 2027-11-29 | 2027-12-28 | 30
9.3 | Functional & through testing | Tester in charge | 2027-12-27 | 2028-01-20 | 25
9.4 | Driver route learning | Operations | 2027-12-05 | 2028-01-18 | 45
10 | ◆ Go / no-go for commissioning |  | 2028-01-22 | 2028-01-22 | [77 empty] | ◆
10.1 | Commissioning possession | All | 2028-01-29 | 2028-01-31 | 3
11 | ◆ System commissioned |  | 2028-02-01 | 2028-02-01 | [79 empty] | ◆
12 | Entry into service |  | 2028-02-01 | 2028-03-31 | 60
12.1 | Signal box handover & fallback | Operations | 2028-02-01 | 2028-02-14 | 14
12.2 | Fault-free running period | Maintenance | 2028-02-03 | 2028-03-03 | 30
12.3 | Safety case closure & as-builts | Assurance | 2028-02-23 | 2028-03-31 | 38
13 | ◆ In service |  | 2028-04-01 | 2028-04-01 | [87 empty] | ◆