## Slide 1
Recruitment & Hiring Plan
Free Gantt chart template · gantts.app

## Slide 2
Recruitment & Hiring Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Role definition & approval
Business case & headcount request
Job description & scorecard
Level & salary banding
Headcount approval
◆ Requisition approved
Sourcing
◆ Job posting live
Advertising & job boards
Referral push
Direct sourcing & outreach
Agency briefing
Screening
Application review
Recruiter screens
Hiring manager screens
◆ Shortlist agreed
Interview loop
Panel scheduling
Structured interviews
Technical or functional exercise
Debrief sessions
Assessment & decision
Final panel
Scorecard consolidation
References & background checks
◆ Hiring decision
Offer & negotiation
Compensation approval
Verbal offer
Contract issued
Negotiation & counter-offer window
◆ Offer accepted
Notice period & pre-start
Candidate resignation & notice
Keep-warm contact
Right to work & compliance
Equipment & access setup
First-week plan handover
◆ Start date
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Role definition & approval |  | 2026-08-02 | 2026-08-22 | 21 | 100%
1.1 | Business case & headcount request | Hiring manager | 2026-08-02 | 2026-08-08 | 7 | 100%
1.2 | Job description & scorecard | Hiring manager | 2026-08-07 | 2026-08-13 | 7 | 100%
1.3 | Level & salary banding | HR | 2026-08-10 | 2026-08-15 | 6 | 100%
1.4 | Headcount approval | Finance | 2026-08-16 | 2026-08-22 | 7 | 100%
2 | Requisition approved |  | 2026-08-23 | 2026-08-23 | — | —
3 | Sourcing |  | 2026-08-23 | 2026-09-19 | 28 | 80%
4 | Job posting live |  | 2026-08-23 | 2026-08-23 | — | —
4.1 | Advertising & job boards | Recruiter | 2026-08-23 | 2026-09-16 | 25 | 100%
4.2 | Referral push | Recruiter | 2026-08-23 | 2026-09-05 | 14 | 100%
4.3 | Direct sourcing & outreach | Recruiter | 2026-08-26 | 2026-09-19 | 25 | 70%
4.4 | Agency briefing | Recruiter | 2026-08-26 | 2026-08-30 | 5 | 100%
5 | Screening |  | 2026-09-01 | 2026-09-24 | 24 | 50%
5.1 | Application review | Recruiter | 2026-09-01 | 2026-09-18 | 18 | 70%
5.2 | Recruiter screens | Recruiter | 2026-09-05 | 2026-09-20 | 16 | 50%
5.3 | Hiring manager screens | Hiring manager | 2026-09-13 | 2026-09-24 | 12 | 20%
6 | Shortlist agreed |  | 2026-09-25 | 2026-09-25 | — | —
7 | Interview loop |  | 2026-09-25 | 2026-10-20 | 26 | 0%
7.1 | Panel scheduling | Coordinator | 2026-09-25 | 2026-10-01 | 7 | 0%
7.2 | Structured interviews | Panel | 2026-10-01 | 2026-10-14 | 14 | 0%
7.3 | Technical or functional exercise | Panel | 2026-10-06 | 2026-10-15 | 10 | 0%

## Slide 4
7.4 | Debrief sessions | Panel | 2026-10-13 | 2026-10-20 | 8 | 0%
8 | Assessment & decision |  | 2026-10-19 | 2026-11-07 | 20 | 0%
8.1 | Final panel | Panel | 2026-10-19 | 2026-10-24 | 6 | 0%
8.2 | Scorecard consolidation | Recruiter | 2026-10-23 | 2026-10-27 | 5 | 0%
8.3 | References & background checks | HR | 2026-10-25 | 2026-11-07 | 14 | 0%
9 | Hiring decision |  | 2026-11-02 | 2026-11-02 | — | —
10 | Offer & negotiation |  | 2026-11-02 | 2026-11-22 | 21 | 0%
10.1 | Compensation approval | HR | 2026-11-02 | 2026-11-06 | 5 | 0%
10.2 | Verbal offer | Hiring manager | 2026-11-07 | 2026-11-08 | 2 | 0%
10.3 | Contract issued | HR | 2026-11-09 | 2026-11-12 | 4 | 0%
10.4 | Negotiation & counter-offer window | Recruiter | 2026-11-11 | 2026-11-22 | 12 | 0%
11 | Offer accepted |  | 2026-11-23 | 2026-11-23 | — | —
12 | Notice period & pre-start |  | 2026-11-23 | 2027-01-13 | 52 | 0%
12.1 | Candidate resignation & notice | Candidate | 2026-11-23 | 2027-01-06 | 45 | 0%
12.2 | Keep-warm contact | Hiring manager | 2026-11-28 | 2027-01-06 | 40 | 0%
12.3 | Right to work & compliance | HR | 2026-11-25 | 2026-12-14 | 20 | 0%
12.4 | Equipment & access setup | IT | 2026-12-25 | 2027-01-08 | 15 | 0%
12.5 | First-week plan handover | Hiring manager | 2027-01-01 | 2027-01-10 | 10 | 0%
13 | Start date |  | 2027-01-14 | 2027-01-14 | — | —