## Gantt
Recruitment & Hiring Plan
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18
1 | Role definition & approval |  | 2026-08-02 | 2026-08-22 | 21
1.1 | Business case & headcount request | Hiring manager | 2026-08-02 | 2026-08-08 | 7
1.2 | Job description & scorecard | Hiring manager | 2026-08-07 | 2026-08-13 | 7
1.3 | Level & salary banding | HR | 2026-08-10 | 2026-08-15 | 6
1.4 | Headcount approval | Finance | 2026-08-16 | 2026-08-22 | 7
2 | ◆ Requisition approved |  | 2026-08-23 | 2026-08-23 |  |  |  |  | ◆
3 | Sourcing |  | 2026-08-23 | 2026-09-19 | 28
4 | ◆ Job posting live |  | 2026-08-23 | 2026-08-23 |  |  |  |  | ◆
4.1 | Advertising & job boards | Recruiter | 2026-08-23 | 2026-09-16 | 25
4.2 | Referral push | Recruiter | 2026-08-23 | 2026-09-05 | 14
4.3 | Direct sourcing & outreach | Recruiter | 2026-08-26 | 2026-09-19 | 25
4.4 | Agency briefing | Recruiter | 2026-08-26 | 2026-08-30 | 5
5 | Screening |  | 2026-09-01 | 2026-09-24 | 24
5.1 | Application review | Recruiter | 2026-09-01 | 2026-09-18 | 18
5.2 | Recruiter screens | Recruiter | 2026-09-05 | 2026-09-20 | 16
5.3 | Hiring manager screens | Hiring manager | 2026-09-13 | 2026-09-24 | 12
6 | ◆ Shortlist agreed |  | 2026-09-25 | 2026-09-25 | [8 empty] | ◆
7 | Interview loop |  | 2026-09-25 | 2026-10-20 | 26
7.1 | Panel scheduling | Coordinator | 2026-09-25 | 2026-10-01 | 7
7.2 | Structured interviews | Panel | 2026-10-01 | 2026-10-14 | 14
7.3 | Technical or functional exercise | Panel | 2026-10-06 | 2026-10-15 | 10
7.4 | Debrief sessions | Panel | 2026-10-13 | 2026-10-20 | 8
8 | Assessment & decision |  | 2026-10-19 | 2026-11-07 | 20
8.1 | Final panel | Panel | 2026-10-19 | 2026-10-24 | 6
8.2 | Scorecard consolidation | Recruiter | 2026-10-23 | 2026-10-27 | 5
8.3 | References & background checks | HR | 2026-10-25 | 2026-11-07 | 14
9 | ◆ Hiring decision |  | 2026-11-02 | 2026-11-02 | [14 empty] | ◆
10 | Offer & negotiation |  | 2026-11-02 | 2026-11-22 | 21
10.1 | Compensation approval | HR | 2026-11-02 | 2026-11-06 | 5
10.2 | Verbal offer | Hiring manager | 2026-11-07 | 2026-11-08 | 2
10.3 | Contract issued | HR | 2026-11-09 | 2026-11-12 | 4
10.4 | Negotiation & counter-offer window | Recruiter | 2026-11-11 | 2026-11-22 | 12
11 | ◆ Offer accepted |  | 2026-11-23 | 2026-11-23 | [17 empty] | ◆
12 | Notice period & pre-start |  | 2026-11-23 | 2027-01-13 | 52
12.1 | Candidate resignation & notice | Candidate | 2026-11-23 | 2027-01-06 | 45
12.2 | Keep-warm contact | Hiring manager | 2026-11-28 | 2027-01-06 | 40
12.3 | Right to work & compliance | HR | 2026-11-25 | 2026-12-14 | 20
12.4 | Equipment & access setup | IT | 2026-12-25 | 2027-01-08 | 15
12.5 | First-week plan handover | Hiring manager | 2027-01-01 | 2027-01-10 | 10
13 | ◆ Start date |  | 2027-01-14 | 2027-01-14 | [24 empty] | ◆